## Template (Variances)
2023-2025 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiative Name | 2023 Planned Budget (as reported in the WMP Errata in 1,000s) | 2023 Actual Expenditure (in 1,000s) | Variance | Met Threshold for Variance Explanation (greater than 10%) | Detailed explanation of the reason for the discrepancy
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 1233980.7283 | 1128010 | -105970.7283 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 83418 | 27275 | -56143 | Yes | FTI's original forecast was based on high level estimates as the scope of the program was being developed. The actual costs in FTI stem from completing 266.6 circuit miles, while future years will 1,500 circuit miles.
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 405732.029 | 386980.266 | -18751.763 | No | *Costs associated with GM-03 have been shown in the QDR Activity "Equipment inspections, maintenance, and repair" in previously filed QDRs.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 53484 | 34947.3955 | -18536.6045 | Yes | TRI unit cost assumptions for the budget were based on historical EVM unit pricing. Actual unit pricing and units came in lower than planned.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | 23455 | 13279.931 | -10175.069 | Yes | VMOM achieved a lower unit cost than originally planned, as well as a lower number of trees to mitigate were identified during the inspections than originally planned.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 27962.0933 | 18258 | -9704.0933 | Yes | Was able to achieve execution efficiencies by bundling fuse replacements with other projects, reducing the overall cost while completing the targeted units.
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | 14931.7992 | 11326.7317 | -3605.0675 | Yes | Reduced marketing, material and labor costs for customer outreach activities.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 12679.2 | 9252.7 | -3426.5 | Yes | PG&E was able to achieve a lower unit cost for IVM related work than previously forecasted while completing the unit target.
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 5620 | 3008 | -2612 | Yes | Original high level forecast included a 20% contingency estimate that was not fully utilized during the course of execution.
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 5006 | 2423 | -2583 | Yes | Discrepancy driven through increased efficiency within the program to track field quality control work and execute work with greater controls
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | 4119 | 1736 | -2383 | Yes | No actual Wildfire events/Wildfire EOC activations to respond to due to favorable weather. Wildfire emergency response forecast accuracy is highly challenging due to many unknown factors and highly dependent on weather conditions. The actuals are reflecting only the base Wildfire work that continues to happen each year with training, exercises, seminars, and emergency plan updates and maintenance. The estimate annual run rate is about $2M. The reason last year actuals is lower because we had only Tabletop exercise instead of a full scope exercise. The year will be a combined WF and PSPS full scope exercise, which means everyone comes in and participates as if in a real world event.
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 5000 | 2673 | -2327 | Yes | Reduced costs by collaboratively identifying efficiencies working with tag crews and leveraging existing clearances.
Target | Grid Design, Operations and Maintenance | 8.1.8.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 41301.1159 | 39290 | -2011.1159 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 2826.0332 | 1083.5342 | -1742.499 | Yes | Technology updates allowed us to become more efficiency and not have to utilize as many contractors in order to complete inspections.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 10163 | 8575.303 | -1587.697 | Yes | PG&E's original 2023 financial forecast for LiDAR included the total projected cost for the vendor contract, which sought to do additional LiDAR inspections above and beyond the VM-01 target. The $8.6 million actual expenditure represents the cost of PG&E completing the VM-01 target.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 3169.8 | 1809.29 | -1360.51 | Yes | Was able to achieve execution efficiencies by bundling MSO replacements with other work, reducing the number of crew mobilizations resulting in lower overall cost while completing the targeted units.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 10177.4132 | 9168.7073 | -1008.7059 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 2596.8896 | 1605.8621 | -991.0275 | Yes | Technology updates allowed us to become more efficiency and not have to utilize as many contractors in order to complete inspections.
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 999.92 | 180 | -819.92 | Yes | 2023 budget was based on a high level forecast developed as the program was stood up. PG&E completed its WMP target units at a lower cost than expected, partially due to pre-construction and engineering being completed in 2022.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1906.6667 | 1321.5244 | -585.1423 | Yes | Costs significantly lower than planned due to internal resources replacing contractors.
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 819.671 | 262.268 | -557.403 | Yes | Materially lower Business Energy Solutions (BES) labor costs than originally planned due to the low number of PSPS events.
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 12679.2 | 12151.24 | -527.96 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1181.6663 | 744.5437 | -437.1225 | Yes | Costs significantly lower than planned, due to internal resource replacing contractor. Enhanced switchyard inspections lower than planned attributed to System Inspection’s ability to inspect more efficiently requiring less hours from System Inspection and Hydro O&M resources.
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 999.6568 | 644 | -355.6568 | Yes | 2023 budget was based on a high level forecast developed as the program was stood up. PG&E completed its WMP target units at a lower cost than expected, partially due to pre-construction and engineering being completed in 2022.
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | 11834.5776 | 11580.847 | -253.7306 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 17049.5 | 16818.3226 | -231.1774 | No
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 10800 | 10610.0236 | -189.9764 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | 3496.1115 | 3404.964 | -91.1475 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 16913.4639 | 16894.164 | -19.2999 | No
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | 0 | 0 | 0 | No | PSPS drone pilot will begin in 2024. No costs in 2023.
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 1100 | 1502 | 402 | Yes | The original 2023 forecast was based on an initial high-level estimate, contract and execution with chosen vendor led to additional costs.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 1100 | 1577 | 477 | Yes | Original forecast was based on unit cost data from early 2022 and did not account for changes in the methods of infrared inspection.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 407.602 | 959 | 551.398 | Yes | Increased precipitation in 2023 resulted in increase vegetation growth requiring crews to conduct brush clearing multiple times at the same location to maintain adequate defensible space.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2521.7317 | 3374.6762 | 852.9445 | Yes | Increased precipitation in 2023 resulted in increase vegetation growth requiring crews to conduct brush clearing multiple times at the same location to maintain adequate defensible space.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 3796.5281 | 5190 | 1393.4719 | Yes | Additional 2023 expenditures due to higher unit cost driven by transitioning to new regional vendors.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 1438 | 2937 | 1499 | Yes | Execution resources were allocated to storm response in the 1st quarter leading to a compressed timeline for execution prior to fire season resulting increased overtime and double-time costs.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 21727.6 | 23798.349 | 2070.749 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 1873.4397 | 4847 | 2973.5603 | Yes | GM-01 was updated during through the Revision Notice resulting increased scope and additional cost.
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 14134.1732 | 17282 | 3147.8268 | Yes | Costs for transmission hardening increased over the original forecast due to three major drivers: -Access roads needed improvement requiring civil construction work such as grading and/or gravel. -Increased use of helicopter required to continue construction due to inclement weather and wet access roads. -Clearance cancellations due to inclement weather resulted in extra mobilizations.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 1000 | 4210.26 | 3210.26 | Yes | The initial 2023 forecasts for transmission second patrol used a high level forecast based on helicopter based patrols in 2022. The actual expenditures reflect PG&E's use of additional patrol technology (e.g. LiDAR) and increased volume of inspections.
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | 5970 | 11424 | 5454 | Yes | Discrepancy driven by volume of additional units completed compared to forecast due to commitments related to pass rates
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program |  | 7168 | 7168 | No | The cost of the distribution aerial pilot was not included in the expenditure forecast provided in the original 2023-2025 WMP.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 23422.894 | 30821 | 7398.106 | Yes | Execution resources were allocated to storm response in the 1st quarter leading to a compressed timeline for execution resulting increased overtime and double-time costs. Furthermore, the expanded use of contractors to complete inspections required increased support from inspection review specialists.
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 140973.8 | 150472.56 | 9498.76 | No
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 451132.103 | 461862.848 | 10730.745 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 8783.5603 | 22725 | 13941.4397 | Yes | Target GM-09 was created through the Revision Notice process and increased the scope of the program resulting in higher costs.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 18000 | 35300.1363 | 17300.1363 | Yes | Variance is attributable to increased requirements and demand, which included increasing demand on O&M support including Live Help Desk, additional licenses purchased for end users of Routine/2nd Patrol, implementation of VC Pole Clearing Program to meet regulatory commitments, requirements and user story writing in addition to the PMO and Focus Tree Inspection enhancements. The costs associated with completing the VM-20 and VM-21 objectives have been captured here as part of the development costs of the overall One VM application.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 100616.61 | 125147.637 | 24531.027 | Yes | Primarily attributable to more additional tree work identified based on revised inspection procedure to include non-dead and dying units.
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 67504.2203 | 125029 | 57524.7797 | Yes | Increased volume of overhead miles completed 157.7 miles compared to the original plan of 140 miles coupled with higher units cost led to overall expenditures. *The GH-01 target includes both overhead and underground miles. To prevent double counting costs, the expenditures related to underground work are shown in GH-04.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 711944.189 | 785445.77 | 73501.581 | Yes | Driven by an increased average cost per unit as the program incurred additional T&M costs related to contractor change-outs and additional support costs (increased SVMI headcount, training/assessment yards and constraint resolution), partly offset by decreased volume of tree work due to efforts to maintain 2023 costs to the Veg Management budget.
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | See detailed explanation | See detailed explanation |  | No | Costs associated with PSPS table top exercises are captured in EP-02.
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | PCC Costs | PCC Costs |  | No
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | PCC Costs | PCC Costs |  | No
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | PCC Costs | PCC Costs |  | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | PCC Costs | PCC Costs |  | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | See detailed explanation | See detailed explanation |  | No | Costs associated with achieving objective GM-08 are captured in target GM-03.
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | PCC Costs | PCC Costs |  | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | PCC Costs | PCC Costs |  | No
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | See detailed explanation | See detailed explanation |  | No | Costs associated with achieving PS-07 are captured in GH-01: System Hardening - Distribution and GH-04: 10K Undergrounding targets.
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | See detailed explanation | See detailed explanation |  | No | Costs associated with achieving PS-07 are captured in GH-01: System Hardening - Distribution and GH-04: 10K Undergrounding targets.
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | PCC Costs | PCC Costs |  | No
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | See detailed explanation | See detailed explanation |  | No | Budget and actuals for SA-05 are captured in the figures provided in SA-04.
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | PCC Costs | PCC Costs |  | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | PCC Costs | PCC Costs |  | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | PCC Costs | PCC Costs |  | No
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | PCC Costs | PCC Costs |  | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | See detailed explanation | See detailed explanation |  | No | Expenditures for activities associated with VM-10 are captured in the individual vegetation management program costs.
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | See detailed explanation | See detailed explanation |  | No | Expenditures for VM-11 are captured in the costs associated with the FTI program shown in VM-03.
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | PCC Costs | PCC Costs |  | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | See detailed explanation | See detailed explanation |  | No | Costs for VM-20 are captured in the development costs of the One VM application.
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | See detailed explanation | See detailed explanation |  | No | Costs for VM-21 are captured in the development costs of the One VM application.
Total | [5 empty] | 3601748.9869 | 3596387.8546 | -5361.1322