## Q2 a-k
PG&E 2024-2026 Undergrounding, Line Removal, and Community Rebuild Workplan
Data as of Feb 22, 2024
[14 empty] | 1463.6684 | 8.4971 | 289.7053 | 29.0958 | 327.2982 | 239.5785 | 846.1565 | 50.6352 | 1136.3702
Order | Category | Circuit ID | Circuit Name | Circuit Protection zone | County | Applicable Risk Model | Applicable Risk Score | Est. Construction Start Date | Est. Construction End Date | MAT Code | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - 2024 Planned Miles | UG - 2024 Planned Miles | Removal - 2024 Planned Miles | 2024 Total Planned Miles | OH - 2025-2026 Forecast Miles | UG - 2025-2026 Forecast Miles | Removal - 2025-2026 Forecast Miles | 2025-2026 Total Forecast Miles
35056808 | Other | 42571102 | MOLINO 1102 | MOLINO 110266006 | SONOMA | v2 | 534 | 2024-03-16 | 2024 | 30A | 0 | 1.5138 | 0 | 1.5138 | 0 | 1.5138 | 0 | 1.5138 | 0 | 0 | 0 | 0
35134959 | Other | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 1101CB | CALAVERAS | v2 | 322 | Not Available | 2024 | 06A | 1.3562 | 0.34337 | 0 | 1.6996 | 1.3562 | 0.34337 | 0 | 1.6996 | 0 | 0 | 0 | 0
35145540 | Base SH | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | CALAVERAS | v2 | 1316 | 2023-09-11 | 2024 | 08W | 0.61212 | 0.53447 | 0 | 1.1466 | 0.61212 | 0.53447 | 0 | 1.1466 | 0 | 0 | 0 | 0
35174478 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2025-03-06 08:00 | 2025 | 08W | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 1.04
35174501 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2024-12-18 08:00 | 2025 | 08W | 0 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0 | 0 | 0 | 3.8303 | 0 | 3.8303
35192282 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | LAKE | v2 | 468 | 2025-05-16 08:00 | 2025 | 08W | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04
35217268 | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | PLUMAS | v2 | 11 | 2023-09-01 | 2024 | 08W | 0 | 0.017803 | 0 | 0.017803 | 0 | 0.017803 | 0 | 0.017803 | 0 | 0 | 0 | 0
35219276 | Base SH | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SOLANO | v2 | 42 | 2023-03-16 | 2024 | 08W | 0 | 2.0733 | 0 | 2.0733 | 0 | 2.0733 | 0 | 2.0733 | 0 | 0 | 0 | 0
35219289 | Base SH | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SHASTA | v2 | 49 | 2024-03-04 08:00 | 2024 | 08W | 0.019697 | 7.0055 | 2.9064 | 9.9316 | 0.019697 | 7.0055 | 2.9064 | 9.9316 | 0 | 0 | 0 | 0
35223063 | Base SH | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | SONOMA | v2 | 2048 | 2023-10-15 | 2024 | 08W | 0 | 0.20019 | 0 | 0.20019 | 0 | 0.20019 | 0 | 0.20019 | 0 | 0 | 0 | 0
35224712 | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | PLUMAS | v2 | 11 | 2023-05-31 | 2024 | 08W | 0 | 0.57727 | 0 | 0.57727 | 0 | 0.57727 | 0 | 0.57727 | 0 | 0 | 0 | 0
35224713 | Fire Rebuild | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | PLUMAS | v2 | 11 | 2022-12-22 | 2024 | 08W | 0 | 1.8095 | 0 | 1.8095 | 0 | 1.8095 | 0 | 1.8095 | 0 | 0 | 0 | 0
35224856 | Other | 102831104 | PARADISE 1104 | PARADISE 11042034 | BUTTE | v2 | 1537 | 2023-08-15 | 2024 | 10K | 0 | 0.11496 | 0 | 0.11496 | 0 | 0.11496 | 0 | 0.11496 | 0 | 0 | 0 | 0
35226628 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011586 | SHASTA | v2 | 7 | 2024-04-15 08:00 | 2024 | 08W | 0 | 0.85511 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0 | 0
35226629 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011586 | SHASTA | v2 | 7 | 2024-04-15 08:00 | 2024 | 08W | 0 | 4.8061 | 0 | 4.8061 | 0 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0 | 0
35226857 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2025-03-28 08:00 | 2025 | 08W | 0 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0 | 0 | 0 | 1.1449 | 0 | 1.1449
35227007 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2025-02-27 08:00 | 2025 | 08W | 0 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 2.8756
35227160 | Base SH | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | LAKE | v2 | 8 | 2025-05-07 08:00 | 2025 | 08W | 0.10019 | 1.5888 | 0 | 1.689 | 0 | 0 | 0 | 0 | 0.10019 | 1.5888 | 0 | 1.689
35228774 | Base SH | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | SONOMA | v2 | 2048 | 2024-03-11 08:00 | 2024 | 08W | 0 | 1.0562 | 0 | 1.0562 | 0 | 1.0562 | 0 | 1.0562 | 0 | 0 | 0 | 0
35228775 | Base SH | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | SONOMA | v2 | 2048 | 2024-07-30 08:00 | 2025 | 08W | 0 | 1.0708 | 0 | 1.0708 | 0 | 0 | 0 | 0 | 0 | 1.0708 | 0 | 1.0708
35231620 | Base SH | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | LAKE | v2 | 27 | 2024-12-02 08:00 | 2025 | 08W | 0 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 2.6782
35231621 | Base SH | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | LAKE | v2 | 27 | 2024-12-02 08:00 | 2025 | 08W | 0 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0 | 0 | 0 | 2.8943 | 0 | 2.8943
35233948 | Base SH | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SHASTA | v2 | 49 | 2024-05-31 08:00 | 2024 | 08W | 0.031629 | 4.7536 | 1.1729 | 5.9581 | 0.031629 | 4.7536 | 1.1729 | 5.9581 | 0 | 0 | 0 | 0
35233950 | Base SH | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SHASTA | v2 | 49 | 2024-07-30 08:00 | 2024 | 08W | 0.039015 | 4.6155 | 1.9937 | 6.6483 | 0.039015 | 4.6155 | 1.9937 | 6.6483 | 0 | 0 | 0 | 0
35234756 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2025-02-18 08:00 | 2025 | 08W | 0 | 2.782 | 0 | 2.782 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 2.782
35234865 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2024-06-19 08:00 | 2024 | 08W | 0 | 1.0684 | 0 | 1.0684 | 0 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0 | 0
35236439 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2022-08-01 | 2024 | 08W | 0 | 0.047348 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0 | 0 | 0
35236985 | Fire Rebuild | 103221101 | KANAKA 1101 | KANAKA 1101CB | BUTTE | v2 | 1480 | 2024-10-03 08:00 | 2025 | 08W | 0 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0 | 0 | 0 | 2.0655 | 0 | 2.0655
35254067 | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | EL DORADO | v2 | 68 | 2025-01-31 08:00 | 2025 | 08W | 0 | 0.58011 | 0 | 0.58011 | 0 | 0 | 0 | 0 | 0 | 0.58011 | 0 | 0.58011
35274589 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | MARIPOSA | v2 | 428 | 2024-03-05 08:00 | 2024 | 08W | 0 | 2.6763 | 0 | 2.6763 | 0 | 2.6763 | 0 | 2.6763 | 0 | 0 | 0 | 0
35278093 | Base SH | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | FRESNO | v2 | 163 | 2024-05-20 08:00 | 2025 | 08W | 0 | 0.41496 | 0 | 0.41496 | 0 | 0 | 0 | 0 | 0 | 0.41496 | 0 | 0.41496
35278890 | Base SH | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | FRESNO | v2 | 163 | 2024-07-09 08:00 | 2025 | 08W | 1.5542 | 0.12235 | 0 | 1.6765 | 0 | 0 | 0 | 0 | 1.5542 | 0.12235 | 0 | 1.6765
35279181 | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v2 | 378 | 2023-09-06 | 2024 | 08W | 0 | 6.786 | 0 | 6.786 | 0 | 6.786 | 0 | 6.786 | 0 | 0 | 0 | 0
35279182 | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v2 | 378 | 2024-09-05 08:00 | 2024 | 08W | 0 | 2.4947 | 0 | 2.4947 | 0 | 2.4947 | 0 | 2.4947 | 0 | 0 | 0 | 0
35279307 | Fire Rebuild | 103021101 | GANSNER 1101 | GANSNER 11012424 | PLUMAS | v2 | 1172 | 2024-04-25 08:00 | 2024 | 08W | 0 | 3.415 | 0 | 3.415 | 0 | 3.415 | 0 | 3.415 | 0 | 0 | 0 | 0
35280362 | Base SH | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | MARIPOSA | v2 | 50 | 2024-04-18 08:00 | 2024 | 08W | 0.028409 | 0.13258 | 0 | 0.16098 | 0.028409 | 0.13258 | 0 | 0.16098 | 0 | 0 | 0 | 0
35280496 | Fire Rebuild | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012056 | PLUMAS | v2 | 895 | 2024-10-02 08:00 | 2025 | 08W | 0 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0 | 0 | 0 | 0.82008 | 0 | 0.82008
35280499 | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v2 | 378 | 2023-10-02 | 2024 | 08W | 0 | 1.4023 | 0 | 1.4023 | 0 | 1.4023 | 0 | 1.4023 | 0 | 0 | 0 | 0
35280505 | Other | 103451101 | KESWICK 1101 | KESWICK 11019712 | SHASTA | v2 | 1614 | Not Available | 2024 | 30A | 0 | 0.37879 | 0 | 0.37879 | 0 | 0.37879 | 0 | 0.37879 | 0 | 0 | 0 | 0
35280560 | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v2 | 378 | 2024-07-12 | 2024 | 08W | 0 | 2.4705 | 0 | 2.4705 | 0 | 2.4705 | 0 | 2.4705 | 0 | 0 | 0 | 0
35281758 | Fire Rebuild | 102530401 | GRAYS FLAT 0401 | GRAYS FLAT 0401CB | PLUMAS | v2 | 1748 | 2024-06-04 08:00 | 2024 | 08W | 0 | 1.4 | 0 | 1.4 | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0
35283198 | Base SH | 43211101 | HARTLEY 1101 | HARTLEY 1101698 | LAKE | v2 | 58 | 2023-08-07 | 2024 | 08W | 0 | 0.29773 | 0 | 0.29773 | 0 | 0.29773 | 0 | 0.29773 | 0 | 0 | 0 | 0
35283346 | Base SH | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | v2 | 335 | 2023-06-23 | 2024 | 08W | 0 | 0.47822 | 0 | 0.47822 | 0 | 0.47822 | 0 | 0.47822 | 0 | 0 | 0 | 0
35283938 | Base SH | 24251101 | WOODSIDE 1101 | WOODSIDE 11018974 | SAN MATEO | v2 | 1145 | 2023-09-18 | 2024 | 08W | 0 | 0.39015 | 0 | 0.39015 | 0 | 0.39015 | 0 | 0.39015 | 0 | 0 | 0 | 0
35284023 | Fire Rebuild | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | SONOMA | v2 | 1684 | 2023-08-14 | 2024 | 08W | 0 | 1.1013 | 0 | 1.1013 | 0 | 1.1013 | 0 | 1.1013 | 0 | 0 | 0 | 0
35284365 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 1702CB | CALAVERAS | v2 | 235 | 2023-09-11 | 2024 | 08W | 0.074242 | 2.7547 | 0 | 2.829 | 0.074242 | 2.7547 | 0 | 2.829 | 0 | 0 | 0 | 0
35284810 | Fire Rebuild | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | SAN MATEO | v2 | 2186 | 2025-04-23 08:00 | 2025 | 08W | 0.037879 | 0.85814 | 0 | 0.89602 | 0 | 0 | 0 | 0 | 0.037879 | 0.85814 | 0 | 0.89602
35285249 | Base SH | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | v2 | 335 | 2023-07-24 | 2024 | 08W | 0 | 0.16629 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0 | 0
35285251 | Base SH | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | v2 | 335 | 2024-01-08 | 2024 | 08W | 0.20777 | 0.41799 | 0 | 0.62576 | 0.20777 | 0.41799 | 0 | 0.62576 | 0 | 0 | 0 | 0
35290504 | Base SH | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | MENDOCINO | v2 | 75 | 2024-11-07 08:00 | 2025 | 08W | 0 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0 | 0 | 0 | 1.0436 | 0 | 1.0436
35290508 | Base SH | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | MENDOCINO | v2 | 75 | 2024-10-01 08:00 | 2025 | 08W | 0 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0.62008
35290510 | Base SH | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | LAKE | v2 | 75 | 2024-10-21 08:00 | 2025 | 08W | 0 | 0.55303 | 0 | 0.55303 | 0 | 0 | 0 | 0 | 0 | 0.55303 | 0 | 0.55303
35290544 | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | v2 | 995 | 2023-05-22 | 2024 | 08W | 0 | 0.020265 | 0 | 0.020265 | 0 | 0.020265 | 0 | 0.020265 | 0 | 0 | 0 | 0
35292784 | Fire Rebuild | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v2 | 378 | 2024-10-17 08:00 | 2025 | 08W | 0 | 3.1443 | 0 | 3.1443 | 0 | 0 | 0 | 0 | 0 | 3.1443 | 0 | 3.1443
35292788 | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012476 | PLUMAS | v2 | 2342 | 2024-09-12 08:00 | 2025 | 08W | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 1.1
35295446 | Fire Rebuild | 102211103 | BUCKS CREEK 1103 | BUCKS CREEK 1103CB | PLUMAS | v2 | 1658 | 2023-08-07 08:00 | 2024 | 08W | 0.42708 | 0.59848 | 0 | 1.0256 | 0.42708 | 0.59848 | 0 | 1.0256 | 0 | 0 | 0 | 0
35297464 | Fire Rebuild | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | SANTA CRUZ | v2 | 2199 | 2025-09-04 08:00 | 2025 | 08W | 0 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0 | 0 | 0 | 1.0021 | 0 | 1.0021
35299629 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 1102CB | BUTTE | v2 | 268 | 2024-07-05 08:00 | 2024 | 08W | 0 | 0.89091 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0.89091 | 0 | 0 | 0 | 0
35299633 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022094 | BUTTE | v2 | 1703 | 2023-09-11 | 2024 | 08W | 0 | 1.4142 | 0 | 1.4142 | 0 | 1.4142 | 0 | 1.4142 | 0 | 0 | 0 | 0
35299635 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110247006 | BUTTE | v2 | 1535 | 2023-08-28 | 2024 | 08W | 0 | 1.6835 | 0 | 1.6835 | 0 | 1.6835 | 0 | 1.6835 | 0 | 0 | 0 | 0
35305303 | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | v2 | 169 | 2025-08-21 08:00 | 2025 | 08W | 0 | 1.1206 | 0 | 1.1206 | 0 | 0 | 0 | 0 | 0 | 1.1206 | 0 | 1.1206
35305308 | Base SH | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | v2 | 169 | 2024-02-05 | 2024 | 08W | 0 | 0.45833 | 0 | 0.45833 | 0 | 0.45833 | 0 | 0.45833 | 0 | 0 | 0 | 0
35311896 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-11-15 08:00 | 2025 | 08W | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 0 | 0 | 2.76 | 0 | 2.76
35312540 | Base SH | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | v2 | 271 | 2023-05-15 | 2024 | 08W | 0 | 0.037689 | 0 | 0.037689 | 0 | 0.037689 | 0 | 0.037689 | 0 | 0 | 0 | 0
35312542 | Base SH | 43071103 | DUNBAR 1103 | DUNBAR 1103534 | SONOMA | v2 | 1827 | 2024-09-03 08:00 | 2025 | 08W | 0 | 0.67386 | 0 | 0.67386 | 0 | 0 | 0 | 0 | 0 | 0.67386 | 0 | 0.67386
35312543 | Base SH | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | v2 | 315 | 2023-07-10 | 2024 | 08W | 0 | 0.26799 | 0 | 0.26799 | 0 | 0.26799 | 0 | 0.26799 | 0 | 0 | 0 | 0
35312545 | Base SH | 152531101 | FLINT 1101 | FLINT 1101750 | PLACER | v2 | 152 | 2024-01-11 | 2024 | 08W | 0 | 1.3299 | 0 | 1.3299 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0
35312551 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101454 | LAKE | v2 | 312 | 2024-04-01 08:00 | 2024 | 08W | 0 | 3.2049 | 0 | 3.2049 | 0 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0 | 0
35312553 | Base SH | 252931102 | TEJON 1102 | TEJON 11022455 | KERN | v2 | 642 | 2024-03-15 08:00 | 2024 | 08W | 0 | 1.7006 | 0 | 1.7006 | 0 | 1.7006 | 0 | 1.7006 | 0 | 0 | 0 | 0
35312560 | Base SH | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | v2 | 976 | 2023-07-18 | 2024 | 08W | 0 | 0.97727 | 0 | 0.97727 | 0 | 0.97727 | 0 | 0.97727 | 0 | 0 | 0 | 0
35314415 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-04-01 08:00 | 2024 | 08W | 0.039962 | 2.05 | 0 | 2.09 | 0.039962 | 2.05 | 0 | 2.09 | 0 | 0 | 0 | 0
35314416 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-05-27 08:00 | 2025 | 08W | 0.31004 | 1.1201 | 0.17008 | 1.6002 | 0 | 0 | 0 | 0 | 0.31004 | 1.1201 | 0.17008 | 1.6002
35316561 | Base SH | 102931102 | COTTONWOOD 1102 | COTTONWOOD 1102544790 | SHASTA | v2 | 123 | 2023-06-20 | 2024 | 08W | 0 | 4.7343 | 0 | 4.7343 | 0 | 4.7343 | 0 | 4.7343 | 0 | 0 | 0 | 0
35317399 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2023-09-18 | 2024 | 08W | 0 | 1.0938 | 0 | 1.0938 | 0 | 1.0938 | 0 | 1.0938 | 0 | 0 | 0 | 0
35320333 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | v2 | 64 | 2023-08-07 | 2024 | 08W | 0 | 3.0348 | 0 | 3.0348 | 0 | 3.0348 | 0 | 3.0348 | 0 | 0 | 0 | 0
35320334 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | v2 | 64 | 2023-09-11 | 2024 | 08W | 0 | 2.5 | 0 | 2.5 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0
35320335 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 110847860 | SOLANO | v2 | 1247 | 2024-07-17 08:00 | 2024 | 08W | 0 | 0.44508 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0
35320440 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 1111CB | SOLANO | v2 | 500 | 2023-06-26 | 2024 | 08W | 0 | 0.84545 | 0 | 0.84545 | 0 | 0.84545 | 0 | 0.84545 | 0 | 0 | 0 | 0
35320441 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 111113652 | SOLANO | v2 | 190 | 2023-08-07 | 2024 | 08W | 0 | 0.45227 | 0 | 0.45227 | 0 | 0.45227 | 0 | 0.45227 | 0 | 0 | 0 | 0
35320442 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2023-07-24 | 2024 | 08W | 0.10189 | 0.67955 | 0 | 0.78144 | 0.10189 | 0.67955 | 0 | 0.78144 | 0 | 0 | 0 | 0
35320450 | Base SH | 153701104 | LINCOLN 1104 | LINCOLN 1104685276 | PLACER | v2 | 230 | 2023-08-28 | 2024 | 08W | 0 | 2.2589 | 0 | 2.2589 | 0 | 2.2589 | 0 | 2.2589 | 0 | 0 | 0 | 0
35320461 | Base SH | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | v2 | 393 | 2023-09-25 | 2024 | 08W | 1.0155 | 1.0729 | 0 | 2.0884 | 1.0155 | 1.0729 | 0 | 2.0884 | 0 | 0 | 0 | 0
35321894 | Fire Rebuild | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | SANTA CRUZ | v2 | 2199 | 2024-08-29 08:00 | 2025 | 08W | 0 | 0.10985 | 0 | 0.10985 | 0 | 0 | 0 | 0 | 0 | 0.10985 | 0 | 0.10985
35325589 | Base SH | 152531101 | FLINT 1101 | FLINT 1101750 | PLACER | v2 | 152 | 2023-10-09 | 2024 | 08W | 0 | 1.21 | 0 | 1.21 | 0 | 1.21 | 0 | 1.21 | 0 | 0 | 0 | 0
35325590 | Base SH | 152531101 | FLINT 1101 | FLINT 1101750 | PLACER | v2 | 152 | 2023-10-02 | 2024 | 08W | 0 | 2.296 | 0 | 2.296 | 0 | 2.296 | 0 | 2.296 | 0 | 0 | 0 | 0
35329012 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022094 | BUTTE | v2 | 1703 | 2023-09-13 | 2024 | 08W | 0 | 1.55 | 0 | 1.55 | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0
35329016 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110247006 | BUTTE | v2 | 1535 | 2023-08-28 | 2024 | 08W | 0 | 3.4301 | 0 | 3.4301 | 0 | 3.4301 | 0 | 3.4301 | 0 | 0 | 0 | 0
35329472 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101454 | LAKE | v2 | 312 | 2023-08-07 | 2024 | 08W | 0 | 2.6585 | 0 | 2.6585 | 0 | 2.6585 | 0 | 2.6585 | 0 | 0 | 0 | 0
35329473 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101454 | LAKE | v2 | 312 | 2024-08-13 08:00 | 2024 | 08W | 0 | 4.761 | 0 | 4.761 | 0 | 4.761 | 0 | 4.761 | 0 | 0 | 0 | 0
35330211 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2023-06-20 | 2024 | 08W | 0 | 1.8019 | 0 | 1.8019 | 0 | 1.8019 | 0 | 1.8019 | 0 | 0 | 0 | 0
35330213 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2024-03-06 08:00 | 2024 | 08W | 0 | 5.5358 | 0 | 5.5358 | 0 | 5.5358 | 0 | 5.5358 | 0 | 0 | 0 | 0
35330215 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2024-08-30 08:00 | 2024 | 08W | 0 | 2.7998 | 0 | 2.7998 | 0 | 2.7998 | 0 | 2.7998 | 0 | 0 | 0 | 0
35330216 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2024-04-22 08:00 | 2024 | 08W | 0 | 1.5464 | 0 | 1.5464 | 0 | 1.5464 | 0 | 1.5464 | 0 | 0 | 0 | 0
35330217 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2024-04-08 08:00 | 2024 | 08W | 0 | 0.32973 | 0 | 0.32973 | 0 | 0.32973 | 0 | 0.32973 | 0 | 0 | 0 | 0
35330248 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | v2 | 345 | 2023-09-18 | 2024 | 08W | 0 | 2.5108 | 0 | 2.5108 | 0 | 2.5108 | 0 | 2.5108 | 0 | 0 | 0 | 0
35330249 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | v2 | 345 | 2023-10-02 | 2024 | 08W | 0 | 2.8723 | 0 | 2.8723 | 0 | 2.8723 | 0 | 2.8723 | 0 | 0 | 0 | 0
35331306 | Base SH | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | v2 | 976 | 2023-09-15 | 2024 | 08W | 0 | 1.7008 | 0 | 1.7008 | 0 | 1.7008 | 0 | 1.7008 | 0 | 0 | 0 | 0
35331307 | Base SH | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | v2 | 976 | 2023-07-25 | 2024 | 08W | 0 | 2.082 | 0 | 2.082 | 0 | 2.082 | 0 | 2.082 | 0 | 0 | 0 | 0
35332213 | Base SH | 102931102 | COTTONWOOD 1102 | COTTONWOOD 1102544790 | SHASTA | v2 | 123 | 2023-07-17 | 2024 | 08W | 0 | 2.5689 | 0 | 2.5689 | 0 | 2.5689 | 0 | 2.5689 | 0 | 0 | 0 | 0
35332360 | Base SH | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | v2 | 315 | 2023-07-31 | 2024 | 08W | 0 | 0.54223 | 0 | 0.54223 | 0 | 0.54223 | 0 | 0.54223 | 0 | 0 | 0 | 0
35332868 | Base SH | 163351701 | CURTIS 1701 | CURTIS 1701CB | TUOLUMNE | v2 | 1166 | 2023-08-15 | 2024 | 08W | 0 | 2.2098 | 0 | 2.2098 | 0 | 2.2098 | 0 | 2.2098 | 0 | 0 | 0 | 0
35332870 | Base SH | 163351701 | CURTIS 1701 | CURTIS 1701CB | TUOLUMNE | v2 | 1166 | 2023-09-05 | 2024 | 08W | 0 | 0.69527 | 0 | 0.69527 | 0 | 0.69527 | 0 | 0.69527 | 0 | 0 | 0 | 0
35333501 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-06-17 08:00 | 2024 | 08W | 0 | 2.96 | 0 | 2.96 | 0 | 2.96 | 0 | 2.96 | 0 | 0 | 0 | 0
35333503 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-09-27 15:00 | 2024 | 08W | 1.44 | 0.3 | 0 | 1.74 | 1.44 | 0.3 | 0 | 1.74 | 0 | 0 | 0 | 0
35333504 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2024-10-14 08:00 | 2024 | 08W | 0 | 0.45 | 0 | 0.45 | 0 | 0.45 | 0 | 0.45 | 0 | 0 | 0 | 0
35334232 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2025-02-04 08:00 | 2025 | 08W | 0 | 1.01 | 0 | 1.01 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 1.01
35334234 | Base SH | 152701108 | BELL 1108 | BELL 11082202 | PLACER | v2 | 118 | 2025-01-29 08:00 | 2025 | 08W | 0 | 2.3 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | 2.3
35334754 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | v2 | 122 | 2023-08-07 | 2024 | 08W | 0 | 0.06553 | 0 | 0.06553 | 0 | 0.06553 | 0 | 0.06553 | 0 | 0 | 0 | 0
35334755 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | v2 | 122 | 2023-07-24 | 2024 | 08W | 0 | 0.016288 | 0 | 0.016288 | 0 | 0.016288 | 0 | 0.016288 | 0 | 0 | 0 | 0
35335286 | Base SH | 252931102 | TEJON 1102 | TEJON 11022455 | KERN | v2 | 642 | 2024-05-06 08:00 | 2025 | 08W | 0 | 5.2104 | 0 | 5.2104 | 0 | 0 | 0 | 0 | 0 | 5.2104 | 0 | 5.2104
35335287 | Base SH | 252931102 | TEJON 1102 | TEJON 11022455 | KERN | v2 | 642 | 2024-04-11 08:00 | 2024 | 08W | 0 | 2.0784 | 0 | 2.0784 | 0 | 2.0784 | 0 | 2.0784 | 0 | 0 | 0 | 0
35335290 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 111113652 | SOLANO | v2 | 190 | 2023-08-14 | 2024 | 08W | 0 | 1.0892 | 0 | 1.0892 | 0 | 1.0892 | 0 | 1.0892 | 0 | 0 | 0 | 0
35335291 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 1111CB | SOLANO | v2 | 500 | 2023-07-25 | 2024 | 08W | 0 | 1.0614 | 0 | 1.0614 | 0 | 1.0614 | 0 | 1.0614 | 0 | 0 | 0 | 0
35335292 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 1111CB | SOLANO | v2 | 500 | 2023-08-21 | 2024 | 08W | 0 | 1.858 | 0 | 1.858 | 0 | 1.858 | 0 | 1.858 | 0 | 0 | 0 | 0
35335293 | Base SH | 63601111 | VACAVILLE 1111 | VACAVILLE 1111CB | SOLANO | v2 | 500 | 2023-08-07 | 2024 | 08W | 0 | 2.3941 | 0 | 2.3941 | 0 | 2.3941 | 0 | 2.3941 | 0 | 0 | 0 | 0
35337008 | Base SH | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | v2 | 389 | 2023-06-20 | 2025 | 08W | 0 | 0.30417 | 0 | 0.30417 | 0 | 0 | 0 | 0 | 0 | 0.30417 | 0 | 0.30417
35338406 | Base SH | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | v2 | 393 | 2023-10-09 | 2024 | 08W | 0 | 1.14 | 0 | 1.14 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0
35338407 | Base SH | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | v2 | 393 | 2024-05-13 08:00 | 2024 | 08W | 0 | 0.66004 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0
35338408 | Base SH | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | v2 | 393 | 2024-02-13 | 2024 | 08W | 0 | 1.1299 | 0 | 1.1299 | 0 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0 | 0
35342143 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2023-08-01 | 2024 | 08W | 0 | 3.2491 | 0 | 3.2491 | 0 | 3.2491 | 0 | 3.2491 | 0 | 0 | 0 | 0
35342144 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2023-08-11 | 2024 | 08W | 0 | 2.3216 | 0 | 2.3216 | 0 | 2.3216 | 0 | 2.3216 | 0 | 0 | 0 | 0
35342146 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2023-09-05 | 2024 | 08W | 0 | 1.6994 | 0 | 1.6994 | 0 | 1.6994 | 0 | 1.6994 | 0 | 0 | 0 | 0
35342147 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2024-03-07 08:00 | 2024 | 08W | 0 | 1.8259 | 0 | 1.8259 | 0 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0 | 0
35342148 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2023-07-17 | 2024 | 08W | 0 | 1.0377 | 0 | 1.0377 | 0 | 1.0377 | 0 | 1.0377 | 0 | 0 | 0 | 0
35342335 | Fire Rebuild | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | SANTA CRUZ | v2 | 2359 | 2024-10-28 08:00 | 2025 | 08W | 0 | 2.1941 | 0 | 2.1941 | 0 | 0 | 0 | 0 | 0 | 2.1941 | 0 | 2.1941
35342336 | Fire Rebuild | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | SANTA CRUZ | v2 | 2359 | 2024-04-18 08:00 | 2025 | 08W | 0 | 2.9763 | 0 | 2.9763 | 0 | 0 | 0 | 0 | 0 | 2.9763 | 0 | 2.9763
35342337 | Fire Rebuild | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | SANTA CRUZ | v2 | 2359 | 2024-10-30 08:00 | 2025 | 08W | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0.52008
35342338 | Fire Rebuild | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | SANTA CRUZ | v2 | 2359 | 2024-01-08 | 2024 | 08W | 0 | 1.4348 | 0 | 1.4348 | 0 | 1.4348 | 0 | 1.4348 | 0 | 0 | 0 | 0
35343394 | Base SH | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | v2 | 976 | 2023-08-02 | 2024 | 08W | 0 | 0.2803 | 0 | 0.2803 | 0 | 0.2803 | 0 | 0.2803 | 0 | 0 | 0 | 0
35343397 | Base SH | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | v2 | 976 | 2023-06-12 | 2024 | 08W | 0 | 0.25057 | 0 | 0.25057 | 0 | 0.25057 | 0 | 0.25057 | 0 | 0 | 0 | 0
35343741 | Base SH | 43071103 | DUNBAR 1103 | DUNBAR 1103534 | SONOMA | v2 | 1827 | 2024-09-04 08:00 | 2025 | 08W | 0 | 0.70795 | 0 | 0.70795 | 0 | 0 | 0 | 0 | 0 | 0.70795 | 0 | 0.70795
35362666 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 2212614950 | CONTRA COSTA | v3 | 100 | 2025-02-26 08:00 | 2025 | 3UG | 0.019886 | 0.65 | 0 | 0.66989 | 0 | 0 | 0 | 0 | 0.019886 | 0.65 | 0 | 0.66989
35363559 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-09-23 08:00 | 2025 | 3UG | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0 | 0 | 3.26 | 0 | 3.26
35363720 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2024-12-06 08:00 | 2025 | 3UG | 0 | 2.7699 | 0 | 2.7699 | 0 | 0 | 0 | 0 | 0 | 2.7699 | 0 | 2.7699
35364784 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-04-15 08:00 | 2025 | 3UG | 0 | 3.0098 | 0 | 3.0098 | 0 | 0 | 0 | 0 | 0 | 3.0098 | 0 | 3.0098
35365064 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | 2024-11-26 08:00 | 2025 | 3UG | 0 | 4.21 | 0 | 4.21 | 0 | 0 | 0 | 0 | 0 | 4.21 | 0 | 4.21
35367335 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | 2024-03-18 08:00 | 2024 | 3UG | 0 | 5.303 | 0 | 5.303 | 0 | 5.303 | 0 | 5.303 | 0 | 0 | 0 | 0
35367414 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2025-02-17 08:00 | 2025 | 3UG | 0 | 6.415 | 0 | 6.415 | 0 | 0 | 0 | 0 | 0 | 6.415 | 0 | 6.415
35367468 | Base SH | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101CB | EL DORADO | v3 | 81 | 2024-10-22 08:00 | 2026 | 3UG | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9
35367478 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-05-21 08:00 | 2024 | 3UG | 0 | 2.425 | 0 | 2.425 | 0 | 2.425 | 0 | 2.425 | 0 | 0 | 0 | 0
35367504 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-04-01 08:00 | 2025 | 3UG | 0 | 4.37 | 0 | 4.37 | 0 | 0 | 0 | 0 | 0 | 4.37 | 0 | 4.37
35367507 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 1102CB | BUTTE | v3 | 17 | 2025-03-19 08:00 | 2025 | 3UG | 0.021 | 0.876 | 0 | 0.897 | 0 | 0 | 0 | 0 | 0.021 | 0.876 | 0 | 0.897
35367516 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-03-04 08:00 | 2025 | 3UG | 0 | 1.358 | 0 | 1.358 | 0 | 0 | 0 | 0 | 0 | 1.358 | 0 | 1.358
35367524 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2025-07-01 08:00 | 2025 | 3UG | 0 | 1.4 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 1.4 | 0 | 1.4
35372259 | Base SH | 163751101 | PINE GROVE 1101 | PINE GROVE 1101CB | AMADOR | v3 | 6 | 2025-07-07 08:00 | 2025 | 3UG | 0 | 2.84 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 2.84 | 0 | 2.84
35372461 | Base SH | 161380201 | TIGER CREEK 0201 | TIGER CREEK 0201CB | AMADOR | v3 | 8 | 2025-04-22 08:00 | 2025 | 3UG | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42
35372462 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | AMADOR | v3 | 62 | 2024-08-09 08:00 | 2025 | 3UG | 0.019886 | 4.85 | 0 | 4.8699 | 0 | 0 | 0 | 0 | 0.019886 | 4.85 | 0 | 4.8699
35372464 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | 2024-04-22 08:00 | 2024 | 3UG | 0 | 3.712 | 0 | 3.712 | 0 | 3.712 | 0 | 3.712 | 0 | 0 | 0 | 0
35372465 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011384 | SHASTA | v3 | 11 | 2024-10-08 08:00 | 2025 | 3UG | 0 | 4.695 | 0 | 4.695 | 0 | 0 | 0 | 0 | 0 | 4.695 | 0 | 4.695
35373530 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-07-02 08:00 | 2024 | 3UG | 0 | 2.635 | 0 | 2.635 | 0 | 2.635 | 0 | 2.635 | 0 | 0 | 0 | 0
35373532 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-12-06 08:00 | 2025 | 3UG | 0 | 2.57 | 0 | 2.57 | 0 | 0 | 0 | 0 | 0 | 2.57 | 0 | 2.57
35373533 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-05-29 08:00 | 2024 | 3UG | 0 | 2.6201 | 0 | 2.6201 | 0 | 2.6201 | 0 | 2.6201 | 0 | 0 | 0 | 0
35373620 | Base SH | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101CB | EL DORADO | v3 | 81 | 2024-10-22 08:00 | 2026 | 3UG | 0 | 0.65 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0.65 | 0 | 0.65
35373628 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-09-02 08:00 | 2025 | 3UG | 0 | 0.70019 | 0 | 0.70019 | 0 | 0 | 0 | 0 | 0 | 0.70019 | 0 | 0.70019
35373704 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-07-11 08:00 | 2025 | 3UG | 0 | 3.648 | 0 | 3.648 | 0 | 0 | 0 | 0 | 0 | 3.648 | 0 | 3.648
35373708 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011384 | SHASTA | v3 | 11 | 2024-07-11 08:00 | 2025 | 3UG | 0 | 3.73 | 0 | 3.73 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 3.73
35374059 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 1101L1697 | AMADOR | v3 | 118 | 2025-06-04 08:00 | 2025 | 3UG | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 0 | 0 | 2.11 | 0 | 2.11
35374200 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-06-24 08:00 | 2025 | 3UG | 0 | 2.884 | 0 | 2.884 | 0 | 0 | 0 | 0 | 0 | 2.884 | 0 | 2.884
35374202 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-07-11 08:00 | 2025 | 3UG | 0 | 1.072 | 0 | 1.072 | 0 | 0 | 0 | 0 | 0 | 1.072 | 0 | 1.072
35374204 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | SIERRA | v3 | 41 | 2025-01-03 08:00 | 2025 | 3UG | 0 | 2.9799 | 0 | 2.9799 | 0 | 0 | 0 | 0 | 0 | 2.9799 | 0 | 2.9799
35374205 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | SIERRA | v3 | 41 | 2025-03-31 08:00 | 2025 | 3UG | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.01
35374206 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2024-12-03 08:00 | 2025 | 3UG | 0 | 4.08 | 0 | 4.08 | 0 | 0 | 0 | 0 | 0 | 4.08 | 0 | 4.08
35374208 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2025-01-21 08:00 | 2025 | 3UG | 0 | 2.28 | 0 | 2.28 | 0 | 0 | 0 | 0 | 0 | 2.28 | 0 | 2.28
35374443 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2024-10-14 08:00 | 2025 | 3UG | 0 | 2.458 | 0 | 2.458 | 0 | 0 | 0 | 0 | 0 | 2.458 | 0 | 2.458
35374563 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2025-06-23 08:00 | 2025 | 3UG | 0 | 3.7383 | 0 | 3.7383 | 0 | 0 | 0 | 0 | 0 | 3.7383 | 0 | 3.7383
35374564 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2025-04-09 08:00 | 2025 | 3UG | 0.28883 | 1.8873 | 1.76 | 3.9362 | 0 | 0 | 0 | 0 | 0.28883 | 1.8873 | 1.76 | 3.9362
35374566 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2024-05-30 08:00 | 2024 | 3UG | 0 | 0.11004 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0 | 0
35374567 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2024-07-22 08:00 | 2024 | 3UG | 0 | 0.43996 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0 | 0
35374569 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2024-09-18 08:00 | 2025 | 3UG | 0 | 2.1807 | 0 | 2.1807 | 0 | 0 | 0 | 0 | 0 | 2.1807 | 0 | 2.1807
35374682 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | v3 | 504 | 2024-09-25 08:00 | 2025 | 08W | 0 | 3.1559 | 0 | 3.1559 | 0 | 0 | 0 | 0 | 0 | 3.1559 | 0 | 3.1559
35374685 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | v3 | 126 | 2024-03-04 | 2024 | 08W | 0 | 2.4203 | 0 | 2.4203 | 0 | 2.4203 | 0 | 2.4203 | 0 | 0 | 0 | 0
35374687 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | v3 | 504 | 2024-04-01 | 2024 | 08W | 0 | 0.87008 | 0 | 0.87008 | 0 | 0.87008 | 0 | 0.87008 | 0 | 0 | 0 | 0
35374863 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 210110170 | MARIPOSA | v3 | 504 | 2023-09-05 | 2024 | 08W | 0 | 0.45076 | 0 | 0.45076 | 0 | 0.45076 | 0 | 0.45076 | 0 | 0 | 0 | 0
35375452 | Base SH | 152201101 | PIKE CITY 1101 | PIKE CITY 11011720 | YUBA | v3 | 52 | 2025-02-14 08:00 | 2025 | 3UG | 0 | 3.1 | 0 | 3.1 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0 | 3.1
35376304 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | v3 | 504 | 2023-10-10 | 2024 | 08W | 0 | 0.52822 | 0 | 0.52822 | 0 | 0.52822 | 0 | 0.52822 | 0 | 0 | 0 | 0
35376306 | Fire Rebuild | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | v3 | 504 | 2023-10-09 | 2024 | 08W | 0 | 0.36023 | 0 | 0.36023 | 0 | 0.36023 | 0 | 0.36023 | 0 | 0 | 0 | 0
35376890 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | AMADOR | v3 | 62 | 2024-08-01 08:00 | 2024 | 3UG | 0 | 2.91 | 0 | 2.91 | 0 | 2.91 | 0 | 2.91 | 0 | 0 | 0 | 0
35376891 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104646776 | NAPA | v3 | 14 | 2025-06-30 08:00 | 2025 | 3UG | 0 | 2.235 | 0 | 2.235 | 0 | 0 | 0 | 0 | 0 | 2.235 | 0 | 2.235
35377520 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101171414 | LAKE | v3 | 38 | 2025-02-03 08:00 | 2025 | 3UG | 0 | 2.4299 | 0 | 2.4299 | 0 | 0 | 0 | 0 | 0 | 2.4299 | 0 | 2.4299
35380368 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | 2024-02-12 17:00 | 2024 | 08W | 0 | 2.1271 | 0 | 2.1271 | 0 | 2.1271 | 0 | 2.1271 | 0 | 0 | 0 | 0
35380369 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | 2024-02-27 08:00 | 2024 | 08W | 0 | 2.3021 | 0 | 2.3021 | 0 | 2.3021 | 0 | 2.3021 | 0 | 0 | 0 | 0
35380370 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | 2024-04-08 08:00 | 2024 | 08W | 0 | 3.6866 | 0 | 3.6866 | 0 | 3.6866 | 0 | 3.6866 | 0 | 0 | 0 | 0
35383305 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2025-05-13 08:00 | 2025 | 3UG | 0 | 0.57 | 0 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0.57
35383758 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2024-11-18 08:00 | 2025 | 3UG | 0 | 2.4598 | 0 | 2.4598 | 0 | 0 | 0 | 0 | 0 | 2.4598 | 0 | 2.4598
35385803 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2024-09-17 08:00 | 2025 | 3UG | 0 | 2.198 | 0 | 2.198 | 0 | 0 | 0 | 0 | 0 | 2.198 | 0 | 2.198
35385804 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2025-07-01 08:00 | 2025 | 3UG | 0 | 2.65 | 0 | 2.65 | 0 | 0 | 0 | 0 | 0 | 2.65 | 0 | 2.65
35385805 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | Not Available | 2025 | 3UG | 0 | 3.1241 | 0 | 3.1241 | 0 | 0 | 0 | 0 | 0 | 3.1241 | 0 | 3.1241
35385806 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | Not Available | 2025 | 3UG | 0 | 2.936 | 0 | 2.936 | 0 | 0 | 0 | 0 | 0 | 2.936 | 0 | 2.936
35391723 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-11-21 08:00 | 2026 | 3UG | 0 | 3.24 | 0 | 3.24 | 0 | 0 | 0 | 0 | 0 | 3.24 | 0 | 3.24
35392113 | Fire Rebuild | 152181101 | FORESTHILL 1101 | FORESTHILL 110137238 | PLACER | v3 | 322 | 2025-03-07 08:00 | 2025 | 08W | 0 | 1.928 | 0 | 1.928 | 0 | 0 | 0 | 0 | 0 | 1.928 | 0 | 1.928
35392114 | Fire Rebuild | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | EL DORADO | v3 | 397 | 2023-10-11 | 2024 | 08W | 0 | 1.0307 | 0 | 1.0307 | 0 | 1.0307 | 0 | 1.0307 | 0 | 0 | 0 | 0
35395928 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | 2024-05-09 08:00 | 2024 | 3UG | 0 | 1.937 | 0 | 1.937 | 0 | 1.937 | 0 | 1.937 | 0 | 0 | 0 | 0
35395929 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | Not Available | 2025 | 3UG | 0 | 0.057 | 0 | 0.057 | 0 | 0 | 0 | 0 | 0 | 0.057 | 0 | 0.057
35395930 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | 2024-07-22 08:00 | 2024 | 3UG | 0 | 0.369 | 0 | 0.369 | 0 | 0.369 | 0 | 0.369 | 0 | 0 | 0 | 0
35396762 | Base SH | 163751101 | PINE GROVE 1101 | PINE GROVE 1101CB | AMADOR | v3 | 6 | 2024-05-23 08:00 | 2024 | 3UG | 0.07 | 2.91 | 0 | 2.98 | 0.07 | 2.91 | 0 | 2.98 | 0 | 0 | 0 | 0
35396763 | Base SH | 163751101 | PINE GROVE 1101 | PINE GROVE 1101CB | AMADOR | v3 | 6 | 2024-05-28 08:00 | 2024 | 3UG | 0 | 0.88 | 0 | 0.88 | 0 | 0.88 | 0 | 0.88 | 0 | 0 | 0 | 0
35396908 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-05-13 08:00 | 2024 | 3UG | 0 | 3.2038 | 0 | 3.2038 | 0 | 3.2038 | 0 | 3.2038 | 0 | 0 | 0 | 0
35396909 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-05-13 08:00 | 2024 | 3UG | 0 | 2.9786 | 0 | 2.9786 | 0 | 2.9786 | 0 | 2.9786 | 0 | 0 | 0 | 0
35396910 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-07-08 08:00 | 2024 | 3UG | 0 | 3.0699 | 0 | 3.0699 | 0 | 3.0699 | 0 | 3.0699 | 0 | 0 | 0 | 0
35396911 | Base SH | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | PLACER | v3 | 114 | 2024-06-24 08:00 | 2024 | 3UG | 0 | 3.571 | 0 | 3.571 | 0 | 3.571 | 0 | 3.571 | 0 | 0 | 0 | 0
35398091 | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | v2 | 995 | 2023-10-23 | 2024 | 08W | 0 | 0.26818 | 0 | 0.26818 | 0 | 0.26818 | 0 | 0.26818 | 0 | 0 | 0 | 0
35401224 | Base SH | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101CB | EL DORADO | v3 | 81 | 2024-10-22 08:00 | 2026 | 3UG | 0 | 0.61 | 0 | 0.61 | 0 | 0 | 0 | 0 | 0 | 0.61 | 0 | 0.61
35401226 | Base SH | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101CB | EL DORADO | v3 | 81 | 2024-10-22 08:00 | 2026 | 3UG | 0 | 2.04 | 0 | 2.04 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 2.04
35402641 | Base SH | 163751102 | PINE GROVE 1102 | PINE GROVE 110213438 | AMADOR | v3 | 204 | 2024-02-13 08:00 | 2024 | 3UG | 0 | 4.914 | 0 | 4.914 | 0 | 4.914 | 0 | 4.914 | 0 | 0 | 0 | 0
35402642 | Base SH | 163751102 | PINE GROVE 1102 | PINE GROVE 110213438 | AMADOR | v3 | 204 | 2024-04-05 08:00 | 2024 | 3UG | 0.15909 | 0.83902 | 0 | 0.99811 | 0.15909 | 0.83902 | 0 | 0.99811 | 0 | 0 | 0 | 0
35402643 | Base SH | 163751101 | PINE GROVE 1101 | PINE GROVE 11013166 | AMADOR | v3 | 147 | 2024-10-28 08:00 | 2024 | 3UG | 0 | 2.456 | 0 | 2.456 | 0 | 2.456 | 0 | 2.456 | 0 | 0 | 0 | 0
35404349 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | AMADOR | v3 | 62 | 2024-10-15 08:00 | 2025 | 3UG | 0 | 4.47 | 0 | 4.47 | 0 | 0 | 0 | 0 | 0 | 4.47 | 0 | 4.47
35404351 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-03-04 08:00 | 2025 | 3UG | 0 | 1.632 | 0 | 1.632 | 0 | 0 | 0 | 0 | 0 | 1.632 | 0 | 1.632
35404352 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-03-04 08:00 | 2025 | 3UG | 0 | 2.029 | 0 | 2.029 | 0 | 0 | 0 | 0 | 0 | 2.029 | 0 | 2.029
35404353 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-03-04 08:00 | 2025 | 3UG | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096
35404354 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-03-04 08:00 | 2025 | 3UG | 0 | 0.862 | 0 | 0.862 | 0 | 0 | 0 | 0 | 0 | 0.862 | 0 | 0.862
35404355 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2024-07-31 08:00 | 2025 | 3UG | 0 | 1.113 | 0 | 1.113 | 0 | 0 | 0 | 0 | 0 | 1.113 | 0 | 1.113
35404726 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | NAPA | v3 | 101 | 2025-06-30 08:00 | 2025 | 3UG | 0 | 3.88 | 0 | 3.88 | 0 | 0 | 0 | 0 | 0 | 3.88 | 0 | 3.88
35406859 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2024-07-01 08:00 | 2024 | 3UG | 0 | 0.22102 | 0 | 0.22102 | 0 | 0.22102 | 0 | 0.22102 | 0 | 0 | 0 | 0
35407303 | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | v2 | 995 | Not Available | 2024 | 08W | 0 | 0.18958 | 0 | 0.18958 | 0 | 0.18958 | 0 | 0.18958 | 0 | 0 | 0 | 0
35409202 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11011314 | LAKE | v3 | 56 | 2024-08-23 08:00 | 2025 | 3UG | 0 | 1.05 | 0 | 1.05 | 0 | 0 | 0 | 0 | 0 | 1.05 | 0 | 1.05
35409213 | Base SH | 153661104 | APPLE HILL 1104 | APPLE HILL 1104CB | EL DORADO | v3 | 30 | 2025-01-16 08:00 | 2025 | 3UG | 0.11 | 3.03 | 0 | 3.14 | 0 | 0 | 0 | 0 | 0.11 | 3.03 | 0 | 3.14
35411026 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2025-05-22 08:00 | 2025 | 3UG | 0 | 3.36 | 0 | 3.36 | 0 | 0 | 0 | 0 | 0 | 3.36 | 0 | 3.36
35411027 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2024-08-28 08:00 | 2025 | 3UG | 0 | 3.51 | 0 | 3.51 | 0 | 0 | 0 | 0 | 0 | 3.51 | 0 | 3.51
35411028 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2025-04-17 08:00 | 2025 | 3UG | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 0 | 0 | 0 | 1.69 | 0 | 1.69
35417127 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2024-10-14 08:00 | 2025 | 3UG | 0 | 6.67 | 0 | 6.67 | 0 | 0 | 0 | 0 | 0 | 6.67 | 0 | 6.67
35418255 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2025-01-23 08:00 | 2025 | 3UG | 0 | 5.23 | 0 | 5.23 | 0 | 0 | 0 | 0 | 0 | 5.23 | 0 | 5.23
35418305 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2025-01-23 08:00 | 2025 | 3UG | 0 | 5.13 | 0 | 5.13 | 0 | 0 | 0 | 0 | 0 | 5.13 | 0 | 5.13
35418375 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 17026028 | CALAVERAS | v3 | 60 | 2025-04-03 08:00 | 2025 | 3UG | 0 | 1.94 | 0 | 1.94 | 0 | 0 | 0 | 0 | 0 | 1.94 | 0 | 1.94
35420747 | Base SH | 24251101 | WOODSIDE 1101 | WOODSIDE 11018974 | SAN MATEO | v2 | 1145 | Not Available | 2025 | 08W | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8
35421185 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | EL DORADO | v3 | 32 | 2025-05-02 08:00 | 2025 | 3UG | 0 | 3.74 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 3.74 | 0 | 3.74
35421186 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | EL DORADO | v3 | 32 | 2025-05-02 08:00 | 2025 | 3UG | 0 | 3.63 | 0 | 3.63 | 0 | 0 | 0 | 0 | 0 | 3.63 | 0 | 3.63
35421187 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 1101CB | AMADOR | v3 | 218 | 2025-06-02 08:00 | 2025 | 3UG | 0 | 3.6598 | 0 | 3.6598 | 0 | 0 | 0 | 0 | 0 | 3.6598 | 0 | 3.6598
35421188 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 1101CB | AMADOR | v3 | 218 | 2025-05-13 08:00 | 2025 | 3UG | 0 | 1.6 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 1.6
35423400 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | 2024-07-24 08:00 | 2025 | 3UG | 0 | 5.655 | 0 | 5.655 | 0 | 0 | 0 | 0 | 0 | 5.655 | 0 | 5.655
35424354 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | 2024-09-05 08:00 | 2025 | 3UG | 0 | 0.381 | 0 | 0.381 | 0 | 0 | 0 | 0 | 0 | 0.381 | 0 | 0.381
35424355 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | 2024-07-24 08:00 | 2025 | 3UG | 0 | 6.817 | 0 | 6.817 | 0 | 0 | 0 | 0 | 0 | 6.817 | 0 | 6.817
35424357 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-12-26 08:00 | 2026 | 3UG | 0 | 1.646 | 0 | 1.646 | 0 | 0 | 0 | 0 | 0 | 1.646 | 0 | 1.646
35424359 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-08-28 08:00 | 2026 | 3UG | 0 | 1.363 | 0 | 1.363 | 0 | 0 | 0 | 0 | 0 | 1.363 | 0 | 1.363
35424427 | Base SH | 163351701 | CURTIS 1701 | CURTIS 1701CB | TUOLUMNE | v2 | 1166 | 2024-04-29 08:00 | 2024 | 08W | 0 | 0.08125 | 0.049242 | 0.13049 | 0 | 0.08125 | 0.049242 | 0.13049 | 0 | 0 | 0 | 0
35424589 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-11-21 08:00 | 2025 | 3UG | 0.015 | 0.712 | 0 | 0.727 | 0 | 0 | 0 | 0 | 0.015 | 0.712 | 0 | 0.727
35424590 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-11-21 08:00 | 2025 | 3UG | 0 | 1.885 | 0 | 1.885 | 0 | 0 | 0 | 0 | 0 | 1.885 | 0 | 1.885
35425643 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2025-09-30 08:00 | 2025 | 3UG | 0 | 2.508 | 0 | 2.508 | 0 | 0 | 0 | 0 | 0 | 2.508 | 0 | 2.508
35425644 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2025-06-10 08:00 | 2025 | 3UG | 0 | 4.114 | 0 | 4.114 | 0 | 0 | 0 | 0 | 0 | 4.114 | 0 | 4.114
35425645 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2025-07-29 08:00 | 2025 | 3UG | 0 | 3.212 | 0 | 3.212 | 0 | 0 | 0 | 0 | 0 | 3.212 | 0 | 3.212
35425646 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2025-02-19 08:00 | 2025 | 3UG | 0 | 2.917 | 0 | 2.917 | 0 | 0 | 0 | 0 | 0 | 2.917 | 0 | 2.917
35425647 | Base SH | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | AMADOR | v3 | 107 | 2024-10-25 08:00 | 2025 | 3UG | 0 | 1.86 | 0 | 1.86 | 0 | 0 | 0 | 0 | 0 | 1.86 | 0 | 1.86
35425877 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 14 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 1.225 | 0 | 1.225 | 0 | 0 | 0 | 0 | 0 | 1.225 | 0 | 1.225
35425878 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 14 | 2025-07-29 08:00 | 2025 | 3UG | 0 | 1.684 | 0 | 1.684 | 0 | 0 | 0 | 0 | 0 | 1.684 | 0 | 1.684
35425879 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0.0028409 | 4.14 | 0 | 4.1428 | 0 | 0 | 0 | 0 | 0.0028409 | 4.14 | 0 | 4.1428
35425921 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-03-16 08:00 | 2026 | 3UG | 0 | 4.4299 | 0 | 4.4299 | 0 | 0 | 0 | 0 | 0 | 4.4299 | 0 | 4.4299
35426736 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | AMADOR | v3 | 62 | 2024-08-19 08:00 | 2024 | 3UG | 0 | 3.57 | 0 | 3.57 | 0 | 3.57 | 0 | 3.57 | 0 | 0 | 0 | 0
35428391 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-10-08 08:00 | 2025 | 3UG | 0 | 3.9123 | 0 | 3.9123 | 0 | 0 | 0 | 0 | 0 | 3.9123 | 0 | 3.9123
35428392 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-09-05 08:00 | 2025 | 3UG | 0 | 4.1402 | 0 | 4.1402 | 0 | 0 | 0 | 0 | 0 | 4.1402 | 0 | 4.1402
35428395 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-08-07 08:00 | 2024 | 3UG | 0 | 3.0453 | 0 | 3.0453 | 0 | 3.0453 | 0 | 3.0453 | 0 | 0 | 0 | 0
35428396 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-07-01 08:00 | 2024 | 3UG | 0 | 3.3636 | 0 | 3.3636 | 0 | 3.3636 | 0 | 3.3636 | 0 | 0 | 0 | 0
35428397 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-12-06 08:00 | 2025 | 3UG | 0 | 2.45 | 0 | 2.45 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 2.45
35428401 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | EL DORADO | v3 | 63 | 2024-10-22 08:00 | 2025 | 3UG | 0 | 3.69 | 0 | 3.69 | 0 | 0 | 0 | 0 | 0 | 3.69 | 0 | 3.69
35428403 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | Not Available | 2025 | 3UG | 0 | 2.739 | 0 | 2.739 | 0 | 0 | 0 | 0 | 0 | 2.739 | 0 | 2.739
35428425 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | 2025-07-25 08:00 | 2025 | 3UG | 0 | 2.57 | 0 | 2.57 | 0 | 0 | 0 | 0 | 0 | 2.57 | 0 | 2.57
35428426 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | Not Available | 2024 | 3UG | 0 | 2.284 | 0 | 2.284 | 0 | 2.284 | 0 | 2.284 | 0 | 0 | 0 | 0
35428427 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | NAPA | v3 | 59 | Not Available | 2024 | 3UG | 0 | 2.972 | 0 | 2.972 | 0 | 2.972 | 0 | 2.972 | 0 | 0 | 0 | 0
35429499 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2024-12-03 08:00 | 2025 | 3UG | 0 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0 | 0 | 0 | 1.1799 | 0 | 1.1799
35429560 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2025-02-03 08:00 | 2025 | 3UG | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5
35429561 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2025-03-31 08:00 | 2025 | 3UG | 0 | 2.0699 | 0 | 2.0699 | 0 | 0 | 0 | 0 | 0 | 2.0699 | 0 | 2.0699
35429562 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2025-01-23 08:00 | 2025 | 3UG | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05
35429563 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | CALAVERAS | v3 | 80 | 2025-04-16 08:00 | 2025 | 3UG | 0.16989 | 0.16989 | 0 | 0.33977 | 0 | 0 | 0 | 0 | 0.16989 | 0.16989 | 0 | 0.33977
35429565 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 11024788 | CALAVERAS | v3 | 164 | 2024-08-01 08:00 | 2024 | 3UG | 0 | 3.26 | 0 | 3.26 | 0 | 3.26 | 0 | 3.26 | 0 | 0 | 0 | 0
35429566 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | Not Available | 2025 | 3UG | 0 | 3.795 | 0 | 3.795 | 0 | 0 | 0 | 0 | 0 | 3.795 | 0 | 3.795
35430878 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2025-07-07 08:00 | 2025 | 3UG | 0 | 3.4676 | 0 | 3.4676 | 0 | 0 | 0 | 0 | 0 | 3.4676 | 0 | 3.4676
35430879 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2025-04-09 08:00 | 2025 | 3UG | 0.73769 | 0.056818 | 0 | 0.79451 | 0 | 0 | 0 | 0 | 0.73769 | 0.056818 | 0 | 0.79451
35430880 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2025-04-09 08:00 | 2025 | 3UG | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2.5
35431074 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 1101L1697 | AMADOR | v3 | 118 | 2025-06-04 08:00 | 2025 | 3UG | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 0 | 2.05 | 0 | 2.05
35431075 | Base SH | 162161101 | ELECTRA 1101 | ELECTRA 1101L1697 | AMADOR | v3 | 118 | 2025-06-04 08:00 | 2025 | 3UG | 0.87992 | 1.5 | 0 | 2.3799 | 0 | 0 | 0 | 0 | 0.87992 | 1.5 | 0 | 2.3799
35431987 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | Not Available | 2024 | 08W | 0 | 0.18239 | 0 | 0.18239 | 0 | 0.18239 | 0 | 0.18239 | 0 | 0 | 0 | 0
35433421 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | 2024-08-19 08:00 | 2025 | 3UG | 0 | 2.841 | 0 | 2.841 | 0 | 0 | 0 | 0 | 0 | 2.841 | 0 | 2.841
35436101 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2024-12-05 08:00 | 2025 | 3UG | 0 | 3.45 | 0 | 3.45 | 0 | 0 | 0 | 0 | 0 | 3.45 | 0 | 3.45
35436513 | Base SH | 153661104 | APPLE HILL 1104 | APPLE HILL 1104CB | EL DORADO | v3 | 30 | 2025-01-03 08:00 | 2025 | 3UG | 0 | 2.36 | 0 | 2.36 | 0 | 0 | 0 | 0 | 0 | 2.36 | 0 | 2.36
35436514 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | EL DORADO | v3 | 32 | 2025-04-10 08:00 | 2025 | 3UG | 0 | 3.56 | 0 | 3.56 | 0 | 0 | 0 | 0 | 0 | 3.56 | 0 | 3.56
35436515 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | EL DORADO | v3 | 32 | 2025-04-17 08:00 | 2025 | 3UG | 0.03 | 3.5 | 0 | 3.53 | 0 | 0 | 0 | 0 | 0.03 | 3.5 | 0 | 3.53
35436516 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | EL DORADO | v3 | 32 | 2025-02-07 08:00 | 2025 | 3UG | 0 | 2.26 | 0 | 2.26 | 0 | 0 | 0 | 0 | 0 | 2.26 | 0 | 2.26
35439661 | Base SH | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102CB | PLUMAS | v3 | 45 | 2024-08-19 08:00 | 2024 | 3UG | 0 | 0.094697 | 0 | 0.094697 | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0
35439898 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011384 | SHASTA | v3 | 11 | 2024-12-10 08:00 | 2025 | 3UG | 0 | 4.939 | 0 | 4.939 | 0 | 0 | 0 | 0 | 0 | 4.939 | 0 | 4.939
35439899 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011384 | SHASTA | v3 | 11 | 2025-01-08 08:00 | 2025 | 3UG | 0 | 1.334 | 0 | 1.334 | 0 | 0 | 0 | 0 | 0 | 1.334 | 0 | 1.334
35447662 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2024-10-14 08:00 | 2025 | 3UG | 0 | 2.197 | 0 | 2.197 | 0 | 0 | 0 | 0 | 0 | 2.197 | 0 | 2.197
35447663 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2024-10-14 08:00 | 2025 | 3UG | 0 | 2.97 | 0 | 2.97 | 0 | 0 | 0 | 0 | 0 | 2.97 | 0 | 2.97
35448085 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-09-17 08:00 | 2025 | 3UG | 0 | 2.338 | 0 | 2.338 | 0 | 0 | 0 | 0 | 0 | 2.338 | 0 | 2.338
35448086 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-09-17 08:00 | 2025 | 3UG | 0 | 1.986 | 0 | 1.986 | 0 | 0 | 0 | 0 | 0 | 1.986 | 0 | 1.986
35450186 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | 20 | Not Available | 2025 | 3UG | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996
35452898 | Base SH | 152201101 | PIKE CITY 1101 | PIKE CITY 11011720 | YUBA | v3 | 52 | 2025-02-07 08:00 | 2025 | 3UG | 0 | 4.42 | 0 | 4.42 | 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 4.42
35454650 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-09-17 08:00 | 2025 | 3UG | 0 | 0.514 | 0 | 0.514 | 0 | 0 | 0 | 0 | 0 | 0.514 | 0 | 0.514
35454651 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-09-17 08:00 | 2025 | 3UG | 0.085 | 1.386 | 0 | 1.471 | 0 | 0 | 0 | 0 | 0.085 | 1.386 | 0 | 1.471
35454652 | Base SH | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | BUTTE | v3 | 37 | 2024-09-17 08:00 | 2025 | 3UG | 0 | 2.695 | 0 | 2.695 | 0 | 0 | 0 | 0 | 0 | 2.695 | 0 | 2.695
35457280 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2025-03-27 08:00 | 2025 | 3UG | 0 | 3.77 | 0 | 3.77 | 0 | 0 | 0 | 0 | 0 | 3.77 | 0 | 3.77
35457281 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2025-03-27 08:00 | 2025 | 3UG | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31
35457800 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | SIERRA | v3 | 41 | 2025-03-31 08:00 | 2025 | 3UG | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 2.14
35458434 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v3 | 41 | 2025-01-15 08:00 | 2025 | 3UG | 0 | 2.39 | 0 | 2.39 | 0 | 0 | 0 | 0 | 0 | 2.39 | 0 | 2.39
35460160 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-03-21 08:00 | 2025 | 3UG | 0 | 4.37 | 0 | 4.37 | 0 | 0 | 0 | 0 | 0 | 4.37 | 0 | 4.37
35460162 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-03-03 08:00 | 2025 | 3UG | 0 | 5.03 | 0 | 5.03 | 0 | 0 | 0 | 0 | 0 | 5.03 | 0 | 5.03
35460286 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 1102CB | BUTTE | v3 | 17 | 2025-04-07 08:00 | 2025 | 3UG | 0 | 2.069 | 0 | 2.069 | 0 | 0 | 0 | 0 | 0 | 2.069 | 0 | 2.069
35460292 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 1102CB | BUTTE | v3 | 17 | 2025-03-24 08:00 | 2025 | 3UG | 0.006 | 0.19201 | 0 | 0.19801 | 0 | 0 | 0 | 0 | 0.006 | 0.19201 | 0 | 0.19801
35464320 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2024-07-03 08:00 | 2025 | 3UG | 0 | 4.34 | 0 | 4.34 | 0 | 0 | 0 | 0 | 0 | 4.34 | 0 | 4.34
35464321 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-03-03 08:00 | 2025 | 3UG | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 0 | 0 | 1.79 | 0 | 1.79
35464322 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-04-15 08:00 | 2025 | 3UG | 0 | 1.67 | 0 | 1.67 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0 | 1.67
35464323 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | 2025-04-15 08:00 | 2025 | 3UG | 0 | 1.55 | 0 | 1.55 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 1.55
35473990 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2026-01-15 08:00 | 2026 | 3UG | 0 | 5.3598 | 0 | 5.3598 | 0 | 0 | 0 | 0 | 0 | 5.3598 | 0 | 5.3598
35473991 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2024-10-14 08:00 | 2026 | 3UG | 0.019886 | 3.94 | 0 | 3.9598 | 0 | 0 | 0 | 0 | 0.019886 | 3.94 | 0 | 3.9598
35473992 | Base SH | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | v2 | 739 | 2024-05-02 08:00 | 2024 | 08W | 0 | 0.4786 | 0 | 0.4786 | 0 | 0.4786 | 0 | 0.4786 | 0 | 0 | 0 | 0
35473993 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | v2 | 64 | 2024-07-18 08:00 | 2024 | 08W | 0 | 0.26174 | 0 | 0.26174 | 0 | 0.26174 | 0 | 0.26174 | 0 | 0 | 0 | 0
35474894 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | v2 | 122 | 2024-06-24 08:00 | 2024 | 08W | 0 | 1.2775 | 0 | 1.2775 | 0 | 1.2775 | 0 | 1.2775 | 0 | 0 | 0 | 0
35474978 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | EL DORADO | v3 | 58 | 2026-01-15 08:00 | 2026 | 3UG | 0 | 6.6199 | 0 | 6.6199 | 0 | 0 | 0 | 0 | 0 | 6.6199 | 0 | 6.6199
35485344 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 17026028 | CALAVERAS | v3 | 60 | 2025-04-03 08:00 | 2025 | 3UG | 0 | 4.11 | 0 | 4.11 | 0 | 0 | 0 | 0 | 0 | 4.11 | 0 | 4.11
35485345 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 17026028 | CALAVERAS | v3 | 60 | 2025-04-03 08:00 | 2025 | 3UG | 0 | 3.23 | 0 | 3.23 | 0 | 0 | 0 | 0 | 0 | 3.23 | 0 | 3.23
35485580 | Base SH | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | v2 | 64 | 2024-10-17 08:00 | 2025 | 08W | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818
35488067 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-03-20 08:00 | 2025 | 3UG | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 1.09
35488068 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-05-28 08:00 | 2025 | 3UG | 0 | 5.8292 | 0 | 5.8292 | 0 | 0 | 0 | 0 | 0 | 5.8292 | 0 | 5.8292
35488069 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-01-22 08:00 | 2025 | 3UG | 0 | 1.4809 | 0 | 1.4809 | 0 | 0 | 0 | 0 | 0 | 1.4809 | 0 | 1.4809
35488560 | Base SH | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | BUTTE | v3 | 61 | 2025-04-01 08:00 | 2025 | 3UG | 0 | 7.18 | 0 | 7.18 | 0 | 0 | 0 | 0 | 0 | 7.18 | 0 | 7.18
35490375 | Base SH | 103331102 | CORNING 1102 | CORNING 1102915324 | TEHAMA | v2 | 457 | Not Available | 2024 | 08W | 0 | 0.093182 | 0 | 0.093182 | 0 | 0.093182 | 0 | 0.093182 | 0 | 0 | 0 | 0
35493212 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0 | 1.9741 | 0 | 1.9741 | 0 | 0 | 0 | 0 | 0 | 1.9741 | 0 | 1.9741
35493213 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0 | 0.9697 | 0 | 0.9697 | 0 | 0 | 0 | 0 | 0 | 0.9697 | 0 | 0.9697
35493214 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0 | 1.6917 | 0 | 1.6917 | 0 | 0 | 0 | 0 | 0 | 1.6917 | 0 | 1.6917
35493215 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0 | 1.658 | 0 | 1.658 | 0 | 0 | 0 | 0 | 0 | 1.658 | 0 | 1.658
35493216 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-06-10 08:00 | 2026 | 3UG | 0 | 2.9295 | 0 | 2.9295 | 0 | 0 | 0 | 0 | 0 | 2.9295 | 0 | 2.9295
35493217 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-03-16 08:00 | 2026 | 3UG | 0 | 3.6299 | 0 | 3.6299 | 0 | 0 | 0 | 0 | 0 | 3.6299 | 0 | 3.6299
35493218 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-04-06 08:00 | 2026 | 3UG | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 0 | 0 | 2.35 | 0 | 2.35
35493219 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | CALAVERAS | v3 | 66 | 2026-03-02 08:00 | 2026 | 3UG | 0 | 2.2201 | 0 | 2.2201 | 0 | 0 | 0 | 0 | 0 | 2.2201 | 0 | 2.2201
35523358 | Base SH | 103732101 | PIT NO 3 2101 | PIT NO 3 2101CB | SHASTA | v3 | 326 | Not Available | 2025 | 3UG | 0 | 3.311 | 0 | 3.311 | 0 | 0 | 0 | 0 | 0 | 3.311 | 0 | 3.311
35523400 | Base SH | 103732101 | PIT NO 3 2101 | PIT NO 3 2101CB | SHASTA | v3 | 326 | Not Available | 2025 | 3UG | 0 | 0.52898 | 0 | 0.52898 | 0 | 0 | 0 | 0 | 0 | 0.52898 | 0 | 0.52898
35524040 | Base SH | 103732101 | PIT NO 3 2101 | PIT NO 3 2101CB | SHASTA | v3 | 326 | Not Available | 2025 | 3UG | 0 | 1.9271 | 0 | 1.9271 | 0 | 0 | 0 | 0 | 0 | 1.9271 | 0 | 1.9271
74001486 | Other | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105BR160 | ALAMEDA | v2 | 2792 | Not Available | 2026 | 30A | 0 | 1.7312 | 0 | 1.7312 | 0 | 0 | 0 | 0 | 0 | 1.7312 | 0 | 1.7312
74010582 | Other | N/A | N/A | DIAMOND SPRINGS 1402 | EL DORADO | v2 | 811 | Not Available | 2024 | 30A | 0 | 1.3299 | 0 | 1.3299 | 0 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0 | 0
35226621 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | LAKE | v2 | 468 | Not Available | 2025 | 08W | 0.55701 | 1.55 | 0 | 2.107 | 0 | 0 | 0 | 0 | 0.55701 | 1.55 | 0 | 2.107
35285594 | Fire Rebuild | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101481660 | EL DORADO | v2 | 2005 | Not Available | 2025 | 08W | 0 | 0.21989 | 0 | 0.21989 | 0 | 0 | 0 | 0 | 0 | 0.21989 | 0 | 0.21989
35335235 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | NAPA | v2 | 1648 | 2024-06-18 08:00 | 2024 | 08W | 0 | 3.5799 | 0 | 3.5799 | 0 | 3.5799 | 0 | 3.5799 | 0 | 0 | 0 | 0
35342315 | Base SH | 252931102 | TEJON 1102 | TEJON 1102732836 | KERN | v2 | 583 | Not Available | 2025 | 08W | 0 | 1.723 | 0 | 1.723 | 0 | 0 | 0 | 0 | 0 | 1.723 | 0 | 1.723
35367464 | Base SH | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | NAPA | v3 | 105 | 2025-12-10 08:00 | 2025 | 3UG | 4.24 | 0.6 | 0 | 4.84 | 0 | 0 | 0 | 0 | 4.24 | 0.6 | 0 | 4.84
35367518 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105 167360 & 990552 | NAPA | v3 | 398 | Not Available | 2025 | 3UG | 5.1299 | 1.8701 | 0 | 7 | 0 | 0 | 0 | 0 | 5.1299 | 1.8701 | 0 | 7
35372257 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104 CB & 4440 | MARIPOSA | v3 | 10 | 2025-10-22 08:00 | 2025 | 3UG | 8.9299 | 0.13996 | 0 | 9.0699 | 0 | 0 | 0 | 0 | 8.9299 | 0.13996 | 0 | 9.0699
35372258 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104 CB & 4440 | MARIPOSA | v3 | 10 | 2025-11-17 08:00 | 2025 | 3UG | 5.06 | 3.2701 | 0 | 8.3301 | 0 | 0 | 0 | 0 | 5.06 | 3.2701 | 0 | 8.3301
35373597 | Base SH | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | NAPA | v3 | 105 | Not Available | 2025 | 3UG | 0.93996 | 3.31 | 0 | 4.25 | 0 | 0 | 0 | 0 | 0.93996 | 3.31 | 0 | 4.25
35375449 | Base SH | 152201101 | PIKE CITY 1101 | PIKE CITY 1101CB | SIERRA | v3 | 116 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 10.86 | 0 | 10.86 | 0 | 0 | 0 | 0 | 0 | 10.86 | 0 | 10.86
35375450 | Base SH | 152201101 | PIKE CITY 1101 | PIKE CITY 1101CB | YUBA | v3 | 116 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 10.66 | 0 | 10.66 | 0 | 0 | 0 | 0 | 0 | 10.66 | 0 | 10.66
35376558 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 105 | 2025-08-26 08:00 | 2025 | 3UG | 0.5 | 6.9201 | 0 | 7.4201 | 0 | 0 | 0 | 0 | 0.5 | 6.9201 | 0 | 7.4201
35376559 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 105 | 2025-08-26 08:00 | 2025 | 3UG | 1.11 | 0.43996 | 0 | 1.55 | 0 | 0 | 0 | 0 | 1.11 | 0.43996 | 0 | 1.55
35377525 | Base SH | 152201101 | PIKE CITY 1101 | PIKE CITY 1101CB | YUBA | v3 | 116 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 6.9701 | 0 | 6.9701 | 0 | 0 | 0 | 0 | 0 | 6.9701 | 0 | 6.9701
35379383 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2024-11-01 08:00 | 2025 | 3UG | 7.3201 | 1.6 | 1.14 | 10.06 | 0 | 0 | 0 | 0 | 7.3201 | 1.6 | 1.14 | 10.06
35382932 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2024-08-16 08:00 | 2025 | 3UG | 8.5201 | 0.22992 | 0.91004 | 9.66 | 0 | 0 | 0 | 0 | 8.5201 | 0.22992 | 0.91004 | 9.66
35385802 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | v3 | 15 | 2025-05-05 08:00 | 2025 | 3UG | 4.6799 | 0.78996 | 0.25 | 5.7199 | 0 | 0 | 0 | 0 | 4.6799 | 0.78996 | 0.25 | 5.7199
35391471 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-11-11 08:00 | 2025 | 3UG | 6.31 | 2.9 | 0 | 9.21 | 0 | 0 | 0 | 0 | 6.31 | 2.9 | 0 | 9.21
35391472 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 5.1701 | 4 | 0 | 9.1701 | 0 | 0 | 0 | 0 | 5.1701 | 4 | 0 | 9.1701
35391473 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 7.81 | 1.5701 | 0 | 9.3801 | 0 | 0 | 0 | 0 | 7.81 | 1.5701 | 0 | 9.3801
35391721 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-12-19 08:00 | 2025 | 3UG | 2.6799 | 6.8 | 0 | 9.4799 | 0 | 0 | 0 | 0 | 2.6799 | 6.8 | 0 | 9.4799
35391722 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-08-28 08:00 | 2025 | 3UG | 3.25 | 5.4701 | 0 | 8.7201 | 0 | 0 | 0 | 0 | 3.25 | 5.4701 | 0 | 8.7201
35397962 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2024-11-01 08:00 | 2025 | 3UG | 0 | 4.2 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 4.2
35397963 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2024-11-01 08:00 | 2025 | 3UG | 0 | 3.8799 | 0 | 3.8799 | 0 | 0 | 0 | 0 | 0 | 3.8799 | 0 | 3.8799
35401011 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2024-10-03 08:00 | 2025 | 3UG | 0 | 2.46 | 0 | 2.46 | 0 | 0 | 0 | 0 | 0 | 2.46 | 0 | 2.46
35401012 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2025-09-08 08:00 | 2025 | 3UG | 0 | 3.11 | 0 | 3.11 | 0 | 0 | 0 | 0 | 0 | 3.11 | 0 | 3.11
35401013 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | v3 | 126 | 2025-10-14 08:00 | 2025 | 3UG | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15
35403551 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | NAPA | v3 | 398 | 2025-02-04 08:00 | 2025 | 3UG | 0 | 1.25 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 1.25
35403552 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | NAPA | v3 | 398 | 2025-02-04 08:00 | 2025 | 3UG | 0 | 2.31 | 0 | 2.31 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 2.31
35403553 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | NAPA | v3 | 398 | 2025-02-04 08:00 | 2025 | 3UG | 0 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0 | 0 | 0 | 1.5299 | 0 | 1.5299
35403554 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | NAPA | v3 | 398 | 2025-02-04 08:00 | 2025 | 3UG | 0 | 2.95 | 0 | 2.95 | 0 | 0 | 0 | 0 | 0 | 2.95 | 0 | 2.95
35403558 | Base SH | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | NAPA | v3 | 105 | Not Available | 2025 | 3UG | 0 | 1.7299 | 0 | 1.7299 | 0 | 0 | 0 | 0 | 0 | 1.7299 | 0 | 1.7299
35409203 | Base SH | 43141101 | MIDDLETOWN 1101 | Middletown 1101433160 | LAKE | v3 | 99 | Not Available | 2025 | 3UG | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 1.39
35409215 | Base SH | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 11021584 | SHASTA | v3 | 64 | Not Available | 2025 | 3UG | 3.8201 | 0.55 | 0 | 4.3701 | 0 | 0 | 0 | 0 | 3.8201 | 0.55 | 0 | 4.3701
35409217 | Base SH | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 11021584 | SHASTA | v3 | 64 | 2025-11-12 08:00 | 2025 | 3UG | 4.66 | 5.21 | 0 | 9.8701 | 0 | 0 | 0 | 0 | 4.66 | 5.21 | 0 | 9.8701
35417110 | Base SH | 152181102 | FORESTHILL 1102 | FORESTHILL 11022106 | PLACER | v3 | 97 | Not Available | 2025 | 3UG | 0 | 9.5701 | 0 | 9.5701 | 0 | 0 | 0 | 0 | 0 | 9.5701 | 0 | 9.5701
35418361 | Base SH | 152431102 | SHADY GLEN 1102 | SHADY GLEN 110248894 | PLACER | v3 | 89 | 2025-10-29 08:00 | 2025 | 3UG | 0 | 7.4201 | 0 | 7.4201 | 0 | 0 | 0 | 0 | 0 | 7.4201 | 0 | 7.4201
35418379 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 170237278 | CALAVERAS | v3 | 98 | 2024-12-05 08:00 | 2025 | 3UG | 0 | 7.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 7.5
35420105 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-08-04 08:00 | 2025 | 3UG | 0 | 2.4299 | 0 | 2.4299 | 0 | 0 | 0 | 0 | 0 | 2.4299 | 0 | 2.4299
35420106 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-09-15 08:00 | 2025 | 3UG | 0 | 1.2299 | 0 | 1.2299 | 0 | 0 | 0 | 0 | 0 | 1.2299 | 0 | 1.2299
35420107 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-07-29 08:00 | 2025 | 3UG | 0 | 2.4201 | 0 | 2.4201 | 0 | 0 | 0 | 0 | 0 | 2.4201 | 0 | 2.4201
35420108 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-08-21 08:00 | 2025 | 3UG | 0 | 1.34 | 0 | 1.34 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 1.34
35420109 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 1.51 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 1.51
35420110 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
35420111 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 3.2799 | 0 | 3.2799 | 0 | 0 | 0 | 0 | 0 | 3.2799 | 0 | 3.2799
35420112 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0.020076 | 4.1299 | 0 | 4.15 | 0 | 0 | 0 | 0 | 0.020076 | 4.1299 | 0 | 4.15
35420113 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0 | 0 | 0.51004 | 0 | 0.51004
35422749 | Base SH | 152431102 | SHADY GLEN 1102 | SHADY GLEN 11022232 | PLACER | v3 | 93 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 7.94 | 0 | 7.94 | 0 | 0 | 0 | 0 | 0 | 7.94 | 0 | 7.94
35422750 | Base SH | 152431102 | SHADY GLEN 1102 | SHADY GLEN 11022232 | PLACER | v3 | 93 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 8.35 | 0 | 8.35 | 0 | 0 | 0 | 0 | 0 | 8.35 | 0 | 8.35
35422751 | Base SH | 152431102 | SHADY GLEN 1102 | SHADY GLEN 11022232 | PLACER | v3 | 93 | 2025-11-12 08:00 | 2025 | 3UG | 0 | 10.74 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 10.74 | 0 | 10.74
35423081 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 3.01
35423082 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 2.9 | 0 | 2.9 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 2.9
35423083 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2025 | 3UG | 0 | 1.75 | 0 | 1.75 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 1.75
35424356 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-12-19 08:00 | 2025 | 3UG | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 0 | 0 | 2.5799 | 0 | 2.5799
35424358 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2024-12-19 08:00 | 2025 | 3UG | 0 | 2.16 | 0 | 2.16 | 0 | 0 | 0 | 0 | 0 | 2.16 | 0 | 2.16
35424580 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-08-21 08:00 | 2025 | 3UG | 0 | 4.01 | 0 | 4.01 | 0 | 0 | 0 | 0 | 0 | 4.01 | 0 | 4.01
35424581 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | 2025-08-21 08:00 | 2025 | 3UG | 0 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0 | 0 | 0 | 2.2799 | 0 | 2.2799
35428406 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | Not Available | 2025 | 3UG | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 0 | 3.1701
35428408 | Base SH | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v3 | 33 | 2025-05-28 08:00 | 2025 | 3UG | 0 | 2.56 | 0 | 2.56 | 0 | 0 | 0 | 0 | 0 | 2.56 | 0 | 2.56
35430872 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 2.038 | 0 | 2.038 | 0 | 0 | 0 | 0 | 0 | 2.038 | 0 | 2.038
35430873 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 2.577 | 0 | 2.577 | 0 | 0 | 0 | 0 | 0 | 2.577 | 0 | 2.577
35430874 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 2.286 | 0 | 2.286 | 0 | 0 | 0 | 0 | 0 | 2.286 | 0 | 2.286
35430875 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 0.511 | 0 | 0.511 | 0 | 0 | 0 | 0 | 0 | 0.511 | 0 | 0.511
35430876 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | SONOMA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 0.56818 | 0 | 0.56818 | 0 | 0 | 0 | 0 | 0 | 0.56818 | 0 | 0.56818
35430877 | Base SH | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | NAPA | v3 | 87 | 2025-08-26 08:00 | 2025 | 3UG | 0 | 0.56818 | 0 | 0.56818 | 0 | 0 | 0 | 0 | 0 | 0.56818 | 0 | 0.56818
35433366 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | v3 | 15 | 2025-05-05 08:00 | 2025 | 3UG | 0.010038 | 2.386 | 0 | 2.396 | 0 | 0 | 0 | 0 | 0.010038 | 2.386 | 0 | 2.396
35433371 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | v3 | 15 | 2025-05-05 08:00 | 2025 | 3UG | 0 | 2.096 | 0 | 2.096 | 0 | 0 | 0 | 0 | 0 | 2.096 | 0 | 2.096
35434253 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 2212681608 | CONTRA COSTA | v3 | 115 | 2025-12-26 08:00 | 2025 | 3UG | 0 | 4.2299 | 0 | 4.2299 | 0 | 0 | 0 | 0 | 0 | 4.2299 | 0 | 4.2299
35434254 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 2212681608 | CONTRA COSTA | v3 | 115 | 2025-12-26 08:00 | 2025 | 3UG | 0 | 3.15 | 0 | 3.15 | 0 | 0 | 0 | 0 | 0 | 3.15 | 0 | 3.15
35434255 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 2212681608 | CONTRA COSTA | v3 | 115 | 2025-12-26 08:00 | 2025 | 3UG | 0 | 0.97008 | 0 | 0.97008 | 0 | 0 | 0 | 0 | 0 | 0.97008 | 0 | 0.97008
35435899 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-17 08:00 | 2025 | 3UG | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0.78996
35436100 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-10 08:00 | 2025 | 3UG | 0 | 2.15 | 0 | 2.15 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 2.15
35448807 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | SIERRA | v3 | 41 | 2025-01-03 08:00 | 2025 | 3UG | 0 | 2.21 | 0 | 2.21 | 0 | 0 | 0 | 0 | 0 | 2.21 | 0 | 2.21
35448810 | Base SH | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | SIERRA | v3 | 41 | 2025-01-03 08:00 | 2025 | 3UG | 0 | 2.56 | 0 | 2.56 | 0 | 0 | 0 | 0 | 0 | 2.56 | 0 | 2.56
35451492 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-07 08:00 | 2025 | 3UG | 0 | 3.3299 | 0 | 3.3299 | 0 | 0 | 0 | 0 | 0 | 3.3299 | 0 | 3.3299
35451493 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-07 08:00 | 2025 | 3UG | 0 | 1.96 | 0 | 1.96 | 0 | 0 | 0 | 0 | 0 | 1.96 | 0 | 1.96
35451494 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-07 08:00 | 2025 | 3UG | 0 | 3.5299 | 0 | 3.5299 | 0 | 0 | 0 | 0 | 0 | 3.5299 | 0 | 3.5299
35451495 | Base SH | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | 2025-01-07 08:00 | 2025 | 3UG | 0 | 0.82992 | 0 | 0.82992 | 0 | 0 | 0 | 0 | 0 | 0.82992 | 0 | 0.82992
35457108 | Base SH | 153132102 | NARROWS 2102 | NARROWS 2102CB | NEVADA | v3 | 46 | Not Available | 2025 | 3UG | 0.01 | 3.84 | 0 | 3.85 | 0 | 0 | 0 | 0 | 0.01 | 3.84 | 0 | 3.85
35510467 | Base SH | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101CB | PLACER | v3 | N/A | Not Available | 2025 | 3UG | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
35519739 | Base SH | 254421103 | OAKHURST 1103 | OAKHURST 110310140 | MADERA | v3 | 22 | Not Available | 2026 | 08W | 11.09 | 5.5201 | 0 | 16.61 | 0 | 0 | 0 | 0 | 11.09 | 5.5201 | 0 | 16.61
35519764 | Base SH | 163351703 | CURTIS 1703 | CURTIS 170356972 | TUOLUMNE | v3 | 34 | Not Available | 2026 | 08W | 7.7299 | 0.7 | 0 | 8.4299 | 0 | 0 | 0 | 0 | 7.7299 | 0.7 | 0 | 8.4299
35519766 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11019712 | SHASTA | v3 | 43 | Not Available | 2026 | 08W | 16.39 | 1.0201 | 0 | 17.41 | 0 | 0 | 0 | 0 | 16.39 | 1.0201 | 0 | 17.41
35519768 | Base SH | 43311102 | KONOCTI 1102 | KONOCTI 11022293 | LAKE | v3 | 51 | Not Available | 2026 | 08W | 1.5201 | 0.18996 | 0 | 1.71 | 0 | 0 | 0 | 0 | 1.5201 | 0.18996 | 0 | 1.71
35519772 | Base SH | 153662102 | APPLE HILL 2102 | APPLE HILL 210289934 | EL DORADO | v3 | 55 | Not Available | 2026 | 08W | 4.05 | 1.49 | 0 | 5.54 | 0 | 0 | 0 | 0 | 4.05 | 1.49 | 0 | 5.54
35519773 | Base SH | 103401102 | GIRVAN 1102 | GIRVAN 11029012 | SHASTA | v3 | 73 | Not Available | 2026 | 08W | 14.96 | 0.17008 | 0 | 15.1301 | 0 | 0 | 0 | 0 | 14.96 | 0.17008 | 0 | 15.1301
35519776 | Base SH | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210576694 | MARIPOSA | v3 | 76 | Not Available | 2026 | 08W | 1.76 | 0.36004 | 0 | 2.1201 | 0 | 0 | 0 | 0 | 1.76 | 0.36004 | 0 | 2.1201
35519777 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011588 | SHASTA | v3 | 83 | Not Available | 2026 | 08W | 2.4 | 0.12992 | 0 | 2.5299 | 0 | 0 | 0 | 0 | 2.4 | 0.12992 | 0 | 2.5299
35519779 | Base SH | 102781101 | ELK CREEK 1101 | ELK CREEK 11012032 | COLUSA | v3 | 85 | Not Available | 2026 | 08W | 8.94 | 0.48996 | 0 | 9.4299 | 0 | 0 | 0 | 0 | 8.94 | 0.48996 | 0 | 9.4299
35519781 | Base SH | 152321101 | DRUM 1101 | DRUM 1101CB | PLACER | v3 | 103 | Not Available | 2026 | 08W | 1.79 | 0.3 | 0 | 2.09 | 0 | 0 | 0 | 0 | 1.79 | 0.3 | 0 | 2.09
35519784 | Base SH | 103611101 | WILDWOOD 1101 | WILDWOOD 110198896 | SHASTA | v3 | 109 | Not Available | 2026 | 08W | 1.5701 | 4.81 | 0 | 6.3801 | 0 | 0 | 0 | 0 | 1.5701 | 4.81 | 0 | 6.3801
35519785 | Base SH | 163201102 | WEST POINT 1102 | WEST POINT 110277204 | CALAVERAS | v3 | 110 | Not Available | 2026 | 08W | 5.06 | 2.64 | 0 | 7.7 | 0 | 0 | 0 | 0 | 5.06 | 2.64 | 0 | 7.7
35519786 | Base SH | 103451101 | KESWICK 1101 | KESWICK 110148480 | SHASTA | v3 | 119 | Not Available | 2026 | 08W | 9.66 | 0.22008 | 0 | 9.8801 | 0 | 0 | 0 | 0 | 9.66 | 0.22008 | 0 | 9.8801
35519789 | Base SH | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21059570 | MARIPOSA | v3 | 125 | Not Available | 2026 | 08W | 5.79 | 2.34 | 0 | 8.1299 | 0 | 0 | 0 | 0 | 5.79 | 2.34 | 0 | 8.1299
35519790 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011590 | SHASTA | v3 | 135 | Not Available | 2026 | 08W | 5.94 | 0.27008 | 0 | 6.21 | 0 | 0 | 0 | 0 | 5.94 | 0.27008 | 0 | 6.21
35521812 | Base SH | 163661702 | MIWUK 1702 | MIWUK 170236888 | TUOLUMNE | v3 | 50 | Not Available | 2026 | 08W | 0.35 | 0.010038 | 0 | 0.36004 | 0 | 0 | 0 | 0 | 0.35 | 0.010038 | 0 | 0.36004
35521818 | Base SH | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 110190730 | NEVADA | v3 | 75 | Not Available | 2026 | 08W | 4.8799 | 2.4701 | 0 | 7.35 | 0 | 0 | 0 | 0 | 4.8799 | 2.4701 | 0 | 7.35
35521819 | Base SH | 12022212 | CLAYTON 2212 | CLAYTON 2212681608 | CONTRA COSTA | v3 | 115 | Not Available | 2026 | 08W | 10.6 | 0.089962 | 0 | 10.69 | 0 | 0 | 0 | 0 | 10.6 | 0.089962 | 0 | 10.69
35522101 | Base SH | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | PLACER | v3 | 120 | Not Available | 2026 | 08W | 1.54 | 3.11 | 0 | 4.65 | 0 | 0 | 0 | 0 | 1.54 | 3.11 | 0 | 4.65
35522102 | Base SH | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | SIERRA | v3 | 128 | Not Available | 2026 | 08W | 1.2299 | 2.2701 | 0 | 3.5 | 0 | 0 | 0 | 0 | 1.2299 | 2.2701 | 0 | 3.5
35522105 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011612 | SHASTA | v2 | 1791 | Not Available | 2026 | 08W | 4.4799 | 3.5299 | 0 | 8.0098 | 0 | 0 | 0 | 0 | 4.4799 | 3.5299 | 0 | 8.0098
35522111 | Base SH | 153081112 | PLACERVILLE 1112 | PLACERVILLE 111219712 | EL DORADO | v3 | 148 | Not Available | 2026 | 08W | 7.4299 | 5.8299 | 0 | 13.2598 | 0 | 0 | 0 | 0 | 7.4299 | 5.8299 | 0 | 13.2598
35523401 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v3 | 127 | Not Available | 2025 | 3UG | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 1.54
35523402 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v3 | 127 | Not Available | 2025 | 3UG | 0 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0 | 0 | 0 | 3.1299 | 0 | 3.1299
35523410 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v3 | 127 | Not Available | 2025 | 3UG | 0 | 2.86 | 0 | 2.86 | 0 | 0 | 0 | 0 | 0 | 2.86 | 0 | 2.86
35523412 | Base SH | 252931102 | TEJON 1102 | TEJON 1102732836 | KERN | v3 | 219 | Not Available | 2025 | 3UG | 0 | 2.9021 | 0 | 2.9021 | 0 | 0 | 0 | 0 | 0 | 2.9021 | 0 | 2.9021
35523413 | Base SH | 252931102 | TEJON 1102 | TEJON 1102732836 | KERN | v3 | 219 | Not Available | 2025 | 3UG | 0 | 2.8131 | 0 | 2.8131 | 0 | 0 | 0 | 0 | 0 | 2.8131 | 0 | 2.8131
35523414 | Base SH | 252931102 | TEJON 1102 | TEJON 1102732836 | KERN | v3 | 219 | Not Available | 2025 | 3UG | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443
35523415 | Base SH | 252931102 | TEJON 1102 | TEJON 1102732836 | KERN | v3 | 219 | Not Available | 2025 | 3UG | 0 | 1.954 | 0 | 1.954 | 0 | 0 | 0 | 0 | 0 | 1.954 | 0 | 1.954
35523416 | Base SH | 252931102 | TEJON 1102 | TEJON 11023751 | KERN | v3 | 368 | Not Available | 2025 | 3UG | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 0 | 2.958 | 0 | 2.958
35523417 | Base SH | 252931102 | TEJON 1102 | TEJON 11023751 | KERN | v3 | 368 | Not Available | 2025 | 3UG | 0 | 2.2521 | 0 | 2.2521 | 0 | 0 | 0 | 0 | 0 | 2.2521 | 0 | 2.2521
35523418 | Base SH | 252931102 | TEJON 1102 | TEJON 11023751 | KERN | v3 | 368 | Not Available | 2025 | 3UG | 0 | 2.997 | 0 | 2.997 | 0 | 0 | 0 | 0 | 0 | 2.997 | 0 | 2.997
35523419 | Base SH | 252931102 | TEJON 1102 | TEJON 11023751 | KERN | v3 | 368 | Not Available | 2025 | 3UG | 0 | 1.357 | 0 | 1.357 | 0 | 0 | 0 | 0 | 0 | 1.357 | 0 | 1.357
35523540 | Base SH | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | LAKE | v3 | 29 | Not Available | 2025 | 3UG | 0 | 0.77992 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0 | 0.77992 | 0 | 0.77992
35524565 | Base SH | 163351703 | CURTIS 1703 | CURTIS 17039240 | TUOLUMNE | v3 | 67 | Not Available | 2026 | 08W | 1.4799 | 12.64 | 0 | 14.1199 | 0 | 0 | 0 | 0 | 1.4799 | 12.64 | 0 | 14.1199
35524572 | Base SH | 101321101 | PIT NO 5 1101 | PIT NO 5 1101CB | SHASTA | v3 | 104 | Not Available | 2026 | 08W | 0 | 0.92992 | 0 | 0.92992 | 0 | 0 | 0 | 0 | 0 | 0.92992 | 0 | 0.92992
35526460 | Base SH | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | PLACER | v3 | 71 | Not Available | 2025 | 08W | 1.1799 | 0.52008 | 0 | 1.7 | 0 | 0 | 0 | 0 | 1.1799 | 0.52008 | 0 | 1.7
35526461 | Base SH | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | PLACER | v3 | 71 | Not Available | 2025 | 08W | 1.6 | 10.14 | 0 | 11.74 | 0 | 0 | 0 | 0 | 1.6 | 10.14 | 0 | 11.74
35526462 | Base SH | 152431102 | SHADY GLEN 1102 | SHADY GLEN 110248894 | NEVADA | v3 | 89 | Not Available | 2025 | 08W | 1.9201 | 2.74 | 0 | 4.66 | 0 | 0 | 0 | 0 | 1.9201 | 2.74 | 0 | 4.66
35526463 | Base SH | 103271101 | ANTLER 1101 | ANTLER 1101CB | SHASTA | v3 | 94 | Not Available | 2025 | 08W | 0.68996 | 0.93996 | 0 | 1.6299 | 0 | 0 | 0 | 0 | 0.68996 | 0.93996 | 0 | 1.6299
35526464 | Base SH | 152181102 | FORESTHILL 1102 | FORESTHILL 11022106 | PLACER | v3 | 97 | Not Available | 2025 | 08W | 0.68996 | 7.2701 | 0 | 7.96 | 0 | 0 | 0 | 0 | 0.68996 | 7.2701 | 0 | 7.96
35526465 | Base SH | 152181102 | FORESTHILL 1102 | FORESTHILL 11022106 | PLACER | v3 | 97 | Not Available | 2025 | 08W | 4.39 | 5.44 | 0 | 9.8299 | 0 | 0 | 0 | 0 | 4.39 | 5.44 | 0 | 9.8299
35526466 | Base SH | 152181102 | FORESTHILL 1102 | FORESTHILL 11022106 | PLACER | v3 | 97 | Not Available | 2025 | 08W | 2.3799 | 5.81 | 0 | 8.19 | 0 | 0 | 0 | 0 | 2.3799 | 5.81 | 0 | 8.19
35112126 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2024-04-19 | 2024 | 08W | 0 | 1.8964 | 0 | 1.8964 | 0 | 1.8964 | 0 | 1.8964 | 0 | 0 | 0 | 0
35127550 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2024-04-08 | 2024 | 95F | 0 | 1.6614 | 0 | 1.6614 | 0 | 1.6614 | 0 | 1.6614 | 0 | 0 | 0 | 0
35352072 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 11061212 | BUTTE | v2 | Not Available | 2024-01-29 | 2024 | 08W | 0 | 0.70947 | 0 | 0.70947 | 0 | 0.70947 | 0 | 0.70947 | 0 | 0 | 0 | 0
35117455 | Community Rebuild | 102831106 | PARADISE 1106 | Paradise 1106CB | BUTTE | v2 | Not Available | 2023-05-01 | 2024 | 08W | 0 | 0.37652 | 0 | 0.37652 | 0 | 0.37652 | 0 | 0.37652 | 0 | 0 | 0 | 0
35227400 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | v2 | Not Available | 2023-08-28 | 2024 | 95F | 0 | 2.1845 | 0 | 2.1845 | 0 | 2.1845 | 0 | 2.1845 | 0 | 0 | 0 | 0
35227402 | Community Rebuild | 102831105 | PARADISE 1105 | Paradise 1105CB | BUTTE | v2 | Not Available | 2023-03-15 | 2024 | 95F | 0 | 0.3053 | 0 | 0.3053 | 0 | 0.3053 | 0 | 0.3053 | 0 | 0 | 0 | 0
35246589 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | v2 | Not Available | 2023-10-05 | 2024 | 08W | 0 | 0.44167 | 0 | 0.44167 | 0 | 0.44167 | 0 | 0.44167 | 0 | 0 | 0 | 0
35475301 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104409622 | BUTTE | v2 | Not Available | 2024-02-26 | 2024 | 95F | 0 | 1.3055 | 0 | 1.3055 | 0 | 1.3055 | 0 | 1.3055 | 0 | 0 | 0 | 0
35246590 | Community Rebuild | 102831104 | PARADISE 1104 | Paradise 11042206 | BUTTE | v2 | Not Available | 2023-07-10 | 2024 | 08W | 0 | 1.0441 | 0 | 1.0441 | 0 | 1.0441 | 0 | 1.0441 | 0 | 0 | 0 | 0
35246308 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104920400 | BUTTE | v2 | Not Available | 2024-02-29 | 2024 | 95F | 0 | 0.68977 | 0 | 0.68977 | 0 | 0.68977 | 0 | 0.68977 | 0 | 0 | 0 | 0
35244220 | Community Rebuild | 102831103 | PARADISE 1103 | PARADISE 1103143744 | BUTTE | v2 | Not Available | 2024-04-15 | 2024 | 08W | 0 | 2.2742 | 0 | 2.2742 | 0 | 2.2742 | 0 | 2.2742 | 0 | 0 | 0 | 0
35491035 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 110453544 | BUTTE | v2 | Not Available | 2024-07-23 | 2024 | 95F | 0 | 0.53106 | 0 | 0.53106 | 0 | 0.53106 | 0 | 0.53106 | 0 | 0 | 0 | 0
35227413 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 110443008 | BUTTE | v2 | Not Available | 2024-03-04 | 2024 | 95F | 0 | 1.1794 | 0 | 1.1794 | 0 | 1.1794 | 0 | 1.1794 | 0 | 0 | 0 | 0
35227409 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104409622 | BUTTE | v2 | Not Available | 2023-09-18 | 2024 | 95F | 0 | 2.2646 | 0 | 2.2646 | 0 | 2.2646 | 0 | 2.2646 | 0 | 0 | 0 | 0
35246594 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104409622 | BUTTE | v2 | Not Available | 2024-04-29 | 2024 | 08W | 0 | 1.9519 | 0 | 1.9519 | 0 | 1.9519 | 0 | 1.9519 | 0 | 0 | 0 | 0
35246316 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104409622 | BUTTE | v2 | Not Available | 2024-02-05 | 2024 | 08W | 0 | 4.9066 | 0 | 4.9066 | 0 | 4.9066 | 0 | 4.9066 | 0 | 0 | 0 | 0
35246592 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 11042034 | BUTTE | v2 | Not Available | 2024-03-04 | 2024 | 08W | 0 | 2.2205 | 0 | 2.2205 | 0 | 2.2205 | 0 | 2.2205 | 0 | 0 | 0 | 0
35353463 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105121988 | BUTTE | v2 | Not Available | 2024-06-03 | 2024 | 08W | 0 | 2.5441 | 0 | 2.5441 | 0 | 2.5441 | 0 | 2.5441 | 0 | 0 | 0 | 0
35118673 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105121988 | BUTTE | v2 | Not Available | 2023-09-18 | 2024 | 08W | 0 | 2.9197 | 0 | 2.9197 | 0 | 2.9197 | 0 | 2.9197 | 0 | 0 | 0 | 0
35118674 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105121988 | BUTTE | v2 | Not Available | 2023-08-14 | 2024 | 08W | 0 | 2.1636 | 0 | 2.1636 | 0 | 2.1636 | 0 | 2.1636 | 0 | 0 | 0 | 0
35353468 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105829194 | BUTTE | v2 | Not Available | 2024-04-15 | 2024 | 08W | 0 | 1.7324 | 0 | 1.7324 | 0 | 1.7324 | 0 | 1.7324 | 0 | 0 | 0 | 0
35353470 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105829194 | BUTTE | v2 | Not Available | 2024-07-01 | 2025 | 08W | 0 | 3.5631 | 0 | 3.5631 | 0 | 1.7045 | 0 | 1.7045 | 0 | 1.8585 | 0 | 1.8585
35353525 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105829194 | BUTTE | v2 | Not Available | 2024-06-03 | 2024 | 08W | 0 | 2.0767 | 0 | 2.0767 | 0 | 2.0767 | 0 | 2.0767 | 0 | 0 | 0 | 0
35353527 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105878870 | BUTTE | v2 | Not Available | 2024-07-15 | 2024 | 08W | 0 | 1.3218 | 0 | 1.3218 | 0 | 1.3218 | 0 | 1.3218 | 0 | 0 | 0 | 0
35441211 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 11052214 | BUTTE | v2 | Not Available | 2024-09-10 | 2024 | 08W | 0 | 0.45568 | 0 | 0.45568 | 0 | 0.45568 | 0 | 0.45568 | 0 | 0 | 0 | 0
35246595 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 5.8848 | 0 | 5.8848 | 0 |  | 0 | 0 | 0 | 5.8848 | 0 | 5.8848
35244027 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 11052214 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 3.9258 | 0 | 3.9258 | 0 |  | 0 | 0 | 0 | 3.9258 | 0 | 3.9258
35463723 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 1.3258 | 0 | 1.3258 | 0 |  | 0 | 0 | 0 | 1.3258 | 0 | 1.3258
35486222 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 11052214 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 95F | 0 | 1.0114 | 0 | 1.0114 | 0 |  | 0 | 0 | 0 | 1.0114 | 0 | 1.0114
35424604 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 11042206 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 3.0303 | 0 | 3.0303 | 0 |  | 0 | 0 | 0 | 3.0303 | 0 | 3.0303
35227412 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 1104920400 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 95F | 0 | 3.1021 | 0 | 3.1021 | 0 |  | 0 | 0 | 0 | 3.1021 | 0 | 3.1021
35227417 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 110443008 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 95F | 0 | 1.1364 | 0 | 1.1364 | 0 |  | 0 | 0 | 0 | 1.1364 | 0 | 1.1364
35246591 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 110439216 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 3.9011 | 0 | 3.9011 | 0 |  | 0 | 0 | 0 | 3.9011 | 0 | 3.9011
35353477 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105829194 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 2.0114 | 0 | 2.0114 | 0 |  | 0 | 0 | 0 | 2.0114 | 0 | 2.0114
35353479 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105829194 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 1.8172 | 0 | 1.8172 | 0 |  | 0 | 0 | 0 | 1.8172 | 0 | 1.8172
35246309 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2025-01-02 | 2025 | 08W | 0 | 1.2898 | 0 | 1.2898 | 0 |  | 0 | 0 | 0 | 1.2898 | 0 | 1.2898
35179068 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 11042488 | BUTTE | v2 | Not Available | 2023-10-03 | 2024 | 95F | 0 | 0.077462 | 0 | 0.077462 | 0 | 0.077462 | 0 | 0.077462 | 0 | 0 | 0 | 0
35254275 | Community Rebuild | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | v2 | Not Available | 2022-02-28 | 2024 | 95F | 0 | 0.074432 | 0 | 0.074432 | 0 | 0.074432 | 0 | 0.074432 | 0 | 0 | 0 | 0
35487869 | Community Rebuild | 102831104 | PARADISE 1104 | PARADISE 110443008 | BUTTE | v2 | Not Available | 2023-12-31 | 2024 | 95F | 0 | 0.21686 | 0 | 0.21686 | 0 | 0.21686 | 0 | 0.21686 | 0 | 0 | 0 | 0
35254345 | Community Rebuild | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | v2 | Not Available | 2022-11-21 | 2024 | 95F | 0 | 0.00625 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | 0
35499494 | Community Rebuild | Not Available | Not Available | Not Available | BUTTE | v2 | Not Available | 2023-08-19 | 2024 | 08W | 0 | 0.47348 | 0 | 0.47348 | 0 | 0.47348 | 0 | 0.47348 | 0 | 0 | 0 | 0
35469309 | Community Rebuild | Not Available | Not Available | Not Available | BUTTE | v2 | Not Available | 2023-08-22 | 2024 | 95F | 0 | 0.073295 | 0 | 0.073295 | 0 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0 | 0
35038611 | Idle Facilities | 63801102 | JAMESON 1102 | JAMESON 1102865502 | SOLANO | v2 | 67 | Not Available | 2024 | 2AF | 0 | 0 | 0.20833 | 0.20833 | 0 | 0 | 0.20833 | 0.20833 | 0 | 0 | 0 | 0
35038684 | Idle Facilities | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 1101402 | MENDOCINO | v2 | 1293 | Not Available | 2024 | 2AF | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0.16818 | 0.16818 | 0 | 0 | 0 | 0
35078178 | Idle Facilities | 82841101 | BIG BASIN 1101 | BIG BASIN 11015028 | SANTA CRUZ | v2 | 2968 | Not Available | 2024 | 2AF | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35099926 | Idle Facilities | 254061102 | DUNLAP 1102 | DUNLAP 11027849F | TULARE | v2 | 589 | Not Available | 2024 | 2AF | 0 | 0 | 0.47973 | 0.47973 | 0 | 0 | 0.47973 | 0.47973 | 0 | 0 | 0 | 0
35145458 | Idle Facilities | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 2105454432 | MARIPOSA | v2 | 882 | 2024-02-12 | 2024 | 2AF | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 0 | 0
35149235 | Idle Facilities | 43361103 | HIGHLANDS 1103 | HIGHLANDS 11031282 | LAKE | v2 | 626 | 2024-05-30 | 2024 | 2AF | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0 | 0
35150641 | Idle Facilities | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103568 | LAKE | v2 | 212 | Not Available | 2024 | 2AF | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0 | 0
35150991 | Idle Facilities | 192311142 | FRUITLAND 1142 | FRUITLAND 114263170 | HUMBOLDT | v2 | 1429 | 2024-01-25 | 2024 | 2AF | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0 | 0
35151005 | Idle Facilities | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101412 | LAKE | v2 | 259 | Not Available | 2024 | 2AF | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0 | 0
35165775 | Idle Facilities | 153081109 | PLACERVILLE 1109 | PLACERVILLE 1109868678 | EL DORADO | v2 | N/A | 2022-10-07 | 2024 | 2AF | 0 | 0 | 0.2108 | 0.2108 | 0 | 0 | 0.2108 | 0.2108 | 0 | 0 | 0 | 0
35204814 | Idle Facilities | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | SHASTA | v2 | 820 | 2024-03-18 | 2024 | 2AF | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0 | 0
35207962 | Idle Facilities | 103601101 | WHITMORE 1101 | WHITMORE 11011594 | SHASTA | v2 | 678 | Not Available | 2024 | 2AF | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0
35208054 | Idle Facilities | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v2 | 1666 | 2024-02-17 | 2024 | 2AF | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0 | 0
35208094 | Idle Facilities | 192221102 | GARBERVILLE 1102 | GARBERVILLE 110237054 | HUMBOLDT | v2 | 1237 | Not Available | 2024 | 2AF | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0.079735 | 0.079735 | 0 | 0 | 0 | 0
35208097 | Idle Facilities | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103482 | LAKE | v2 | 181 | Not Available | 2024 | 2AF | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0 | 0
35211643 | Idle Facilities | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 11031500 | SHASTA | v2 | 981 | Not Available | 2024 | 2AF | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0.24489 | 0.24489 | 0 | 0 | 0 | 0
35211659 | Idle Facilities | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 1101764 | YUBA | v2 | 1590 | Not Available | 2024 | 2AF | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0 | 0
35217564 | Idle Facilities | 153132101 | NARROWS 2101 | NARROWS 21011202 | YUBA | v2 | 758 | Not Available | 2024 | 2AF | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35221249 | Idle Facilities | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110292622 | BUTTE | v2 | 771 | Not Available | 2024 | 2AF | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0.086364 | 0.086364 | 0 | 0 | 0 | 0
35221620 | Idle Facilities | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR176 | SANTA CLARA | v2 | 854 | 2024-06-30 | 2024 | 2AF | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0
35221715 | Idle Facilities | 163351705 | CURTIS 1705 | CURTIS 17058170 | TUOLUMNE | v2 | 1770 | Not Available | 2024 | 2AF | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0
35224438 | Idle Facilities | 183101104 | CABRILLO 1104 | CABRILLO 1104Y24 | SANTA BARBARA | v2 | 949 | Not Available | 2024 | 2AF | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0 | 0
35225011 | Idle Facilities | 183071101 | PERRY 1101 | PERRY 1101V74 | SAN LUIS OBISPO | v2 | 2433 | Not Available | 2024 | 2AF | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0
35225318 | Idle Facilities | 183031101 | PALMER 1101 | PALMER 1101M84 | SANTA BARBARA | v2 | 256 | Not Available | 2024 | 2AF | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0 | 0
35225467 | Idle Facilities | 83692104 | ROB ROY 2104 | ROB ROY 210410298 | SANTA CRUZ | v2 | 2387 | Not Available | 2024 | 2AF | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0 | 0
35226625 | Base SH | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | GLENN | v2 | 340 | 2025-03-25 08:00 | 2025 | 08W | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9 | 8.9
35226873 | Base SH | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | 2024-09-12 08:00 | 2025 | 08W | 0 | 0 | 1.0394 | 1.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 1.0394
35227654 | Base SH | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SOLANO | v2 | 42 | Not Available | 2024 | 08W | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0.87216 | 0.87216 | 0 | 0 | 0 | 0
35231623 | Base SH | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | LAKE | v2 | 27 | 2024-05-01 | 2024 | 08W | 0 | 0 | 1.3917 | 1.3917 | 0 | 0 | 1.3917 | 1.3917 | 0 | 0 | 0 | 0
35235701 | Fire Rebuild | 103221101 | KANAKA 1101 | KANAKA 1101CB | BUTTE | v2 | 1480 | 2024-06-04 08:00 | 2025 | 08W | 0 | 0 | 0.10909 | 0.10909 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10909 | 0.10909
35236997 | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | BUTTE | v2 | 1299 | 2023-07-05 08:00 | 2025 | 08W | 0 | 0 | 0.066288 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066288 | 0.066288
35241060 | Base SH | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | MADERA | v2 | 421 | 2022-11-02 | 2024 | 08W | 0 | 0 | 1.3898 | 1.3898 | 0 | 0 | 1.3898 | 1.3898 | 0 | 0 | 0 | 0
35241075 | Fire Rebuild | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | BUTTE | v2 | 1299 | 2023-07-10 08:00 | 2025 | 08W | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758
35242865 | Idle Facilities | 24251101 | WOODSIDE 1101 | WOODSIDE 11018972 | SAN MATEO | v2 | 1376 | Not Available | 2024 | 2AF | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35243444 | Base SH | 102541101 | VOLTA 1101 | VOLTA 11011568 | SHASTA | v2 | 85 | 2024-01-17 | 2024 | 08W | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
35243447 | Base SH | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SHASTA | v2 | 100 | 2024-05-01 08:00 | 2024 | 08W | 2.64 | 0 | 0.032955 | 2.6729 | 2.64 | 0 | 0.032955 | 2.6729 | 0 | 0 | 0 | 0
35244017 | Idle Facilities | 192221101 | GARBERVILLE 1101 | GARBERVILLE 1101323694 | HUMBOLDT | v2 | 1750 | Not Available | 2024 | 2AF | 0 | 0 | 0.25189 | 0.25189 | 0 | 0 | 0.25189 | 0.25189 | 0 | 0 | 0 | 0
35244105 | Idle Facilities | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | v2 | 474 | Not Available | 2024 | 2AF | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35244150 | Idle Facilities | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102CB | NEVADA | v2 | 1700 | Not Available | 2024 | 2AF | 0 | 0 | 0.022727 | 0.022727 | 0 | 0 | 0.022727 | 0.022727 | 0 | 0 | 0 | 0
35244173 | Idle Facilities | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210911092 | EL DORADO | v2 | 2116 | Not Available | 2024 | 2AF | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0 | 0
35247033 | Idle Facilities | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | SANTA CLARA | v2 | 1864 | Not Available | 2024 | 2AF | 0 | 0 | 0.070644 | 0.070644 | 0 | 0 | 0.070644 | 0.070644 | 0 | 0 | 0 | 0
35249877 | Base SH | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21046210 | MADERA | v2 | 132 | 2023-07-31 08:00 | 2024 | 08W | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 0
35250938 | Idle Facilities | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 210851476 | EL DORADO | v2 | 424 | Not Available | 2024 | 2AF | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0.24432 | 0.24432 | 0 | 0 | 0 | 0
35254738 | Base SH | 102541101 | VOLTA 1101 | VOLTA 11011568 | SHASTA | v2 | 85 | 2024-01-04 08:00 | 2024 | 08W | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0
35254940 | Base SH | 102541101 | VOLTA 1101 | VOLTA 11011568 | SHASTA | v2 | 85 | 2023-08-29 | 2024 | 08W | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0.64697 | 0.64697 | 0 | 0 | 0 | 0
35260868 | Idle Facilities | 162161101 | ELECTRA 1101 | ELECTRA 110161816 | AMADOR | v2 | 1571 | Not Available | 2024 | 2AF | 0 | 0 | 0.21098 | 0.21098 | 0 | 0 | 0.21098 | 0.21098 | 0 | 0 | 0 | 0
35274594 | Base SH | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | MARIPOSA | v2 | 428 | 2023-11-03 | 2024 | 08W | 0.23447 | 0 | 0.12367 | 0.35814 | 0.23447 | 0 | 0.12367 | 0.35814 | 0 | 0 | 0 | 0
35281215 | Idle Facilities | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | AMADOR | v2 | 1548 | Not Available | 2024 | 2AF | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0 | 0
35284366 | Base SH | 162821702 | STANISLAUS 1702 | STANISLAUS 1702CB | TUOLUMNE | v2 | 235 | 2024-04-25 08:00 | 2025 | 08W | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60871 | 0.60871
35285462 | Idle Facilities | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110147968 | CALAVERAS | v2 | 1941 | Not Available | 2024 | 2AF | 0 | 0 | 0.16496 | 0.16496 | 0 | 0 | 0.16496 | 0.16496 | 0 | 0 | 0 | 0
35290545 | Fire Rebuild | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | v2 | 995 | Not Available | 2025 | 08W | 0 | 0 | 0.66932 | 0.66932 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66932 | 0.66932
35297984 | Fire Rebuild | 103561101 | STILLWATER 1101 | STILLWATER 110148950 | SHASTA | v2 | 851 | Not Available | 2025 | 08W | 0 | 0 | 1.1201 | 1.1201 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1201 | 1.1201
35312067 | Idle Facilities | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11014786 | CALAVERAS | v2 | 804 | Not Available | 2024 | 2AF | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0
35329015 | Base SH | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022070 | BUTTE | v2 | 1033 | 2024-07-02 08:00 | 2024 | 08W | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 1.9299 | 1.9299 | 0 | 0 | 0 | 0
35330243 | Base SH | 43191101 | REDBUD 1101 | REDBUD 1101323962 | LAKE | v2 | 423 | 2025-07-18 08:00 | 2025 | 08W | 0 | 0 | 4.1479 | 4.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1479 | 4.1479
35331303 | Base SH | 103261103 | ANDERSON 1103 | ANDERSON 11031600 | SHASTA | v2 | 143 | 2025-08-04 08:00 | 2025 | 08W | 1.1837 | 0 | 0.1 | 1.2837 | 0 | 0 | 0 | 0 | 1.1837 | 0 | 0.1 | 1.2837
35332361 | Base SH | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | v2 | 315 | Not Available | 2025 | 08W | 0 | 0 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2
35334230 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | 2024-11-14 08:00 | 2025 | 08W | 0 | 0 | 3.6701 | 3.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6701 | 3.6701
35337164 | Base SH | 153701104 | LINCOLN 1104 | LINCOLN 1104275986 | PLACER | v2 | 185 | 2025-07-25 08:00 | 2025 | 08W | 1.9701 | 0 | 0.86004 | 2.8301 | 0 | 0 | 0 | 0 | 1.9701 | 0 | 0.86004 | 2.8301
35338364 | Idle Facilities | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101439572 | LAKE | v2 | 450 | Not Available | 2024 | 2AF | 0 | 0 | 0.092045 | 0.092045 | 0 | 0 | 0.092045 | 0.092045 | 0 | 0 | 0 | 0
35353435 | Base SH | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | EL DORADO | v2 | 1363 | 2025-05-16 08:00 | 2025 | 08W | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7
35355026 | Idle Facilities | 103541101 | RED BLUFF 1101 | RED BLUFF 11011556 | TEHAMA | v2 | 390 | Not Available | 2024 | 2AF | 0 | 0 | 0.10057 | 0.10057 | 0 | 0 | 0.10057 | 0.10057 | 0 | 0 | 0 | 0
35355041 | Idle Facilities | 192461102 | BRIDGEVILLE 1102 | BRIDGEVILLE 110255612 | HUMBOLDT | v2 | 816 | Not Available | 2024 | 2AF | 0 | 0 | 0.040341 | 0.040341 | 0 | 0 | 0.040341 | 0.040341 | 0 | 0 | 0 | 0
35355043 | Idle Facilities | 153132101 | NARROWS 2101 | NARROWS 2101CB | YUBA | v2 | 287 | Not Available | 2024 | 2AF | 0 | 0 | 0.082765 | 0.082765 | 0 | 0 | 0.082765 | 0.082765 | 0 | 0 | 0 | 0
35355045 | Idle Facilities | 153132101 | NARROWS 2101 | NARROWS 2101CB | YUBA | v2 | 287 | Not Available | 2024 | 2AF | 0 | 0 | 0.23504 | 0.23504 | 0 | 0 | 0.23504 | 0.23504 | 0 | 0 | 0 | 0
35355050 | Idle Facilities | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 110193870 | YUBA | v2 | 774 | Not Available | 2024 | 2AF | 0 | 0 | 0.033902 | 0.033902 | 0 | 0 | 0.033902 | 0.033902 | 0 | 0 | 0 | 0
35355350 | Idle Facilities | 103191101 | BANGOR 1101 | BANGOR 110182350 | YUBA | v2 | 363 | 2024-02-13 | 2024 | 2AF | 0 | 0 | 0.066477 | 0.066477 | 0 | 0 | 0.066477 | 0.066477 | 0 | 0 | 0 | 0
35355353 | Idle Facilities | 103201101 | CHALLENGE 1101 | CHALLENGE 1101CB | BUTTE | v2 | 1874 | Not Available | 2024 | 2AF | 0 | 0 | 0.061742 | 0.061742 | 0 | 0 | 0.061742 | 0.061742 | 0 | 0 | 0 | 0
35359451 | Idle Facilities | 43291105 | PUEBLO 1105 | PUEBLO 1105637242 | NAPA | v2 | 873 | Not Available | 2024 | 2AF | 0 | 0 | 0.24943 | 0.24943 | 0 | 0 | 0.24943 | 0.24943 | 0 | 0 | 0 | 0
35359496 | Idle Facilities | 43292103 | PUEBLO 2103 | PUEBLO 210378504 | NAPA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.15152 | 0.15152 | 0 | 0 | 0.15152 | 0.15152 | 0 | 0 | 0 | 0
35359508 | Idle Facilities | 42571102 | MOLINO 1102 | MOLINO 1102178 | SONOMA | v2 | 1208 | 2023-10-16 | 2024 | 2AF | 0 | 0 | 0.0375 | 0.0375 | 0 | 0 | 0.0375 | 0.0375 | 0 | 0 | 0 | 0
35361657 | Idle Facilities | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 1101752104 | CALAVERAS | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.17879 | 0.17879 | 0 | 0 | 0.17879 | 0.17879 | 0 | 0 | 0 | 0
35372278 | Idle Facilities | 254061103 | DUNLAP 1103 | DUNLAP 11037220 | FRESNO | v2 | 364 | Not Available | 2024 | 2AF | 0 | 0 | 0.018939 | 0.018939 | 0 | 0 | 0.018939 | 0.018939 | 0 | 0 | 0 | 0
35372408 | Idle Facilities | 253142102 | CUYAMA 2101 | CUYAMA 21013542 | SANTA BARBARA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0.072538 | 0.072538 | 0 | 0 | 0 | 0
35380374 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | Not Available | 2025 | 08W | 0 | 0 | 2.5299 | 2.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5299 | 2.5299
35380375 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | Not Available | 2026 | 08W | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85
35380377 | Base SH | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | v2 | 413 | 2024-07-15 08:00 | 2025 | 08W | 0 | 0 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09
35384512 | Idle Facilities | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 1107CB | EL DORADO | v3 | 2896 | Not Available | 2024 | 2AF | 0 | 0 | 0.11023 | 0.11023 | 0 | 0 | 0.11023 | 0.11023 | 0 | 0 | 0 | 0
35384519 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 1102CB | CALAVERAS | v2 | 1634 | Not Available | 2024 | 2AF | 0 | 0 | 0.093182 | 0.093182 | 0 | 0 | 0.093182 | 0.093182 | 0 | 0 | 0 | 0
35387702 | Idle Facilities | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11057722 | EL DORADO | v2 | 649 | Not Available | 2024 | 2AF | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0.054924 | 0.054924 | 0 | 0 | 0 | 0
35390785 | Idle Facilities | 43361102 | HIGHLANDS 1102 | HIGHLANDS 110275140 | LAKE | v2 | 1129 | Not Available | 2024 | 2AF | 0 | 0 | 0.042992 | 0.042992 | 0 | 0 | 0.042992 | 0.042992 | 0 | 0 | 0 | 0
35390793 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | CALAVERAS | v2 | 1909 | Not Available | 2024 | 2AF | 0 | 0 | 0.19527 | 0.19527 | 0 | 0 | 0.19527 | 0.19527 | 0 | 0 | 0 | 0
35391226 | Idle Facilities | 43311102 | KONOCTI 1102 | KONOCTI 1102354890 | LAKE | v2 | 139 | Not Available | 2024 | 2AF | 0 | 0 | 0.061553 | 0.061553 | 0 | 0 | 0.061553 | 0.061553 | 0 | 0 | 0 | 0
35395931 | Base SH | 103271101 | ANTLER 1101 | ANTLER 11011520 | SHASTA | v3 | 91 | Not Available | 2026 | 08W | 0 | 0 | 2.377 | 2.377 | 0 | 0 | 0 | 0 | 0 | 0 | 2.377 | 2.377
35396566 | Base SH | 103751101 | BIG BEND 1101 | BIG BEND 1101641808 | BUTTE | v3 | 318 | 2024-10-31 08:00 | 2025 | 08W | 0 | 0 | 1.7799 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 1.7799
35396567 | Base SH | 103381102 | FRENCH GULCH 1102 | FRENCH GULCH 11022902 | SHASTA | v3 | 262 | Not Available | 2026 | 08W | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939
35396568 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011588 | SHASTA | v3 | 83 | Not Available | 2026 | 08W | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939
35396569 | Base SH | 103451101 | KESWICK 1101 | KESWICK 11011588 | SHASTA | v3 | 83 | Not Available | 2026 | 08W | 0 | 0 | 1.8939 | 1.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8939 | 1.8939
35399124 | Idle Facilities | 42661104 | WILLITS 1104 | WILLITS 1104341020 | MENDOCINO | v2 | 778 | Not Available | 2024 | 2AF | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0
35401371 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | CALAVERAS | v3 | 384 | Not Available | 2024 | 2AF | 0 | 0 | 0.10417 | 0.10417 | 0 | 0 | 0.10417 | 0.10417 | 0 | 0 | 0 | 0
35404632 | Idle Facilities | 42661103 | WILLITS 1103 | WILLITS 1103538 | MENDOCINO | v2 | 937 | Not Available | 2024 | 2AF | 0 | 0 | 0.063258 | 0.063258 | 0 | 0 | 0.063258 | 0.063258 | 0 | 0 | 0 | 0
35406744 | Idle Facilities | 103601101 | WHITMORE 1101 | WHITMORE 1101 | SHASTA | v2 | 678 | Not Available | 2024 | 2AF | 0 | 0 | 0.051136 | 0.051136 | 0 | 0 | 0.051136 | 0.051136 | 0 | 0 | 0 | 0
35406748 | Idle Facilities | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 11011268 | YUBA | v2 | 550 | Not Available | 2024 | 2AF | 0 | 0 | 0.058712 | 0.058712 | 0 | 0 | 0.058712 | 0.058712 | 0 | 0 | 0 | 0
35409360 | Idle Facilities | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102878 | LAKE | v3 | 1051 | Not Available | 2024 | 2AF | 0 | 0 | 0.071212 | 0.071212 | 0 | 0 | 0.071212 | 0.071212 | 0 | 0 | 0 | 0
35418882 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 110277204 | CALAVERAS | v2 | 1815 | Not Available | 2024 | 2AF | 0 | 0 | 0.11591 | 0.11591 | 0 | 0 | 0.11591 | 0.11591 | 0 | 0 | 0 | 0
35418932 | Idle Facilities | 82831109 | MILPITAS 1109 | MILPITAS 1109903328 | SANTA CLARA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.0085227 | 0.0085227 | 0 | 0 | 0.0085227 | 0.0085227 | 0 | 0 | 0 | 0
35420799 | Idle Facilities | 42601102 | PHILO 1102 | PHILO 1102920 | MENDOCINO | v2 | 1835 | Not Available | 2024 | 2AF | 0 | 0 | 0.088636 | 0.088636 | 0 | 0 | 0.088636 | 0.088636 | 0 | 0 | 0 | 0
35420822 | Idle Facilities | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SOLANO | v2 | 42 | Not Available | 2024 | 2AF | 0 | 0 | 0.18144 | 0.18144 | 0 | 0 | 0.18144 | 0.18144 | 0 | 0 | 0 | 0
35421129 | Idle Facilities | 103401101 | GIRVAN 1101 | GIRVAN 11019732 | SHASTA | v3 | 209 | Not Available | 2024 | 2AF | 0 | 0 | 0.058902 | 0.058902 | 0 | 0 | 0.058902 | 0.058902 | 0 | 0 | 0 | 0
35421130 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 11024788 | CALAVERAS | v2 | 1206 | 2023-11-29 | 2024 | 2AF | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0 | 0
35429197 | Idle Facilities | 42861101 | ANNAPOLIS 1101 | ANNAPOLIS 1101 | SONOMA | v2 | 2204 | Not Available | 2024 | 2AF | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0 | 0
35429199 | Idle Facilities | 192401101 | HOOPA 1101 | HOOPA 1101 | HUMBOLDT | v2 | 1863 | Not Available | 2024 | 2AF | 0 | 0 | 0.03125 | 0.03125 | 0 | 0 | 0.03125 | 0.03125 | 0 | 0 | 0 | 0
35429200 | Idle Facilities | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101 | LAKE | v2 | 705 | Not Available | 2024 | 2AF | 0 | 0 | 0.047727 | 0.047727 | 0 | 0 | 0.047727 | 0.047727 | 0 | 0 | 0 | 0
35429205 | Idle Facilities | 82841102 | BIG BASIN 1102 | BIG BASIN 110212124 | SANTA CRUZ | v2 | 2256 | Not Available | 2024 | 2AF | 0 | 0 | 0.11648 | 0.11648 | 0 | 0 | 0.11648 | 0.11648 | 0 | 0 | 0 | 0
35431967 | Idle Facilities | 14341105 | VALLEY VIEW 1105 | VALLEY VIEW 1105305072 | CONTRA COSTA | v3 | 2447 | 2023-11-03 | 2024 | 2AF | 0 | 0 | 0.014205 | 0.014205 | 0 | 0 | 0.014205 | 0.014205 | 0 | 0 | 0 | 0
35432822 | Idle Facilities | 163781701 | PEORIA 1701 | PEORIA 1701169700 | TUOLUMNE | v2 | 2479 | Not Available | 2024 | 2AF | 0 | 0 | 0.088258 | 0.088258 | 0 | 0 | 0.088258 | 0.088258 | 0 | 0 | 0 | 0
35433291 | Idle Facilities | 43432104 | SILVERADO 2104 | SILVERADO 2104515946 | NAPA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0.032576 | 0.032576 | 0 | 0 | 0 | 0
35433303 | Idle Facilities | 43321103 | RINCON 1103 | RINCON 1103568 | SONOMA | v3 | 460 | Not Available | 2024 | 2AF | 0 | 0 | 0.2964 | 0.2964 | 0 | 0 | 0.2964 | 0.2964 | 0 | 0 | 0 | 0
35433764 | Base SH | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | BUTTE | v3 | 57 | Not Available | 2026 | 08W | 0 | 0 | 0.48 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0.48
35434924 | Idle Facilities | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106 | CONTRA COSTA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0.04072 | 0.04072 | 0 | 0 | 0 | 0
35434926 | Idle Facilities | 163351702 | CURTIS 1702 | CURTIS 170234426 | TUOLUMNE | v2 | 2355 | Not Available | 2024 | 2AF | 0 | 0 | 0.057955 | 0.057955 | 0 | 0 | 0.057955 | 0.057955 | 0 | 0 | 0 | 0
35434949 | Idle Facilities | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | v2 | 377 | Not Available | 2024 | 2AF | 0 | 0 | 0.25322 | 0.25322 | 0 | 0 | 0.25322 | 0.25322 | 0 | 0 | 0 | 0
35434962 | Idle Facilities | 13921104 | FRANKLIN 1104 | FRANKLIN 1104P146 | CONTRA COSTA | v3 | 2505 | 2023-12-11 | 2024 | 2AF | 0 | 0 | 0.01553 | 0.01553 | 0 | 0 | 0.01553 | 0.01553 | 0 | 0 | 0 | 0
35435567 | Idle Facilities | 153662102 | APPLE HILL 2102 | APPLE HILL 21028372 | EL DORADO | v2 | 654 | Not Available | 2024 | 2AF | 0 | 0 | 0.064394 | 0.064394 | 0 | 0 | 0.064394 | 0.064394 | 0 | 0 | 0 | 0
35435605 | Idle Facilities | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | EL DORADO | v3 | 68 | Not Available | 2024 | 2AF | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0
35436041 | Idle Facilities | 163201102 | WEST POINT 1102 | WEST POINT 11024788 | CALAVERAS | v2 | 1206 | Not Available | 2024 | 2AF | 0 | 0 | 0.035985 | 0.035985 | 0 | 0 | 0.035985 | 0.035985 | 0 | 0 | 0 | 0
35439171 | Idle Facilities | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104CB | MARIPOSA | v3 | 10 | Not Available | 2024 | 2AF | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0
35442809 | Idle Facilities | 254452102 | MARIPOSA 2102 | MARIPOSA 210237282 | MARIPOSA | v3 | 484 | Not Available | 2024 | 2AF | 0 | 0 | 0.33087 | 0.33087 | 0 | 0 | 0.33087 | 0.33087 | 0 | 0 | 0 | 0
35447090 | Idle Facilities | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11014786 | CALAVERAS | v2 | 804 | Not Available | 2024 | 2AF | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0 | 0
35449024 | Idle Facilities | 82021107 | LOS GATOS 1107 | LOS GATOS 1107CB | SANTA CLARA | v3 | 508 | Not Available | 2024 | 2AF | 0 | 0 | 0.017992 | 0.017992 | 0 | 0 | 0.017992 | 0.017992 | 0 | 0 | 0 | 0
35449025 | Idle Facilities | 83912110 | PIERCY 2110 | PIERCY 2110XR258 | SANTA CLARA | v3 | 852 | Not Available | 2024 | 2AF | 0 | 0 | 0.31061 | 0.31061 | 0 | 0 | 0.31061 | 0.31061 | 0 | 0 | 0 | 0
35455636 | Idle Facilities | 162821702 | STANISLAUS 1702 | STANISLAUS 170237278 | CALAVERAS | v3 | 98 | 2024-02-14 | 2024 | 2AF | 0 | 0 | 0.036932 | 0.036932 | 0 | 0 | 0.036932 | 0.036932 | 0 | 0 | 0 | 0
35460267 | Idle Facilities | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | SANTA BARBARA | v3 | 1417 | Not Available | 2024 | 2AF | 0 | 0 | 0.06875 | 0.06875 | 0 | 0 | 0.06875 | 0.06875 | 0 | 0 | 0 | 0
35460269 | Idle Facilities | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101CB | SIERRA | v3 | 170 | Not Available | 2024 | 2AF | 0 | 0 | 0.064394 | 0.064394 | 0 | 0 | 0.064394 | 0.064394 | 0 | 0 | 0 | 0
35475077 | Idle Facilities | 103441101 | JESSUP 1101 | JESSUP 110141356 | SHASTA | v3 | 479 | Not Available | 2024 | 2AF | 0 | 0 | 0.27367 | 0.27367 | 0 | 0 | 0.27367 | 0.27367 | 0 | 0 | 0 | 0
35479186 | Idle Facilities | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 210448268 | KERN | v3 | 1497 | Not Available | 2024 | 2AF | 0 | 0 | 1.0795 | 1.0795 | 0 | 0 | 1.0795 | 1.0795 | 0 | 0 | 0 | 0
35482519 | Idle Facilities | 12022212 | CLAYTON 2212 | CLAYTON 2212681608 | CONTRA COSTA | v2 | N/A | Not Available | 2024 | 2AF | 0 | 0 | 0.14261 | 0.14261 | 0 | 0 | 0.14261 | 0.14261 | 0 | 0 | 0 | 0
35511078 | Idle Facilities | 103381102 | FRENCH GULCH 1102 | FRENCH GULCH 11022902 | SHASTA | v2 | 2518 | Not Available | 2024 | 2AF | 0 | 0 | 0.019508 | 0.019508 | 0 | 0 | 0.019508 | 0.019508 | 0 | 0 | 0 | 0
35294840 | Idle Facilities | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | SHASTA | v2 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.18883 | 0.18883 | 0 | 0 | 0.18883 | 0.18883 | 0 | 0 | 0 | 0
35451154 | Idle Facilities | 103331101 | CORNING 1101 | CORNING 110164090 | TEHAMA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.18864 | 0.18864 | 0 | 0 | 0.18864 | 0.18864 | 0 | 0 | 0 | 0
35453793 | Idle Facilities | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21059570 | MARIPOSA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.12443 | 0.12443 | 0 | 0 | 0.12443 | 0.12443 | 0 | 0 | 0 | 0
35507355 | Idle Facilities | 103551101 | RISING RIVER 1101 | RISING RIVER 11011530 | SHASTA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.16894 | 0.16894 | 0 | 0 | 0.16894 | 0.16894 | 0 | 0 | 0 | 0
35511103 | Idle Facilities | 103451101 | KESWICK 1101 | KESWICK 11019712 | SHASTA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.032765 | 0.032765 | 0 | 0 | 0.032765 | 0.032765 | 0 | 0 | 0 | 0
35511686 | Idle Facilities | 163761704 | RACETRACK 1704 | RACETRACK 170455798 | TUOLUMNE | v2 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.11553 | 0.11553 | 0 | 0 | 0.11553 | 0.11553 | 0 | 0 | 0 | 0
35511690 | Idle Facilities | 163351704 | CURTIS 1704 | CURTIS 170463502 | TUOLUMNE | v2 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.090341 | 0.090341 | 0 | 0 | 0.090341 | 0.090341 | 0 | 0 | 0 | 0
35511693 | Idle Facilities | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | FRESNO | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0 | 0
35516072 | Idle Facilities | 42091102 | MIRABEL 1102 | MIRABEL 1102334 | SONOMA | v2 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.050189 | 0.050189 | 0 | 0 | 0.050189 | 0.050189 | 0 | 0 | 0 | 0
35516114 | Idle Facilities | 42091102 | MIRABEL 1102 | MIRABEL 1102334 | SONOMA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.019886 | 0.019886 | 0 | 0 | 0.019886 | 0.019886 | 0 | 0 | 0 | 0
35516116 | Idle Facilities | 42091102 | MIRABEL 1102 | MIRABEL 1102334 | SONOMA | v3 | N/A | Not Available | Not Available | 2AF | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0 | 0
35524570 | Base SH | 103501101 | PIT NO 7 1101 | PIT NO 7 1101CB | SHASTA | v3 | 549 | Not Available | 2025 | 08W | 0 | 0 | 2.7098 | 2.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7098 | 2.7098
35524571 | Base SH | 254061102 | DUNLAP 1102 | DUNLAP 11027050 | TULARE | v3 | 482 | Not Available | 2025 | 08W | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6
35526199 | Base SH | 162821701 | STANISLAUS 1701 | STANISLAUS 1701CB | CALAVERAS | v3 | 95 | Not Available | 2025 | 08W | 7.8 | 0 | 0.039962 | 7.84 | 0 | 0 | 0 | 0 | 7.8 | 0 | 0.039962 | 7.84

## Q2 l-m
CPZs where UG work planned for 2024-2026
CPZ | Customer Count (as of April 2024) | Sum of PSPS Minutes for Average Customer Outage on CPZ | Sum of PSPS Minutes for Maximum Event Duration on CPZ
MOLINO 110266006 | 172 | 7866.1453 | 10961
NORTH BRANCH 1101CB | 100 | 2356 | 2356
FROGTOWN 1702CB | 423 | 3963.7904 | 4273
MIDDLETOWN 1101548 | 366 | 20560.4088 | 31284
MIDDLETOWN 110148212 | 129 | 24631.7542 | 25045.55
PLACERVILLE 210611132 | 432 | 17098.9126 | 17302
BUCKS CREEK 1101CB | N/A | 27491 | 27491
HIGHLANDS 1102628 | 21 | 17248 | 17258
VACAVILLE 11046542 | 779 | 12290.7566 | 13738
OREGON TRAIL 110335002 | 786 | 14395 | 14395
DUNBAR 1101CB | 60 | 11271 | 11271
PARADISE 11042034 | 99 | 25029.8182 | 25096
KESWICK 11011586 | 24 | 14562 | 14562
MIDDLETOWN 1102302610 | 44 | 14818 | 14818
KANAKA 1101CB | 108 | 17518.7859 | 19446
ALLEGHANY 1102CB | 152 | 23000 | 23000
MARIPOSA 210135244 | 107 | N/A | N/A
MOUNTAIN QUARRIES 2101CB | 290 | 9905 | 9905
MOUNTAIN QUARRIES 21011350 | 248 | 13881.3761 | 13886
POTTER VALLEY P H 11051904 | 341 | 12897.2089 | 13401
AUBERRY 1101R2578 | 582 | 3564.8325 | 3905
UPPER LAKE 11011276 | 166 | 12528 | 12528
BUCKS CREEK 1102CB | 48 | 20898.726 | 22411
GANSNER 11012424 | 201 | 2744 | 2744
MARIPOSA 2102440236 | 495 | N/A | N/A
CRESCENT MILLS 21012056 | 115 | 2690 | 2690
KESWICK 11019712 | 270 | 13323 | 13323
ELECTRA 11017104 | 367 | 11096.5335 | 11106
GRAYS FLAT 0401CB | 115 | 2633 | 2633
HARTLEY 1101698 | 71 | 11947 | 11947
WOODSIDE 11018974 | 298 | 10212.9838 | 10497
DUNBAR 1101416 | 21 | 22653.1071 | 22816
STANISLAUS 1702CB | 71 | 12315.3333 | 12406
HALF MOON BAY 11036012 | 162 | 7870 | 7870
BIG MEADOWS 21012260 | 272 | 2589 | 2589
BIG MEADOWS 21012476 | 155 | 2589 | 2589
BUCKS CREEK 1103CB | 16 | 25315 | 25315
POINT MORETTI 110112122 | 54 | 3590.5 | 3593
CLARK ROAD 1102CB | 12 | 12021.5 | 14876
CLARK ROAD 11022094 | N/A | 25928.75 | 29669
CLARK ROAD 110247006 | 94 | 26585.4571 | 29590
BELL 11082202 | 509 | 8102.0101 | 10964
COTTONWOOD 11029026 | 285 | 10682.035 | 13135
DUNBAR 1103534 | 161 | 23029.4886 | 23814
ELK CREEK 11012002 | 30 | 9096.7719 | 9118
FLINT 1101750 | 188 | 4790.6011 | 7940
REDBUD 1101454 | 33 | 13489 | 13489
TEJON 11022455 | 263 | 10530 | 10530
WYANDOTTE 1110980944 | 1108 | 9463.399 | 12614
COTTONWOOD 1102544790 | 40 | 8839.4557 | 12954
REDBUD 1101323962 | 479 | 17045.6953 | 19336
VACAVILLE 11088762 | 152 | 14989.1751 | 16597
VACAVILLE 110847860 | 1118 | 9575.3186 | 12697
VACAVILLE 1111CB | 691 | 9354.4637 | 9919
VACAVILLE 111113652 | 74 | 10039.4296 | 10345
JAMESON 110265516 | 496 | 13971.2727 | 15338
LINCOLN 1104685276 | 194 | 9410 | 9410
JAMESON 1105466348 | 244 | 14150.0859 | 15495
REDBUD 1101708166 | 87 | 12000 | 12000
CURTIS 1701CB | 629 | 5712.6458 | 5874
CORNING 110253184 | 78 | 18108.0256 | 18112
VACAVILLE 110838316 | 88 | 15586 | 15586
JESSUP 11021550 | 218 | 14346.3443 | 15036
BIG BASIN 11025066 | 94 | 8252.9565 | 9262
CLAYTON 2212614950 | 48 | 2593 | 2593
SYCAMORE CREEK 11112268 | 274 | 18769 | 18769
BONNIE NOOK 1101CB | 349 | 17154.6045 | 17265
APPLE HILL 21027502 | 376 | 17847.9889 | 17940
EL DORADO PH 2101CB | 88 | 13882.1667 | 16061
FORESTHILL 110150486 | 914 | 14288.2528 | 17601
ORO FINO 110276008 | 364 | 26878 | 26878
ORO FINO 1102CB | 22 | 23452.0526 | 25359
SILVERADO 210478268 | 311 | 21106.8237 | 25296
WEST POINT 11014706 | 331 | 16845 | 16845
PINE GROVE 1101CB | 235 | 6689.5819 | 10315
TIGER CREEK 0201CB | 11 | 14262 | 14262
ANTLER 11011520 | 117 | 10486 | 10486
ANTLER 11011384 | 386 | 9417 | 9417
ELECTRA 1101L1697 | 246 | 11135.7468 | 12882
NOTRE DAME 11042028 | 130 | 20324.3759 | 20396
MARIPOSA 21019400 | 770 | 7941.1326 | 10569
MARIPOSA 210110170 | 197 | 6850 | 6850
PIKE CITY 11011720 | 28 | 21849 | 21849
SILVERADO 2104646776 | 254 | 17975.3372 | 21459
MIDDLETOWN 1101171414 | 21 | 17703.95 | 17747
WEST POINT 11021341 | 85 | 18954 | 18954
SILVERADO 2104632 | 242 | 24545.6759 | 24570
SILVERADO 2104515946 | 368 | 20426.2426 | 25395.6167
FORESTHILL 110137238 | 95 | 14886.9608 | 17447
PLACERVILLE 21061104 | 636 | 20200.3891 | 21423
KESWICK 11011588 | 29 | 14647 | 14647
PINE GROVE 110213438 | 284 | 17308 | 17308
PINE GROVE 11013166 | 246 | 12036.9587 | 12094
MIDDLETOWN 11011314 | 39 | 16729.3226 | 16732
APPLE HILL 1104CB | 212 | 11561.0234 | 14716
PLACERVILLE 2106935216 | 231 | 16314 | 16314
STANISLAUS 17026028 | 495 | 12884.1255 | 12989
WEST POINT 110277204 | 49 | 19982 | 19982
WEST POINT 11024788 | 592 | 18953.7397 | 18954
APPLE HILL 21026552 | 197 | 16956 | 16956
WEST POINT 1101CB | 4 | 16000 | 16000
STANISLAUS 17011812 | 587 | 14088 | 14088
CLAYTON 221296224 | 100 | 9178.59 | 9683
INDIAN FLAT 1104CB | 359 | 2967.2804 | 2969
STANISLAUS 170237278 | 438 | 13222 | 13222
CLAYTON 2212681608 | 271 | 6576.5201 | 7068
CORNING 1102915324 | N/A | 15331.0909 | 17551
PIT NO 3 2101CB | N/A | N/A | N/A
EL CERRITO G 1105BR160 | 1708 | 4971.8181 | 5090
DIAMOND SPRINGS 1402 | N/A | N/A | N/A
ECHO SUMMIT 1101481660 | 4 | 3206 | 3206
SILVERADO 2104708 | 133 | 15304.1025 | 18542
TEJON 1102732836 | 278 | 10573.8392 | 11176
CALISTOGA 110143924 | 397 | 25564.4191 | 27924.3833
SILVERADO 2105167360 | 80 | 15873 | 15873
INDIAN FLAT 1104CB | 359 | 2967.2804 | 2969
NARROWS 2102CB | 28 | 9133.3667 | 13359
PIKE CITY 1101CB | 229 | 21355 | 21355
SILVERADO 2105658898 | 109 | 13588 | 13588
MARIPOSA 210110240 | 280 | N/A | N/A
SILVERADO 2105167360 | 80 | 15873 | 15873
Middletown 1101433160 | 18 | 18991 | 18991
OREGON TRAIL 11021584 | 244 | 9474.7531 | 12095
FORESTHILL 11022106 | 427 | 14747.4673 | 17179
SHADY GLEN 110248894 | 193 | 17658.7183 | 18808
SHADY GLEN 11022232 | 337 | 17518.2757 | 18920
BEAR VALLEY 21059570 | 40 | 2868 | 2868
OAKHURST 110310140 | 527 | 4052.59 | 4994
CURTIS 170356972 | 77 | 6627 | 6627
KONOCTI 11022293 | 64 | 12811 | 12811
APPLE HILL 210289934 | 68 | 18534 | 18534
GIRVAN 11029012 | 240 | 10891.1444 | 13112
BEAR VALLEY 210576694 | 32 | 5209 | 5209
ELK CREEK 11012032 | 44 | 12793.5833 | 12793.5833
DRUM 1101CB | 3 | 17367 | 17367
WILDWOOD 110198896 | 19 | 6326.6522 | 10171
KESWICK 110148480 | 134 | 12303 | 12303
KESWICK 11011590 | 51 | 14264 | 14264
MIWUK 170236888 | 4 | 7776 | 10167
COLUMBIA HILL 110190730 | 86 | 20283 | 20283
SHADY GLEN 11012768 | 172 | 10202.5692 | 12955
ALLEGHANY 1101VR816 | 287 | 13859.5945 | 20960
ANTLER 11011612 | 77 | 10749 | 10749
PLACERVILLE 111219712 | 470 | 12257.6086 | 15296
TEJON 11023751 | 45 | 11321.3932 | 11748
CURTIS 17039240 | 838 | 7905.3882 | 7935
PIT NO 5 1101CB | 5 | 9339 | 9339
SHADY GLEN 110132726 | 250 | 10446.0077 | 13018
ANTLER 1101CB | 33 | 9248 | 9248
PARADISE 110636042 | 277 | 22118.1816 | 22209
PARADISE 11061212 | 279 | 21845 | 21845
Paradise 1106CB | 59 | 20954 | 20954
PARADISE 1105CB | 66 | 22034 | 22034
PARADISE 1104409622 | 213 | 23698.2005 | 24268
Paradise 11042206 | 682 | 24828.1776 | 25087
PARADISE 1104920400 | 70 | 24647 | 24647
PARADISE 1103143744 | 28 | 23795.7115 | 24304
PARADISE 110453544 | 46 | 23551.7905 | 23919
PARADISE 110443008 | 206 | 24222.3146 | 24234
PARADISE 1105121988 | 131 | 24191 | 24191
PARADISE 1105829194 | 365 | 24181.011 | 24189
PARADISE 1105878870 | 113 | 23907.918 | 24252
PARADISE 11052214 | 382 | 23842 | 23842
PARADISE 110439216 | 214 | 23845.2979 | 23898
PARADISE 11042488 | 56 | 23895.3636 | 23939
JAMESON 1102865502 | 25 | 12758.68 | 14053
LAYTONVILLE 1101402 | 151 | 5710 | 5710
BIG BASIN 11015028 | 255 | 6180.2023 | 7902
DUNLAP 11027849F | 45 | 1846 | 1846
BEAR VALLEY 2105454432 | 127 | 5329.8788 | 6326
HIGHLANDS 11031282 | 164 | 18224.3684 | 18287
HIGHLANDS 1103568 | 294 | 12522 | 12522
FRUITLAND 114263170 | 121 | 5118.832 | 6621
UPPER LAKE 1101412 | 152 | 10335.2434 | 11293
PLACERVILLE 1109868678 | 502 | 17844 | 17844
WHITMORE 11011598 | 158 | 21095.1667 | 21097
WHITMORE 11011594 | 116 | 20859.3687 | 21656
GARBERVILLE 110237054 | 47 | 4255 | 4255
HIGHLANDS 1103482 | 123 | 22725.565 | 22750
OREGON TRAIL 11031500 | 610 | 12287.0216 | 12713
COLUMBIA HILL 1101764 | 252 | 23148.2727 | 23189
NARROWS 21011202 | 480 | 13523.6575 | 13771
CLARK ROAD 110292622 | 238 | 22644.075 | 24675
MORGAN HILL 2105XR176 | 559 | 2973.8445 | 3862
CURTIS 17058170 | 493 | 9818 | 9818
CABRILLO 1104Y24 | 69 | 0 | 0
PERRY 1101V74 | 231 | N/A | N/A
PALMER 1101M84 | 76 | 0 | 0
ROB ROY 210410298 | 217 | 4640.2928 | 7699
ELK CREEK 11012106 | 24 | 11646.7692 | 12622
WYANDOTTE 11031976 | 35 | 14287.5417 | 16265
OAKHURST 110110090 | 614 | 3740.2525 | 4154
WOODSIDE 11018972 | 69 | 12138.0435 | 12235
VOLTA 11011568 | 81 | 21352.5843 | 21720
DESCHUTES 11041370 | 398 | 11888.665 | 13956
GARBERVILLE 1101323694 | 6 | 5730 | 5730
SHINGLE SPRINGS 210911092 | 296 | 8154.0505 | 10546
LOS GATOS 1106LB44 | 292 | 8096.7387 | 8172
COARSEGOLD 21046210 | 26 | 1840 | 1840
SHINGLE SPRINGS 210851476 | 94 | 2601 | 2601
ELECTRA 110161816 | 367 | 12224.7225 | 13207
CALAVERAS CEMENT 110147968 | 74 | 10756.8732 | 10818
STILLWATER 110148950 | 231 | 11192.8471 | 14173
CALAVERAS CEMENT 11014786 | 154 | 10386.0461 | 11680
CLARK ROAD 11022070 | 6 | 26643.9747 | 29632
ANDERSON 11031600 | 111 | 13455.5574 | 15604
LINCOLN 1104275986 | N/A | 4010 | 4010
MIDDLETOWN 1101439572 | 61 | 13042 | 13042
PLACERVILLE 21067522 | 1021 | 18631.2678 | 20257
RED BLUFF 11011556 | 460 | 13003.7634 | 14116
BRIDGEVILLE 110255612 | 47 | 10188 | 10188
NARROWS 2101CB | 38 | 12655.8125 | 13337
BROWNS VALLEY 110193870 | 386 | 8818.6944 | 10723
BANGOR 110182350 | 244 | 16976 | 16976
CHALLENGE 1101CB | 228 | 14705.4105 | 15962
PUEBLO 1105637242 | 145 | 19887 | 19887
PUEBLO 210378504 | 266 | 13536 | 13536
MOLINO 1102178 | 340 | 6151.0149 | 6729
NORTH BRANCH 1101752104 | 363 | 2455 | 2455
DUNLAP 11037220 | 144 | 2104 | 2104
CUYAMA 21013542 | 101 | 0 | 0
DIAMOND SPRINGS 1107CB | 546 | 7303.4385 | 7314
WEST POINT 1102CB | 436 | 12133.9105 | 14884
DIAMOND SPRINGS 11057722 | 718 | 9891.236 | 10790
HIGHLANDS 110275140 | 1727 | 9049.584 | 9532
WEST POINT 110293116 | 513 | 19291.2562 | 19735
KONOCTI 1102354890 | 511 | 11107 | 11107
BIG BEND 1101641808 | 134 | 32738.9862 | 33361
FRENCH GULCH 11022902 | 6 | 6440.1667 | 9416
WILLITS 1104341020 | N/A | N/A | N/A
WILLITS 1103538 | 42 | 5681 | 5681
WHITMORE 1101 | N/A | N/A | N/A
BROWNS VALLEY 11011268 | 119 | 13108 | 13108
MIDDLETOWN 1102878 | 63 | 14922.6349 | 16016
MILPITAS 1109903328 | 202 | 6208.995 | 8090
PHILO 1102920 | 267 | 6284 | 6284
GIRVAN 11019732 | 481 | 12308.7757 | 15415
ANNAPOLIS 1101 | N/A | N/A | N/A
HOOPA 1101 | N/A | N/A | N/A
UPPER LAKE 1101 | N/A | N/A | N/A
BIG BASIN 110212124 | 268 | 5874.4437 | 8018
VALLEY VIEW 1105305072 | 295 | 2399.8712 | 2407
PEORIA 1701169700 | 71 | 6794 | 6794
RINCON 1103568 | 102 | 19098.3519 | 20366
VALLEY VIEW 1106 | N/A | N/A | N/A
CURTIS 170234426 | 530 | 6972 | 6972
FRANKLIN 1104P146 | 30 | 2512 | 2512
APPLE HILL 21028372 | 694 | 19809 | 19809
MARIPOSA 210237282 | 593 | N/A | N/A
LOS GATOS 1107CB | 1041 | 5427 | 5427
PIERCY 2110XR258 | 730 | 3515.4779 | 5180
SANTA YNEZ 1104Y66 | 141 | 0 | 0
ALLEGHANY 1101CB | 74 | 20231 | 20231
JESSUP 110141356 | 335 | 16658.8813 | 18276
POSO MOUNTAIN 210448268 | 5 | 4447 | 4447
DESCHUTES 11011580 | 334 | 21293.4993 | 21507
CORNING 110164090 | 225 | 15542.0567 | 18526
RISING RIVER 11011530 | 157 | 2185 | 2185
RACETRACK 170455798 | 348 | 10666.9324 | 10685
CURTIS 170463502 | 316 | 8961.2177 | 9342
MIRABEL 1102334 | 73 | 8148 | 8148
PIT NO 7 1101CB | 2 | 22860 | 22860
DUNLAP 11027050 | 290 | 1822.4932 | 2074
STANISLAUS 1701CB | 359 | 9433.5229 | 12740

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program tracked in PG&E's Maintenance Activity Type (MAT) 08W. May include underground, overhead hardening and line removal projects.
Community Rebuild | Specific Fire Rebuild projects outside a High Fire Threat District (HFTD) currently associated with the Dixie and Camp fires in the county of Butte (towns of Paradise, Magalia) and Plumas (city of Greenville) .
Fire Rebuild | System Hardening work as a result of fires in an HFTD.
Other | Non-rebuild, base system hardening or targeted undergrounding projects in HFTD that are new business, Work Requested by Others (WRO), capacity upgrades, Rule 20A, etc.
MAT Code
MAT Code | Description
08W | System Hardening Wildfire Resiliency Projects
10H | Work Requested by Others - Rule 20B
10I | Work Requested by Others - Rule 20C
10J | Work Requested by Others - Overhead Relocation
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
3UG | Targeted Undergrounding
49M | Preinstalled Interconnection Hubs / Microgrids: non-gen
95F | Electric Distribution Major Emergency