## Q1 a-h
PG&E 2023 Completed Undergrounding Work
Data as of Feb 22, 2024
[9 empty] | 21.5159 | 386.6252 | 1.0843 | 409.2254 | 9.9905 | 9.1621 | 0 | 19.1527 | 11.3557 | 364.4002 | 1.0843 | 376.8402 | 0.1697 | 14.7888 | 0 | 14.9585 | 1182.9446
Order | Circuit ID | Circuit Name | Circuit Protection Zone (CPZ) | County | Construction Start Date | Construction End Date | MAT | Category | Total Planned OH Miles | Total Planned UG Miles | Total Planned Removal Miles | Total Planned Circuit Miles | OH - Pre-2023 Complete | UG - Pre-2023 Complete | Removal - Pre-2023 Complete | Pre-2023 Total Complete Miles | OH - 2023 Complete | UG - 2023 Complete | Removal - 2023 Complete | 2023 Total Complete Miles | OH - Post 2023 Forecast | UG - Post 2023 Forecast | Removal - Post 2023 Forecast | Post 2023 Total Forecat Miles | Total Estimated Actual Cost
35056733 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | EL DORADO | 2022-09-06 | 2023-07-18 | 08W | Base SH | 1.7455 | 0.57348 | 0 | 2.3189 | 1.6231 | 0 | 0 | 1.6231 | 0.12235 | 0.57348 | 0 | 0.69583 | 0 | 0 | 0 | 0 | 5.179
35057010 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | EL DORADO | 2022-04-26 | 2023-07-21 | 08W | Base SH | 0.62519 | 2.2348 | 0 | 2.86 | 0 | 0 | 0 | 0 | 0.62519 | 2.2348 | 0 | 2.86 | 0 | 0 | 0 | 0 | 8.8479
35062376 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | EL DORADO | 2022-08-10 | 2023-08-09 | 08W | Base SH | 0.19413 | 5.0311 | 0 | 5.2252 | 0 | 0.97178 | 0 | 0.97178 | 0.19413 | 4.0593 | 0 | 4.2534 | 0 | 0 | 0 | 0 | 18.6939
35094513 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | CALAVERAS | 2022-03-14 | 2022-12-29 | 08W | Base SH | 1.6826 | 0.053977 | 0.048485 | 1.785 | 1.483 | 0.053977 | 0 | 1.5369 | 0.19962 | 0 | 0.048485 | 0.24811 | 0 | 0 | 0 | 0 | 4.9134
35109541 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | EL DORADO | 2022-10-17 | 2023-07-25 | 08W | Base SH | 2.2746 | 0.34223 | 0 | 2.6169 | 1.5992 | 0.0034091 | 0 | 1.6027 | 0.67538 | 0.33883 | 0 | 1.0142 | 0 | 0 | 0 | 0 | 6.8842
35109546 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | EL DORADO | 2022-08-29 | 2022-12-18 | 08W | Base SH | 2.3513 | 0.44621 | 0 | 2.7975 | 2.2216 | 0.44621 | 0 | 2.6678 | 0.12973 | 0 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 6.3917
35114040 | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | AMADOR | 2020-07-21 | 2023-06-07 | 08W | Base SH | 1.3951 | 0.098106 | 0 | 1.4932 | 1.2725 | 0.04072 | 0 | 1.3133 | 0.12254 | 0.057386 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 3.4803
35145001 | 12022215 | CLAYTON 2215 | CLAYTON 2215184604 | CONTRA COSTA | 2022-05-06 | 2023-10-18 | 08W | Base SH | 0.040341 | 1.875 | 0 | 1.9153 | 0 | 0 | 0 | 0 | 0.040341 | 1.875 | 0 | 1.9153 | 0 | 0 | 0 | 0 | 5.6489
35148392 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021850 | CALAVERAS | 2020-07-20 | 2023-06-14 | 49M | Other | 0 | 0.34735 | 0 | 0.34735 | 0 | 0 | 0 | 0 | 0 | 0.34735 | 0 | 0.34735 | 0 | 0 | 0 | 0 | Not Available
35192280 | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | 2023-03-20 | 2023-09-15 | 08W | Base SH | 0 | 1.6784 | 0 | 1.6784 | 0 | 0 | 0 | 0 | 0 | 1.6784 | 0 | 1.6784 | 0 | 0 | 0 | 0 | 3.8714
35219093 | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | CONTRA COSTA | 2023-06-12 | 2023-11-06 | 08W | Base SH | 0 | 1.5739 | 0 | 1.5739 | 0 | 0 | 0 | 0 | 0 | 1.5739 | 0 | 1.5739 | 0 | 0 | 0 | 0 | 6.942
35219096 | 14452104 | KIRKER 2104 | KIRKER 2104442850 | CONTRA COSTA | 2022-06-13 | 2023-06-28 | 08W | Base SH | 0.11288 | 1.7894 | 0 | 1.9023 | 0.11288 | 1.761 | 0 | 1.8739 | 0 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | 0 | 5.0817
35219588 | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | MARIPOSA | 2022-05-31 | 2022-12-23 | 08W | Base SH | 0.88182 | 0.040909 | 0 | 0.92273 | 0.87045 | 0.040909 | 0 | 0.91136 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | 0 | 0 | 1.978
35220895 | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | LAKE | 2023-08-07 | 2023-11-03 | 08W | Base SH | 0 | 2.0684 | 0 | 2.0684 | 0 | 0 | 0 | 0 | 0 | 2.0684 | 0 | 2.0684 | 0 | 0 | 0 | 0 | 9.3881
35223030 | 103191101 | BANGOR 1101 | BANGOR 1101CB | BUTTE | 2022-08-01 | 2022-12-21 | 08W | Base SH | 0.28352 | 1.3922 | 0 | 1.6758 | 0.28352 | 1.2625 | 0 | 1.546 | 0 | 0.12973 | 0 | 0.12973 | 0 | 0 | 0 | 0 | 4.8702
35223032 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | EL DORADO | 2023-06-05 | 2023-11-14 | 08W | Base SH | 0 | 0.9358 | 0 | 0.9358 | 0 | 0 | 0 | 0 | 0 | 0.9358 | 0 | 0.9358 | 0 | 0 | 0 | 0 | 5.5403
35225593 | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | CONTRA COSTA | 2021-11-01 | 2023-09-07 | 08W | Base SH | 1.1027 | 0.092992 | 0 | 1.1956 | 0 | 0 | 0 | 0 | 1.1027 | 0.092992 | 0 | 1.1956 | 0 | 0 | 0 | 0 | 1.3938
35226799 | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | SHASTA | 2023-07-26 | 2023-08-18 | 08W | Base SH | 0 | 0.19792 | 0 | 0.19792 | 0 | 0 | 0 | 0 | 0 | 0.19792 | 0 | 0.19792 | 0 | 0 | 0 | 0 | 0.52491
35226878 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2023-04-03 | 2023-08-01 | 08W | Base SH | 0 | 0.70511 | 0 | 0.70511 | 0 | 0 | 0 | 0 | 0 | 0.70511 | 0 | 0.70511 | 0 | 0 | 0 | 0 | 3.9738
35227001 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2022-11-07 | 2023-07-21 | 08W | Base SH | 0 | 0.69924 | 0 | 0.69924 | 0 | 0 | 0 | 0 | 0 | 0.69924 | 0 | 0.69924 | 0 | 0 | 0 | 0 | 5.0487
35227002 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2022-10-24 | 2023-10-18 | 08W | Base SH | 0 | 0.43674 | 0 | 0.43674 | 0 | 0 | 0 | 0 | 0 | 0.43674 | 0 | 0.43674 | 0 | 0 | 0 | 0 | 2.9736
35227025 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2022-10-03 | 2023-10-18 | 08W | Base SH | 0 | 0.69261 | 0 | 0.69261 | 0 | 0 | 0 | 0 | 0 | 0.69261 | 0 | 0.69261 | 0 | 0 | 0 | 0 | 3.9616
35227030 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | LAKE | 2022-08-15 | 2023-08-24 | 08W | Base SH | 0 | 1.372 | 0 | 1.372 | 0 | 0 | 0 | 0 | 0 | 1.372 | 0 | 1.372 | 0 | 0 | 0 | 0 | 3.4313
35227031 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | LAKE | 2023-01-30 | 2023-08-29 | 08W | Base SH | 0.13958 | 1.4125 | 0 | 1.5521 | 0 | 0 | 0 | 0 | 0.13958 | 1.4125 | 0 | 1.5521 | 0 | 0 | 0 | 0 | 5.8805
35227652 | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SOLANO | 2022-11-14 | 2023-04-19 | 08W | Base SH | 0.0075758 | 0.45871 | 0 | 0.46629 | 0 | 0 | 0 | 0 | 0.0075758 | 0.45871 | 0 | 0.46629 | 0 | 0 | 0 | 0 | 1.4615
35227864 | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | LAKE | 2022-09-19 | 2023-05-23 | 08W | Base SH | 0 | 1.4473 | 0 | 1.4473 | 0 | 0.34242 | 0 | 0.34242 | 0 | 1.1049 | 0 | 1.1049 | 0 | 0 | 0 | 0 | 3.7219
35228186 | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | LAKE | 2023-07-19 | 2023-10-31 | 08W | Base SH | 0 | 0.95852 | 0 | 0.95852 | 0 | 0 | 0 | 0 | 0 | 0.95852 | 0 | 0.95852 | 0 | 0 | 0 | 0 | 2.9623
35233995 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | EL DORADO | 2022-11-18 | 2023-05-08 | 08W | Base SH | 0 | 0.66042 | 0 | 0.66042 | 0 | 0 | 0 | 0 | 0 | 0.66042 | 0 | 0.66042 | 0 | 0 | 0 | 0 | 2.5654
35233996 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | EL DORADO | 2022-11-15 | 2023-08-10 | 08W | Base SH | 0 | 0.64129 | 0 | 0.64129 | 0 | 0 | 0 | 0 | 0 | 0.64129 | 0 | 0.64129 | 0 | 0 | 0 | 0 | 3.6505
35234399 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | SHASTA | 2022-10-31 | 2023-04-15 | 08W | Base SH | 0.027841 | 0.6053 | 0 | 0.63314 | 0 | 0 | 0 | 0 | 0.027841 | 0.6053 | 0 | 0.63314 | 0 | 0 | 0 | 0 | 2.6544
35234526 | 163011101 | MARTELL 1101 | MARTELL 1101CB | AMADOR | 2022-11-08 | 2023-04-27 | 08W | Base SH | 0 | 0.87614 | 0 | 0.87614 | 0 | 0 | 0 | 0 | 0 | 0.87614 | 0 | 0.87614 | 0 | 0 | 0 | 0 | 4.142
35234758 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2023-08-14 | 2023-10-13 | 08W | Base SH | 0 | 0.80208 | 0 | 0.80208 | 0 | 0 | 0 | 0 | 0 | 0.80208 | 0 | 0.80208 | 0 | 0 | 0 | 0 | 2.7075
35234862 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | LAKE | 2023-05-01 | 2023-06-28 | 08W | Base SH | 0.0037879 | 0.12311 | 0 | 0.12689 | 0 | 0 | 0 | 0 | 0.0037879 | 0.12311 | 0 | 0.12689 | 0 | 0 | 0 | 0 | 0.50803
35237937 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210311046 | SANTA CRUZ | 2023-02-01 | 2024-02-21 | 2BP | Other | 0.055114 | 0.015341 | 0 | 0.070455 | 0 | 0 | 0 | 0 | 0.055114 | 0.015341 | 0 | 0.070455 | 0 | 0 | 0 | 0 | Not Available
35240166 | 102541101 | VOLTA 1101 | VOLTA 1101CB | SHASTA | 2022-03-28 | 2023-01-27 | 08W | Base SH | 0.46326 | 0.015341 | 0 | 0.4786 | 0.46326 | 0 | 0 | 0.46326 | 0 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0 | 0 | 2.4705
35254259 | 102541101 | VOLTA 1101 | VOLTA 1101CB | SHASTA | 2023-02-06 | 2023-04-14 | 08W | Base SH | 0.24848 | 0.25455 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 0.24848 | 0.25455 | 0 | 0.50303 | 0 | 0 | 0 | 0 | 1.0524
35254650 | 102541101 | VOLTA 1101 | VOLTA 110153118 | TEHAMA | 2022-10-10 | 2022-12-16 | 08W | Base SH | 0.0075758 | 0.30436 | 0 | 0.31193 | 0 | 0.30436 | 0 | 0.30436 | 0.0075758 | 0 | 0 | 0.0075758 | 0 | 0 | 0 | 0 | 1.1995
35254945 | 102541101 | VOLTA 1101 | VOLTA 11011596 | TEHAMA | 2023-05-15 | 2023-06-30 | 08W | Base SH | 0.0028409 | 0.49148 | 0 | 0.49432 | 0 | 0 | 0 | 0 | 0.0028409 | 0.49148 | 0 | 0.49432 | 0 | 0 | 0 | 0 | 1.5067
35254947 | 102541101 | VOLTA 1101 | VOLTA 11011596 | TEHAMA | 2023-04-17 | 2023-06-02 | 08W | Base SH | 0.013447 | 0.25038 | 0 | 0.26383 | 0 | 0 | 0 | 0 | 0.013447 | 0.25038 | 0 | 0.26383 | 0 | 0 | 0 | 0 | 1.2282
35256083 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | 2023-01-30 | 2023-09-21 | 08W | Base SH | 0.0089015 | 1.8593 | 0 | 1.8682 | 0 | 0 | 0 | 0 | 0.0089015 | 1.8593 | 0 | 1.8682 | 0 | 0 | 0 | 0 | 5.9755
35259512 | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | SHASTA | 2023-01-16 | 2023-06-28 | 08W | Base SH | 0 | 0.10739 | 0 | 0.10739 | 0 | 0 | 0 | 0 | 0 | 0.10739 | 0 | 0.10739 | 0 | 0 | 0 | 0 | 0.85013
35274593 | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | MARIPOSA | 2023-07-24 | 2023-11-30 | 08W | Base SH | 0 | 2.9869 | 0 | 2.9869 | 0 | 0 | 0 | 0 | 0 | 2.9869 | 0 | 2.9869 | 0 | 0 | 0 | 0 | 6.5661
35277924 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | FRESNO | 2023-05-08 | 2023-06-23 | 08W | Base SH | 0 | 0.12633 | 0 | 0.12633 | 0 | 0 | 0 | 0 | 0 | 0.12633 | 0 | 0.12633 | 0 | 0 | 0 | 0 | 0.41023
35277925 | 254151101 | AUBERRY 1101 | AUBERRY 1101CB | FRESNO | 2023-06-09 | 2023-08-09 | 08W | Base SH | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0.027652 | 0.14148 | 0.057008 | 0.22614 | 0 | 0 | 0 | 0 | 0.59313
35277938 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | FRESNO | 2023-05-01 | 2023-10-20 | 08W | Base SH | 0.026705 | 0.42822 | 0 | 0.45492 | 0 | 0 | 0 | 0 | 0.026705 | 0.42822 | 0 | 0.45492 | 0 | 0 | 0 | 0 | 1.4866
35278899 | 162821701 | STANISLAUS 1701 | STANISLAUS 1701CB | CALAVERAS | 2023-04-03 | 2024-04-08 | 08W | Base SH | 0 | 1.5324 | 0 | 1.5324 | 0 | 0 | 0 | 0 | 0 | 1.5324 | 0 | 1.5324 | 0 | 0 | 0 | 0 | 5.3693
35279120 | 162821701 | STANISLAUS 1701 | STANISLAUS 1701CB | CALAVERAS | 2023-08-29 | 2024-02-16 | 08W | Base SH | 0 | 0.98769 | 0 | 0.98769 | 0 | 0 | 0 | 0 | 0 | 0.98769 | 0 | 0.98769 | 0 | 0 | 0 | 0 | 4.4389
35283343 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | 2023-07-24 | 2023-10-27 | 08W | Base SH | 0.18731 | 0.55909 | 0 | 0.7464 | 0 | 0 | 0 | 0 | 0.18731 | 0.55909 | 0 | 0.7464 | 0 | 0 | 0 | 0 | 1.6655
35284364 | 162821702 | STANISLAUS 1702 | STANISLAUS 1702CB | CALAVERAS | 2023-07-10 | 2023-10-16 | 08W | Base SH | 0.0047348 | 0.80985 | 0 | 0.81458 | 0 | 0 | 0 | 0 | 0.0047348 | 0.80985 | 0 | 0.81458 | 0 | 0 | 0 | 0 | 0.68436
35285064 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110537476 | MENDOCINO | 2023-07-10 | 2023-10-20 | 08W | Base SH | 0.021402 | 0.63125 | 0 | 0.65265 | 0 | 0 | 0 | 0 | 0.021402 | 0.63125 | 0 | 0.65265 | 0 | 0 | 0 | 0 | 2.3304
35290808 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | MENDOCINO | 2023-06-05 | 2023-09-01 | 08W | Base SH | 0 | 0.20587 | 0 | 0.20587 | 0 | 0 | 0 | 0 | 0 | 0.20587 | 0 | 0.20587 | 0 | 0 | 0 | 0 | 1.4195
35293508 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | EL DORADO | 2023-05-01 | 2023-07-28 | 08W | Base SH | 0 | 0.46212 | 0 | 0.46212 | 0 | 0 | 0 | 0 | 0 | 0.46212 | 0 | 0.46212 | 0 | 0 | 0 | 0 | 1.6009
35293662 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | 2023-03-16 | 2023-08-11 | 08W | Base SH | 0.0060606 | 0.58902 | 0 | 0.59508 | 0 | 0 | 0 | 0 | 0.0060606 | 0.58902 | 0 | 0.59508 | 0 | 0 | 0 | 0 | 1.6975
35293663 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | 2023-05-15 | 2023-10-20 | 08W | Base SH | 0.053788 | 1.0653 | 0 | 1.1191 | 0 | 0 | 0 | 0 | 0.053788 | 1.0653 | 0 | 1.1191 | 0 | 0 | 0 | 0 | 3.73
35293665 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | 2023-02-13 | 2023-04-26 | 08W | Base SH | 0 | 0.3017 | 0 | 0.3017 | 0 | 0 | 0 | 0 | 0 | 0.3017 | 0 | 0.3017 | 0 | 0 | 0 | 0 | 0.97159
35293670 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | EL DORADO | 2023-04-26 | 2023-07-18 | 08W | Base SH | 0 | 0.65417 | 0 | 0.65417 | 0 | 0 | 0 | 0 | 0 | 0.65417 | 0 | 0.65417 | 0 | 0 | 0 | 0 | 0.91345
35293846 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | MENDOCINO | 2023-06-26 | 2023-08-16 | 08W | Base SH | 0 | 0.70133 | 0 | 0.70133 | 0 | 0 | 0 | 0 | 0 | 0.70133 | 0 | 0.70133 | 0 | 0 | 0 | 0 | 1.6375
35298571 | 103261103 | ANDERSON 1103 | ANDERSON 11031600 | SHASTA | 2023-07-06 | 2023-07-21 | 08W | Base SH | 0 | 0.29678 | 0 | 0.29678 | 0 | 0 | 0 | 0 | 0 | 0.29678 | 0 | 0.29678 | 0 | 0 | 0 | 0 | 0.61248
35299631 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110281296 | BUTTE | 2023-05-01 | 2024-02-16 | 08W | Base SH | 0 | 3.5237 | 0 | 3.5237 | 0 | 0 | 0 | 0 | 0 | 3.5237 | 0 | 3.5237 | 0 | 0 | 0 | 0 | 8.5067
35299634 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022070 | BUTTE | 2023-07-31 | 2024-03-30 | 08W | Base SH | 0 | 2.322 | 0 | 2.322 | 0 | 0 | 0 | 0 | 0 | 2.322 | 0 | 2.322 | 0 | 0 | 0 | 0 | 7.1414
35300933 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | EL DORADO | 2023-03-06 | 2023-06-07 | 08W | Base SH | 0.015152 | 0.49432 | 0 | 0.50947 | 0 | 0 | 0 | 0 | 0.015152 | 0.49432 | 0 | 0.50947 | 0 | 0 | 0 | 0 | 1.909
35301112 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | EL DORADO | 2023-05-01 | 2023-08-18 | 08W | Base SH | 0.067235 | 0.49905 | 0 | 0.56629 | 0 | 0 | 0 | 0 | 0.067235 | 0.49905 | 0 | 0.56629 | 0 | 0 | 0 | 0 | 2.1445
35311895 | 103261103 | ANDERSON 1103 | ANDERSON 1103226050 | SHASTA | 2023-07-17 | 2023-11-10 | 08W | Base SH | 0 | 2.4659 | 0 | 2.4659 | 0 | 0 | 0 | 0 | 0 | 2.4659 | 0 | 2.4659 | 0 | 0 | 0 | 0 | 5.5073
35311897 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-10-23 | 2024-04-19 | 08W | Base SH | 0 | 4.1133 | 0 | 4.1133 | 0 | 0 | 0 | 0 | 0 | 4.1133 | 0 | 4.1133 | 0 | 0 | 0 | 0 | 8.1381
35311898 | 103331102 | CORNING 1102 | CORNING 1102915324 | TEHAMA | 2023-09-25 | 2024-03-22 | 08W | Base SH | 0 | 2.0881 | 0 | 2.0881 | 0 | 0 | 0 | 0 | 0 | 2.0881 | 0 | 2.0881 | 0 | 0 | 0 | 0 | 5.4291
35311899 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 1102544790 | SHASTA | 2023-06-22 | 2024-01-31 | 08W | Base SH | 0 | 3.339 | 0 | 3.339 | 0 | 0 | 0 | 0 | 0 | 3.339 | 0 | 3.339 | 0 | 0 | 0 | 0 | 7.1569
35312541 | 163351701 | CURTIS 1701 | CURTIS 1701CB | TUOLUMNE | 2023-06-16 | 2023-09-11 | 08W | Base SH | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0 | 0 | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0 | 0 | 1.7448
35312544 | 102781101 | ELK CREEK 1101 | ELK CREEK 110193504 | GLENN | 2023-06-12 | 2023-08-26 | 08W | Base SH | 0.077841 | 0.51913 | 0 | 0.59697 | 0 | 0 | 0 | 0 | 0.077841 | 0.51913 | 0 | 0.59697 | 0 | 0 | 0 | 0 | 1.4873
35312549 | 103441103 | JESSUP 1103 | JESSUP 1103348657 | SHASTA | 2023-08-14 | 2023-10-11 | 08W | Base SH | 0 | 0.94489 | 0 | 0.94489 | 0 | 0 | 0 | 0 | 0 | 0.94489 | 0 | 0.94489 | 0 | 0 | 0 | 0 | 2.6878
35312552 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | 2023-04-24 | 2023-07-14 | 08W | Base SH | 0 | 0.73409 | 0 | 0.73409 | 0 | 0 | 0 | 0 | 0 | 0.73409 | 0 | 0.73409 | 0 | 0 | 0 | 0 | 1.647
35316278 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-07-24 | 2023-10-06 | 08W | Base SH | 0 | 2.5396 | 0 | 2.5396 | 0 | 0 | 0 | 0 | 0 | 2.5396 | 0 | 2.5396 | 0 | 0 | 0 | 0 | 5.3598
35316567 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-04-10 | 2023-11-03 | 08W | Base SH | 0.0081439 | 2.6206 | 0.062879 | 2.6917 | 0 | 0 | 0 | 0 | 0.0081439 | 2.6206 | 0.062879 | 2.6917 | 0 | 0 | 0 | 0 | 4.3343
35316569 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-05-19 | 2023-08-18 | 08W | Base SH | 0 | 4.4525 | 0 | 4.4525 | 0 | 0 | 0 | 0 | 0 | 4.4525 | 0 | 4.4525 | 0 | 0 | 0 | 0 | 7.7152
35317398 | 43191101 | REDBUD 1101 | REDBUD 1101754544 | LAKE | 2023-06-26 | 2023-11-03 | 08W | Base SH | 0 | 1.8322 | 0 | 1.8322 | 0 | 0 | 0 | 0 | 0 | 1.8322 | 0 | 1.8322 | 0 | 0 | 0 | 0 | 3.5779
35317887 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-05-30 | 2023-07-27 | 08W | Base SH | 0 | 0.8053 | 0 | 0.8053 | 0 | 0 | 0 | 0 | 0 | 0.8053 | 0 | 0.8053 | 0 | 0 | 0 | 0 | 2.6067
35320312 | 153701104 | LINCOLN 1104 | LINCOLN 11042070 | PLACER | 2023-07-31 | 2023-12-13 | 08W | Base SH | 0 | 2.0256 | 0 | 2.0256 | 0 | 0 | 0 | 0 | 0 | 2.0256 | 0 | 2.0256 | 0 | 0 | 0 | 0 | 4.9706
35320336 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-06-12 | 2023-09-29 | 08W | Base SH | 0 | 1.4021 | 0 | 1.4021 | 0 | 0 | 0 | 0 | 0 | 1.4021 | 0 | 1.4021 | 0 | 0 | 0 | 0 | 4.4556
35320339 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-07-26 | 2024-03-01 | 08W | Base SH | 0 | 0.77462 | 0 | 0.77462 | 0 | 0 | 0 | 0 | 0 | 0.77462 | 0 | 0.77462 | 0 | 0 | 0 | 0 | 2.455
35320447 | 152571101 | HORSESHOE 1101 | HORSESHOE 110150140 | PLACER | 2023-05-15 | 2023-09-20 | 08W | Base SH | 0.97027 | 0.87633 | 0 | 1.8466 | 0 | 0 | 0 | 0 | 0.97027 | 0.87633 | 0 | 1.8466 | 0 | 0 | 0 | 0 | 3.6314
35320449 | 153701104 | LINCOLN 1104 | LINCOLN 1104275986 | PLACER | 2023-04-25 | 2023-10-13 | 08W | Base SH | 0 | 2.7277 | 0 | 2.7277 | 0 | 0 | 0 | 0 | 0 | 2.7277 | 0 | 2.7277 | 0 | 0 | 0 | 0 | 5.7738
35320460 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-08-07 | 2023-11-06 | 08W | Base SH | 0 | 1.5277 | 0 | 1.5277 | 0 | 0 | 0 | 0 | 0 | 1.5277 | 0 | 1.5277 | 0 | 0 | 0 | 0 | 3.6525
35320462 | 63801105 | JAMESON 1105 | JAMESON 1105371694 | SOLANO | 2023-09-11 | 2023-10-07 | 08W | Base SH | 0 | 0.28826 | 0 | 0.28826 | 0 | 0 | 0 | 0 | 0 | 0.28826 | 0 | 0.28826 | 0 | 0 | 0 | 0 | 0.83108
35320463 | 63801105 | JAMESON 1105 | JAMESON 1105913400 | SOLANO | 2023-07-10 | 2023-11-15 | 08W | Base SH | 0 | 1.5386 | 0 | 1.5386 | 0 | 0 | 0 | 0 | 0 | 1.5386 | 0 | 1.5386 | 0 | 0 | 0 | 0 | 4.8874
35320464 | 103461101 | PANORAMA 1101 | PANORAMA 1101CB | SHASTA | 2023-07-11 | 2023-09-11 | 08W | Base SH | 0 | 0.22292 | 0 | 0.22292 | 0 | 0 | 0 | 0 | 0 | 0.22292 | 0 | 0.22292 | 0 | 0 | 0 | 0 | 1.0451
35326790 | 152531101 | FLINT 1101 | FLINT 1101958726 | PLACER | 2023-11-20 | 2023-12-11 | 08W | Base SH | 0 | 0.1322 | 0 | 0.1322 | 0 | 0 | 0 | 0 | 0 | 0.1322 | 0 | 0.1322 | 0 | 0 | 0 | 0 | 0.36397
35329008 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 1102CB | BUTTE | 2023-04-10 | 2024-01-11 | 08W | Base SH | 0 | 0.39602 | 0 | 0.39602 | 0 | 0 | 0 | 0 | 0 | 0.39602 | 0 | 0.39602 | 0 | 0 | 0 | 0 | 1.1817
35329009 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110281296 | BUTTE | 2023-04-05 | 2024-02-29 | 08W | Base SH | 0 | 0.70795 | 0.023674 | 0.73163 | 0 | 0 | 0 | 0 | 0 | 0.70795 | 0.023674 | 0.73163 | 0 | 0 | 0 | 0 | 4.0437
35329010 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110281296 | BUTTE | 2023-05-25 | 2024-03-30 | 08W | Base SH | 0 | 2.336 | 0 | 2.336 | 0 | 0 | 0 | 0 | 0 | 2.336 | 0 | 2.336 | 0 | 0 | 0 | 0 | 8.1855
35329011 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110281296 | BUTTE | 2023-05-22 | 2024-01-18 | 08W | Base SH | 0 | 1.5634 | 0 | 1.5634 | 0 | 0 | 0 | 0 | 0 | 1.5634 | 0 | 1.5634 | 0 | 0 | 0 | 0 | 3.3058
35329014 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022070 | BUTTE | 2023-09-18 | 2024-03-30 | 08W | Base SH | 0 | 2.7237 | 0 | 2.7237 | 0 | 0 | 0 | 0 | 0 | 2.7237 | 0 | 2.7237 | 0 | 0 | 0 | 0 | 6.7876
35329474 | 43191101 | REDBUD 1101 | REDBUD 1101754544 | LAKE | 2023-06-05 | 2023-08-10 | 08W | Base SH | 1.332 | 0.1375 | 0 | 1.4695 | 0 | 0 | 0 | 0 | 1.332 | 0.1375 | 0 | 1.4695 | 0 | 0 | 0 | 0 | 1.4375
35330244 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | 2023-04-24 | 2023-08-21 | 08W | Base SH | 0 | 0.46723 | 0 | 0.46723 | 0 | 0 | 0 | 0 | 0 | 0.46723 | 0 | 0.46723 | 0 | 0 | 0 | 0 | 1.6964
35330245 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | 2023-03-27 | 2023-07-10 | 08W | Base SH | 0 | 0.077273 | 0 | 0.077273 | 0 | 0 | 0 | 0 | 0 | 0.077273 | 0 | 0.077273 | 0 | 0 | 0 | 0 | 0.65333
35330246 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | 2023-04-19 | 2024-02-28 | 08W | Base SH | 0 | 0.78504 | 0 | 0.78504 | 0 | 0 | 0 | 0 | 0 | 0.78504 | 0 | 0.78504 | 0 | 0 | 0 | 0 | 1.4805
35330247 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | LAKE | 2023-05-08 | 2023-10-31 | 08W | Base SH | 0 | 0.82405 | 0 | 0.82405 | 0 | 0 | 0 | 0 | 0 | 0.82405 | 0 | 0.82405 | 0 | 0 | 0 | 0 | 1.5347
35330812 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-07-19 | 2023-11-18 | 08W | Base SH | 0 | 2.3237 | 0 | 2.3237 | 0 | 0 | 0 | 0 | 0 | 2.3237 | 0 | 2.3237 | 0 | 0 | 0 | 0 | 4.5312
35330815 | 103261103 | ANDERSON 1103 | ANDERSON 1103226050 | SHASTA | 2023-07-06 | 2023-08-25 | 08W | Base SH | 0 | 0.46913 | 0 | 0.46913 | 0 | 0 | 0 | 0 | 0 | 0.46913 | 0 | 0.46913 | 0 | 0 | 0 | 0 | 1.9398
35331305 | 103261103 | ANDERSON 1103 | ANDERSON 11031600 | SHASTA | 2023-08-10 | 2023-11-17 | 08W | Base SH | 0 | 0.50417 | 0 | 0.50417 | 0 | 0 | 0 | 0 | 0 | 0.50417 | 0 | 0.50417 | 0 | 0 | 0 | 0 | 1.489
35332214 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-07-13 | 2024-03-22 | 08W | Base SH | 0 | 4.307 | 0 | 4.307 | 0 | 0 | 0 | 0 | 0 | 4.307 | 0 | 4.307 | 0 | 0 | 0 | 0 | 8.0586
35332215 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-05-02 | 2023-08-04 | 08W | Base SH | 0 | 2.1809 | 0 | 2.1809 | 0 | 0 | 0 | 0 | 0 | 2.1809 | 0 | 2.1809 | 0 | 0 | 0 | 0 | 3.5356
35332216 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-08-22 | 2023-10-27 | 08W | Base SH | 0 | 1.325 | 0 | 1.325 | 0 | 0 | 0 | 0 | 0 | 1.325 | 0 | 1.325 | 0 | 0 | 0 | 0 | 2.3316
35332217 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-09-13 | 2024-02-23 | 08W | Base SH | 0 | 2.6513 | 0 | 2.6513 | 0 | 0 | 0 | 0 | 0 | 2.6513 | 0 | 2.6513 | 0 | 0 | 0 | 0 | 5.4214
35332218 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 1102544790 | SHASTA | 2023-08-10 | 2024-02-02 | 08W | Base SH | 0 | 3.2642 | 0 | 3.2642 | 0 | 0 | 0 | 0 | 0 | 3.2642 | 0 | 3.2642 | 0 | 0 | 0 | 0 | 6.0196
35332362 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-09-26 | 2024-04-30 | 08W | Base SH | 0 | 3.0616 | 0 | 3.0616 | 0 | 0 | 0 | 0 | 0 | 3.0616 | 0 | 3.0616 | 0 | 0 | 0 | 0 | 5.8844
35332363 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-06-12 | 2023-08-11 | 08W | Base SH | 0 | 1.2686 | 0 | 1.2686 | 0 | 0 | 0 | 0 | 0 | 1.2686 | 0 | 1.2686 | 0 | 0 | 0 | 0 | 1.5574
35332364 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-06-12 | 2023-07-28 | 08W | Base SH | 0 | 1.0562 | 0 | 1.0562 | 0 | 0 | 0 | 0 | 0 | 1.0562 | 0 | 1.0562 | 0 | 0 | 0 | 0 | 1.6099
35332866 | 103441103 | JESSUP 1103 | JESSUP 1103348657 | SHASTA | 2023-08-28 | 2024-03-22 | 08W | Base SH | 0 | 0.7411 | 0 | 0.7411 | 0 | 0 | 0 | 0 | 0 | 0.7411 | 0 | 0.7411 | 0 | 0 | 0 | 0 | 3.0534
35332872 | 153701104 | LINCOLN 1104 | LINCOLN 1104997576 | PLACER | 2023-09-25 | 2023-12-12 | 08W | Base SH | 2.0771 | 0.20777 | 0 | 2.2848 | 0 | 0 | 0 | 0 | 2.0771 | 0.20777 | 0 | 2.2848 | 0 | 0 | 0 | 0 | 2.3096
35332958 | 153701104 | LINCOLN 1104 | LINCOLN 11042070 | PLACER | 2023-08-14 | 2023-12-12 | 08W | Base SH | 0 | 2.2254 | 0 | 2.2254 | 0 | 0 | 0 | 0 | 0 | 2.2254 | 0 | 2.2254 | 0 | 0 | 0 | 0 | 4.3359
35334229 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-09-18 | 2024-04-26 | 08W | Base SH | 0 | 2.986 | 0 | 2.986 | 0 | 0 | 0 | 0 | 0 | 2.986 | 0 | 2.986 | 0 | 0 | 0 | 0 | 5.2628
35334750 | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | 2023-09-06 | 2024-04-27 | 08W | Base SH | 0 | 1.2367 | 0 | 1.2367 | 0 | 0 | 0 | 0 | 0 | 1.2367 | 0 | 1.2367 | 0 | 0 | 0 | 0 | 5.3867
35334752 | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | SOLANO | 2023-09-18 | 2024-03-24 | 08W | Base SH | 0 | 1.8445 | 0 | 1.8445 | 0 | 0 | 0 | 0 | 0 | 1.8445 | 0 | 1.8445 | 0 | 0 | 0 | 0 | 6.2179
35334753 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-07-10 | 2023-09-30 | 08W | Base SH | 0 | 1.7612 | 0 | 1.7612 | 0 | 0 | 0 | 0 | 0 | 1.7612 | 0 | 1.7612 | 0 | 0 | 0 | 0 | 4.0045
35337010 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-07-10 | 2024-03-15 | 08W | Base SH | 0 | 3.4553 | 0 | 3.4553 | 0 | 0 | 0 | 0 | 0 | 3.4553 | 0 | 3.4553 | 0 | 0 | 0 | 0 | 5.8109
35337011 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-07-24 | 2024-03-06 | 08W | Base SH | 0 | 2.9191 | 0 | 2.9191 | 0 | 0 | 0 | 0 | 0 | 2.9191 | 0 | 2.9191 | 0 | 0 | 0 | 0 | 4.5139
35337012 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-08-07 | 2024-02-29 | 08W | Base SH | 0 | 4.1544 | 0 | 4.1544 | 0 | 0 | 0 | 0 | 0 | 4.1544 | 0 | 4.1544 | 0 | 0 | 0 | 0 | 7.1976
35337014 | 63801105 | JAMESON 1105 | JAMESON 11059472 | SOLANO | 2023-06-19 | 2023-08-19 | 08W | Base SH | 0.97595 | 0.031818 | 0 | 1.0078 | 0.060985 | 0 | 0 | 0.060985 | 0.91496 | 0.031818 | 0 | 0.94678 | 0 | 0 | 0 | 0 | 1.6468
35337015 | 63801105 | JAMESON 1105 | JAMESON 11059472 | SOLANO | 2023-06-19 | 2023-08-19 | 08W | Base SH | 0 | 0.4572 | 0 | 0.4572 | 0 | 0 | 0 | 0 | 0 | 0.4572 | 0 | 0.4572 | 0 | 0 | 0 | 0 | 1.6803
35337151 | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | MADERA | 2022-08-22 | 2022-11-28 | 10J | Other | 0 | 0.11837 | 0 | 0.11837 | 0 | 0 | 0 | 0 | 0 | 0.11837 | 0 | 0.11837 | 0 | 0 | 0 | 0 | Not Available
35337163 | 153701104 | LINCOLN 1104 | LINCOLN 1104275986 | PLACER | 2023-07-17 | 2023-10-12 | 08W | Base SH | 0.47727 | 0.89811 | 0 | 1.3754 | 0 | 0 | 0 | 0 | 0.47727 | 0.89811 | 0 | 1.3754 | 0 | 0 | 0 | 0 | 3.1906
35337306 | 162821702 | STANISLAUS 1702 | STANISLAUS 1702CB | CALAVERAS | 2023-04-14 | 2024-02-16 | 08W | Base SH | 0.019318 | 2.3008 | 0 | 2.3201 | 0 | 0 | 0 | 0 | 0.019318 | 2.3008 | 0 | 2.3201 | 0 | 0 | 0 | 0 | 7.2854
35338384 | 162821701 | STANISLAUS 1701 | STANISLAUS 1701CB | CALAVERAS | 2023-07-10 | 2024-04-16 | 08W | Base SH | 0 | 1.5968 | 0 | 1.5968 | 0 | 0 | 0 | 0 | 0 | 1.5968 | 0 | 1.5968 | 0 | 0 | 0 | 0 | 4.7609
35338402 | 103461101 | PANORAMA 1101 | PANORAMA 1101CB | SHASTA | 2023-07-17 | 2023-09-06 | 08W | Base SH | 0 | 1.4112 | 0 | 1.4112 | 0 | 0 | 0 | 0 | 0 | 1.4112 | 0 | 1.4112 | 0 | 0 | 0 | 0 | 1.8413
35338404 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-08-28 | 2023-11-30 | 08W | Base SH | 0 | 1.5994 | 0 | 1.5994 | 0 | 0 | 0 | 0 | 0 | 1.5994 | 0 | 1.5994 | 0 | 0 | 0 | 0 | 4.6086
35338405 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-07-17 | 2023-10-28 | 08W | Base SH | 0 | 2.147 | 0 | 2.147 | 0 | 0 | 0 | 0 | 0 | 2.147 | 0 | 2.147 | 0 | 0 | 0 | 0 | 5.6791
35338409 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-07-17 | 2023-11-06 | 08W | Base SH | 0 | 2.5402 | 0 | 2.5402 | 0 | 0 | 0 | 0 | 0 | 2.5402 | 0 | 2.5402 | 0 | 0 | 0 | 0 | 5.4714
35338410 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-07-31 | 2023-11-10 | 08W | Base SH | 0 | 2.0521 | 0 | 2.0521 | 0 | 0 | 0 | 0 | 0 | 2.0521 | 0 | 2.0521 | 0 | 0 | 0 | 0 | 4.2009
35339282 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-09-18 | 2024-01-05 | 08W | Base SH | 0 | 0.52027 | 0 | 0.52027 | 0 | 0 | 0 | 0 | 0 | 0.52027 | 0 | 0.52027 | 0 | 0 | 0 | 0 | 1.5488
35339283 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-08-07 | 2024-03-08 | 08W | Base SH | 0 | 2.553 | 0 | 2.553 | 0 | 0 | 0 | 0 | 0 | 2.553 | 0 | 2.553 | 0 | 0 | 0 | 0 | 5.9918
35339285 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-06-20 | 2024-01-12 | 08W | Base SH | 0 | 1.3479 | 0 | 1.3479 | 0 | 0 | 0 | 0 | 0 | 1.3479 | 0 | 1.3479 | 0 | 0 | 0 | 0 | 2.8091
35339286 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-06-26 | 2024-01-26 | 08W | Base SH | 0 | 1.9854 | 0 | 1.9854 | 0 | 0 | 0 | 0 | 0 | 1.9854 | 0 | 1.9854 | 0 | 0 | 0 | 0 | 2.9897
35339287 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-06-05 | 2023-08-08 | 08W | Base SH | 0 | 1.068 | 0 | 1.068 | 0 | 0 | 0 | 0 | 0 | 1.068 | 0 | 1.068 | 0 | 0 | 0 | 0 | 2.4437
35339288 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-04-17 | 2023-09-07 | 08W | Base SH | 0.0034091 | 2.5028 | 0 | 2.5063 | 0 | 0 | 0 | 0 | 0.0034091 | 2.5028 | 0 | 2.5063 | 0 | 0 | 0 | 0 | 6.0599
35339289 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-06-05 | 2023-08-25 | 08W | Base SH | 0 | 1.1839 | 0 | 1.1839 | 0 | 0 | 0 | 0 | 0 | 1.1839 | 0 | 1.1839 | 0 | 0 | 0 | 0 | 2.2356
35339293 | 63801105 | JAMESON 1105 | JAMESON 1105466348 | SOLANO | 2023-07-17 | 2023-09-02 | 08W | Base SH | 0 | 1.2508 | 0 | 1.2508 | 0 | 0 | 0 | 0 | 0 | 1.2508 | 0 | 1.2508 | 0 | 0 | 0 | 0 | 3.443
35339665 | 152571101 | HORSESHOE 1101 | HORSESHOE 110150140 | PLACER | 2023-07-31 | 2023-10-27 | 08W | Base SH | 0 | 0.8072 | 0 | 0.8072 | 0 | 0 | 0 | 0 | 0 | 0.8072 | 0 | 0.8072 | 0 | 0 | 0 | 0 | 4.3286
35340270 | 103331102 | CORNING 1102 | CORNING 1102915324 | TEHAMA | 2023-10-04 | 2024-04-12 | 08W | Base SH | 0 | 2.3447 | 0 | 2.3447 | 0 | 0 | 0 | 0 | 0 | 2.3447 | 0 | 2.3447 | 0 | 0 | 0 | 0 | 5.432
35342145 | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | 2023-07-10 | 2023-09-15 | 08W | Base SH | 0 | 0.18068 | 0 | 0.18068 | 0 | 0 | 0 | 0 | 0 | 0.18068 | 0 | 0.18068 | 0 | 0 | 0 | 0 | 1.1783
35342151 | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | 2023-07-13 | 2023-08-07 | 08W | Base SH | 0 | 0.077841 | 0 | 0.077841 | 0 | 0 | 0 | 0 | 0 | 0.077841 | 0 | 0.077841 | 0 | 0 | 0 | 0 | 0.30969
35343395 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | 2023-08-02 | 2024-01-19 | 08W | Base SH | 0 | 1.9903 | 0 | 1.9903 | 0 | 0 | 0 | 0 | 0 | 1.9903 | 0 | 1.9903 | 0 | 0 | 0 | 0 | 6.2878
35343396 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | 2023-06-20 | 2024-01-31 | 08W | Base SH | 0 | 1.0896 | 0 | 1.0896 | 0 | 0 | 0 | 0 | 0 | 1.0896 | 0 | 1.0896 | 0 | 0 | 0 | 0 | 3.6329
35349244 | 153701104 | LINCOLN 1104 | LINCOLN 1104685276 | PLACER | 2023-07-24 | 2023-10-31 | 08W | Base SH | 0 | 0.62879 | 0.67973 | 1.3085 | 0 | 0 | 0 | 0 | 0 | 0.62879 | 0.67973 | 1.3085 | 0 | 0 | 0 | 0 | 1.2146
35367520 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | CALAVERAS | 2023-06-06 | 2024-03-29 | 3UG | Base SH | 0 | 2.0172 | 0 | 2.0172 | 0 | 0 | 0 | 0 | 0 | 2.0172 | 0 | 2.0172 | 0 | 0 | 0 | 0 | 7.9908
35380365 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-09-14 | 2024-04-05 | 08W | Base SH | 0 | 2.6271 | 0 | 2.6271 | 0 | 0 | 0 | 0 | 0 | 2.6271 | 0 | 2.6271 | 0 | 0 | 0 | 0 | 4.7712
35380371 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-08-15 | 2024-02-16 | 08W | Base SH | 0 | 2.0348 | 0 | 2.0348 | 0 | 0 | 0 | 0 | 0 | 2.0348 | 0 | 2.0348 | 0 | 0 | 0 | 0 | 3.3716
35380372 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-08-22 | 2024-01-26 | 08W | Base SH | 0 | 1.5839 | 0 | 1.5839 | 0 | 0 | 0 | 0 | 0 | 1.5839 | 0 | 1.5839 | 0 | 0 | 0 | 0 | 2.4482
35380373 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-08-28 | 2024-02-16 | 08W | Base SH | 0 | 1.5989 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 0 | 1.5989 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 2.6533
35380376 | 103331102 | CORNING 1102 | CORNING 110253184 | TEHAMA | 2023-08-17 | 2024-02-23 | 08W | Base SH | 0 | 2.515 | 0 | 2.515 | 0 | 0 | 0 | 0 | 0 | 2.515 | 0 | 2.515 | 0 | 0 | 0 | 0 | 2.8617
35384087 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022070 | BUTTE | 2023-07-28 | 2024-03-30 | 08W | Base SH | 0 | 0.43258 | 0 | 0.43258 | 0 | 0 | 0 | 0 | 0 | 0.43258 | 0 | 0.43258 | 0 | 0 | 0 | 0 | 0.97125
35385888 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | CALAVERAS | 2023-06-06 | 2024-01-30 | 3UG | Base SH | 0 | 1.51 | 0 | 1.51 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 1.51 | 0 | 0 | 0 | 0 | 4.9241
35385889 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | CALAVERAS | 2023-08-07 | 2024-01-30 | 3UG | Base SH | 0 | 1.9521 | 0 | 1.9521 | 0 | 0 | 0 | 0 | 0 | 1.9521 | 0 | 1.9521 | 0 | 0 | 0 | 0 | 5.9774
35385890 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | CALAVERAS | 2023-07-13 | 2024-03-29 | 3UG | Base SH | 0 | 0.81572 | 0 | 0.81572 | 0 | 0 | 0 | 0 | 0 | 0.81572 | 0 | 0.81572 | 0 | 0 | 0 | 0 | 2.8342
35390288 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | NEVADA | 2023-10-04 | 2023-10-27 | 3UG | Base SH | 0 | 0.10549 | 0 | 0.10549 | 0 | 0 | 0 | 0 | 0 | 0.10549 | 0 | 0.10549 | 0 | 0 | 0 | 0 | 0.81527
35404727 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-06-20 | 2023-09-07 | 08W | Base SH | 0 | 1.086 | 0 | 1.086 | 0 | 0 | 0 | 0 | 0 | 1.086 | 0 | 1.086 | 0 | 0 | 0 | 0 | 2.094
35404728 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-08-07 | 2023-10-07 | 08W | Base SH | 0 | 0.82462 | 0 | 0.82462 | 0 | 0 | 0 | 0 | 0 | 0.82462 | 0 | 0.82462 | 0 | 0 | 0 | 0 | 1.568
35404729 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-06-12 | 2023-10-25 | 08W | Base SH | 0 | 0.80644 | 0 | 0.80644 | 0 | 0 | 0 | 0 | 0 | 0.80644 | 0 | 0.80644 | 0 | 0 | 0 | 0 | 2.0576
35421339 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110576498 | MENDOCINO | Not Available | Not Available | 3UG | Base SH | 0 | 0.37178 | 0 | 0.37178 | 0 | 0 | 0 | 0 | 0 | 0.37178 | 0 | 0.37178 | 0 | 0 | 0 | 0 | 0.37121
35217274 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | SAN MATEO | 2022-09-07 | 2023-08-08 | 08W | Fire Rebuild | 0 | 2.5239 | 0 | 2.5239 | 0 | 1.6411 | 0 | 1.6411 | 0 | 0.88277 | 0 | 0.88277 | 0 | 0 | 0 | 0 | 4.3274
35217275 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | SAN MATEO | 2022-11-02 | 2023-05-05 | 08W | Fire Rebuild | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 0 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0 | 0 | 7.5974
35241077 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | BUTTE | 2023-08-29 | 2023-11-28 | 08W | Fire Rebuild | 0 | 0.33807 | 0 | 0.33807 | 0 | 0 | 0 | 0 | 0 | 0.33807 | 0 | 0.33807 | 0 | 0 | 0 | 0 | 1.2863
35279985 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2023-05-16 | 2023-08-31 | 08W | Fire Rebuild | 0 | 2.7989 | 0 | 2.7989 | 0 | 0 | 0 | 0 | 0 | 2.7989 | 0 | 2.7989 | 0 | 0 | 0 | 0 | 7.8738
35280493 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2023-04-14 | 2023-08-26 | 08W | Fire Rebuild | 0 | 0.44811 | 0 | 0.44811 | 0 | 0 | 0 | 0 | 0 | 0.44811 | 0 | 0.44811 | 0 | 0 | 0 | 0 | 1.9448
35281815 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-07-17 | 2023-10-06 | 08W | Fire Rebuild | 0 | 0.51799 | 0 | 0.51799 | 0 | 0 | 0 | 0 | 0 | 0.51799 | 0 | 0.51799 | 0 | 0 | 0 | 0 | 3.4867
35282166 | 103104401 | SPANISH CREEK 4401 | SPANISH CREEK 4401CB | PLUMAS | 2023-07-06 | 2023-10-14 | 08W | Fire Rebuild | 0 | 2.5703 | 0 | 2.5703 | 0 | 0 | 0 | 0 | 0 | 2.5703 | 0 | 2.5703 | 0 | 0 | 0 | 0 | 21.8438
35290517 | 103104401 | SPANISH CREEK 4401 | SPANISH CREEK 4401CB | PLUMAS | 2023-05-08 | 2024-03-29 | 08W | Fire Rebuild | 0 | 0.6625 | 0 | 0.6625 | 0 | 0 | 0 | 0 | 0 | 0.6625 | 0 | 0.6625 | 0 | 0 | 0 | 0 | 2.3625
35290540 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2022-10-26 | 2023-07-28 | 08W | Fire Rebuild | 0 | 1.335 | 0.094697 | 1.4297 | 0 | 0 | 0 | 0 | 0 | 1.335 | 0.094697 | 1.4297 | 0 | 0 | 0 | 0 | 14.7496
35290542 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-04-24 | 2023-09-21 | 08W | Fire Rebuild | 0 | 1.2955 | 0 | 1.2955 | 0 | 0 | 0 | 0 | 0 | 1.2955 | 0 | 1.2955 | 0 | 0 | 0 | 0 | 3.1419
35290944 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-05-30 | 2023-06-26 | 08W | Fire Rebuild | 0 | 0.48788 | 0 | 0.48788 | 0 | 0 | 0 | 0 | 0 | 0.48788 | 0 | 0.48788 | 0 | 0 | 0 | 0 | 0.93359
35292754 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2022-10-29 | 2023-09-19 | 08W | Fire Rebuild | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 0 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0 | 0 | 30.1994
35292755 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2022-10-26 | 2023-09-18 | 08W | Fire Rebuild | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 0 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0 | 0 | 23.9702
35292756 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | PLUMAS | 2023-05-19 | 2023-09-20 | 08W | Fire Rebuild | 0 | 1.2301 | 0 | 1.2301 | 0 | 0 | 0 | 0 | 0 | 1.2301 | 0 | 1.2301 | 0 | 0 | 0 | 0 | 4.5971
35292780 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-08-29 | 2023-09-23 | 08W | Fire Rebuild | 0 | 0.24318 | 0 | 0.24318 | 0 | 0 | 0 | 0 | 0 | 0.24318 | 0 | 0.24318 | 0 | 0 | 0 | 0 | 0.70867
35292789 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012476 | PLUMAS | 2023-06-26 | 2023-07-13 | 08W | Fire Rebuild | 0 | 0.23636 | 0 | 0.23636 | 0 | 0 | 0 | 0 | 0 | 0.23636 | 0 | 0.23636 | 0 | 0 | 0 | 0 | 0.89569
35292791 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012586 | PLUMAS | 2022-08-08 | 2022-08-14 | 08W | Fire Rebuild | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0 | 0 | 0.4176
35297692 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-07-25 | 2023-10-23 | 08W | Fire Rebuild | 0 | 4.5937 | 0 | 4.5937 | 0 | 0 | 0 | 0 | 0 | 4.5937 | 0 | 4.5937 | 0 | 0 | 0 | 0 | 20.1627
35297693 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-08-07 | 2023-10-30 | 08W | Fire Rebuild | 0 | 0.95928 | 0 | 0.95928 | 0 | 0 | 0 | 0 | 0 | 0.95928 | 0 | 0.95928 | 0 | 0 | 0 | 0 | 4.7756
35297694 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-08-16 | 2023-11-04 | 08W | Fire Rebuild | 0 | 0.93371 | 0 | 0.93371 | 0 | 0 | 0 | 0 | 0 | 0.93371 | 0 | 0.93371 | 0 | 0 | 0 | 0 | 3.8927
35297695 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-08-17 | 2023-10-13 | 08W | Fire Rebuild | 0 | 0.45455 | 0 | 0.45455 | 0 | 0 | 0 | 0 | 0 | 0.45455 | 0 | 0.45455 | 0 | 0 | 0 | 0 | 1.0428
35297696 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-09-12 | 2023-10-23 | 08W | Fire Rebuild | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0 | 1.3739
35297699 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-07-21 | 2023-10-12 | 08W | Fire Rebuild | 0 | 1.0606 | 0 | 1.0606 | 0 | 0 | 0 | 0 | 0 | 1.0606 | 0 | 1.0606 | 0 | 0 | 0 | 0 | 4.7524
35313249 | Not Available | Not Available | Not Available | PLUMAS | 2023-10-14 | 2023-10-29 | 95F | Community Rebuild | 0 | 1.1652 | 0 | 1.1652 | 0 | 0 | 0 | 0 | 0 | 1.1652 | 0 | 1.1652 | 0 | 0 | 0 | 0 | 3.681
35318072 | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | SANTA CRUZ | 2023-04-17 | 2023-12-15 | 08W | Fire Rebuild | 0.013826 | 0.1803 | 0 | 0.19413 | 0 | 0 | 0 | 0 | 0.013826 | 0.1803 | 0 | 0.19413 | 0 | 0 | 0 | 0 | 1.1632
35318074 | 82841102 | BIG BASIN 1102 | BIG BASIN 11022253 | SANTA CRUZ | 2023-10-20 | 2023-11-14 | 08W | Fire Rebuild | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0.80569
35334407 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | TRINITY | 2023-07-11 | 2023-10-06 | 08W | Fire Rebuild | 0 | 0.22538 | 0 | 0.22538 | 0 | 0 | 0 | 0 | 0 | 0.22538 | 0 | 0.22538 | 0 | 0 | 0 | 0 | 0.79861
35334541 | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | SANTA CRUZ | 2023-03-27 | 2023-12-15 | 08W | Fire Rebuild | 0 | 0.13617 | 0 | 0.13617 | 0 | 0 | 0 | 0 | 0 | 0.13617 | 0 | 0.13617 | 0 | 0 | 0 | 0 | 1.0574
35342339 | 82841102 | BIG BASIN 1102 | BIG BASIN 110296986 | SANTA CRUZ | 2023-07-12 | 2023-08-04 | 08W | Fire Rebuild | 0 | 0.14489 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0 | 0.14489 | 0 | 0.14489 | 0 | 0 | 0 | 0 | 0.41924
35350039 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | BUTTE | Not Available | Not Available | 08W | Fire Rebuild | 0 | 0.096212 | 0 | 0.096212 | 0 | 0 | 0 | 0 | 0 | 0.096212 | 0 | 0.096212 | 0 | 0 | 0 | 0 | 0.25826
35373051 | 103221101 | KANAKA 1101 | KANAKA 1101CB | BUTTE | Not Available | Not Available | 08W | Fire Rebuild | 0 | 0.12424 | 0 | 0.12424 | 0 | 0 | 0 | 0 | 0 | 0.12424 | 0 | 0.12424 | 0 | 0 | 0 | 0 | 0.34955
35374559 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-05-22 | 2024-02-29 | 08W | Fire Rebuild | 0 | 3.9581 | 0 | 3.9581 | 0 | 0 | 0 | 0 | 0 | 3.9581 | 0 | 3.9581 | 0 | 0 | 0 | 0 | 10.1106
35374681 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | 2023-05-08 | 2024-01-19 | 08W | Fire Rebuild | 0 | 5.0826 | 0 | 5.0826 | 0 | 0 | 0 | 0 | 0 | 5.0826 | 0 | 5.0826 | 0 | 0 | 0 | 0 | 13.0541
35374683 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-07-24 | 2024-02-29 | 08W | Fire Rebuild | 0 | 1.3799 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 0 | 1.3799 | 0 | 1.3799 | 0 | 0 | 0 | 0 | 5.2504
35374684 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-08-11 | 2024-02-29 | 08W | Fire Rebuild | 0 | 1.4767 | 0 | 1.4767 | 0 | 0 | 0 | 0 | 0 | 1.4767 | 0 | 1.4767 | 0 | 0 | 0 | 0 | 4.4644
35374686 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-06-05 | 2023-11-17 | 08W | Fire Rebuild | 0 | 2.5994 | 0 | 2.5994 | 0 | 0 | 0 | 0 | 0 | 2.5994 | 0 | 2.5994 | 0 | 0 | 0 | 0 | 5.25
35374862 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-09-18 | 2024-06-30 | 08W | Fire Rebuild | 0 | 1.5746 | 0.1178 | 1.6924 | 0 | 0 | 0 | 0 | 0 | 1.5746 | 0.1178 | 1.6924 | 0 | 0 | 0 | 0 | 3.3892
35374864 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-09-11 | 2023-12-08 | 08W | Fire Rebuild | 0 | 1.7504 | 0 | 1.7504 | 0 | 0 | 0 | 0 | 0 | 1.7504 | 0 | 1.7504 | 0 | 0 | 0 | 0 | 3.4629
35374865 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-07-17 | 2023-10-27 | 08W | Fire Rebuild | 0 | 0.78883 | 0 | 0.78883 | 0 | 0 | 0 | 0 | 0 | 0.78883 | 0 | 0.78883 | 0 | 0 | 0 | 0 | 1.5728
35374866 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-06-05 | 2023-10-27 | 08W | Fire Rebuild | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 0 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0 | 0 | 1.3066
35375721 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | MARIPOSA | 2023-08-14 | 2023-12-08 | 08W | Fire Rebuild | 0 | 0.95928 | 0 | 0.95928 | 0 | 0 | 0 | 0 | 0 | 0.95928 | 0 | 0.95928 | 0 | 0 | 0 | 0 | 1.9105
35376303 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | MARIPOSA | 2023-07-10 | 2023-11-17 | 08W | Fire Rebuild | 0 | 0.27348 | 0 | 0.27348 | 0 | 0 | 0 | 0 | 0 | 0.27348 | 0 | 0.27348 | 0 | 0 | 0 | 0 | 0.90665
35376305 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110170 | MARIPOSA | 2023-09-05 | 2023-12-08 | 08W | Fire Rebuild | 0 | 0.53068 | 0 | 0.53068 | 0 | 0 | 0 | 0 | 0 | 0.53068 | 0 | 0.53068 | 0 | 0 | 0 | 0 | 1.4872
35398092 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-09-07 | 2023-10-27 | 08W | Fire Rebuild | 0 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0 | 0 | 0.26164
35398093 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-09-07 | 2023-10-27 | 08W | Fire Rebuild | 0 | 0.14508 | 0 | 0.14508 | 0 | 0 | 0 | 0 | 0 | 0.14508 | 0 | 0.14508 | 0 | 0 | 0 | 0 | 0.30035
35404061 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-09-13 | 2023-10-27 | 08W | Fire Rebuild | 0 | 0.071591 | 0 | 0.071591 | 0 | 0 | 0 | 0 | 0 | 0.071591 | 0 | 0.071591 | 0 | 0 | 0 | 0 | 0.16888
35419624 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031941 | BUTTE | Not Available | Not Available | 08W | Fire Rebuild | 0 | 0.099621 | 0 | 0.099621 | 0 | 0 | 0 | 0 | 0 | 0.099621 | 0 | 0.099621 | 0 | 0 | 0 | 0 | 0.38337
35127360 | 102831103 | PARADISE 1103 | Paradise 110353544 | BUTTE | 2023-09-11 | 2023-12-19 17:00 | 95F | Community Rebuild | 0 | 0.71212 | 0 | 0.71212 | 0 | 0 | 0 | 0 | 0 | 0.71212 | 0 | 0.71212 | 0 | 0 | 0 | 0 | 3.5368
35352075 | 102831106 | PARADISE 1106 | PARADISE 110636042 | BUTTE | 2023-04-17 | 2023-11-17 17:00 | 08W | Community Rebuild | 0 | 5.1972 | 0 | 5.1972 | 0 | 0 | 0 | 0 | 0 | 5.1972 | 0 | 5.1972 | 0 | 0 | 0 | 0 | 14.2514
35189791 | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | 2022-08-13 | 2023-02-09 17:00 | 95F | Community Rebuild | 0 | 1.4091 | 0 | 1.4091 | 0 | 0 | 0 | 0 | 0 | 1.4091 | 0 | 1.4091 | 0 | 0 | 0 | 0 | 3.044
35189792 | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | 2023-01-24 | 2023-10-20 17:00 | 95F | Community Rebuild | 0 | 3.6905 | 0 | 3.6905 | 0 | 0 | 0 | 0 | 0 | 3.6905 | 0 | 3.6905 | 0 | 0 | 0 | 0 | 5.9396
35117455 | 102831106 | PARADISE 1106 | Paradise 1106CB | BUTTE | 2023-05-01 | 2024-05-24 17:00 | 08W | Community Rebuild | 0 | 0.82955 | 0 | 0.82955 | 0 | 0 | 0 | 0 | 0 | 0.82955 | 0 | 0.82955 | 0 | 0.37652 | 0 | 0.37652 | 6.1294
35126750 | 102831104 | PARADISE 1104 | PARADISE 11042206 | BUTTE | 2022-03-14 | 2023-04-26 17:00 | 95F | Community Rebuild | 0 | 2.5801 | 0 | 2.5801 | 0 | 0 | 0 | 0 | 0 | 2.5801 | 0 | 2.5801 | 0 | 0 | 0 | 0 | 8.9951
35175547 | 102831105 | PARADISE 1105 | PARADISE 1105CB | BUTTE | 2021-12-01 | 2023-02-06 08:00 | 95F | Community Rebuild | 0 | 1.2951 | 0 | 1.2951 | 0 | 0 | 0 | 0 | 0 | 1.2951 | 0 | 1.2951 | 0 | 0 | 0 | 0 | 9.5895
35189851 | 102831103 | PARADISE 1103 | PARADISE 11032534 | BUTTE | 2022-07-11 | 2022-12-12 17:00 | 95F | Community Rebuild | 0 | 2.4947 | 0 | 2.4947 | 0 | 2.2938 | 0 | 2.2938 | 0 | 0.20095 | 0 | 0.20095 | 0 | 0 | 0 | 0 | 6.105
35227401 | 102831103 | PARADISE 1103 | Paradise 11032534 | BUTTE | 2023-05-22 | 2023-10-20 17:00 | 95F | Community Rebuild | 0 | 1.2627 | 0 | 1.2627 | 0 | 0 | 0 | 0 | 0 | 1.2627 | 0 | 1.2627 | 0 | 0 | 0 | 0 | 4.3862
35118676 | 102831103 | PARADISE 1103 | PARADISE 11032534 | BUTTE | 2022-10-10 | 2023-08-31 17:00 | 95F | Community Rebuild | 0 | 3.4761 | 0 | 3.4761 | 0 | 0 | 0 | 0 | 0 | 3.4761 | 0 | 3.4761 | 0 | 0 | 0 | 0 | 7.146
35126645 | 102831103 | PARADISE 1103 | PARADISE 1103CB | BUTTE | 2022-09-06 | 2023-08-31 17:00 | 95F | Community Rebuild | 0 | 2.2104 | 0 | 2.2104 | 0 | 0 | 0 | 0 | 0 | 2.2104 | 0 | 2.2104 | 0 | 0 | 0 | 0 | 5.9237
35227402 | 102831105 | PARADISE 1105 | Paradise 1105CB | BUTTE | 2023-03-15 | 2024-03-05 08:00 | 95F | Community Rebuild | 0 | 0.9089 | 0 | 0.9089 | 0 | 0 | 0 | 0 | 0 | 0.9089 | 0 | 0.9089 | 0 | 0.3053 | 0 | 0.3053 | 5.1943
35175548 | 102831103 | PARADISE 1103 | PARADISE 1103CB | BUTTE | 2022-07-11 | 2023-09-18 17:00 | 95F | Community Rebuild | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 0 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0 | 0 | 7.981
35227403 | 102831103 | PARADISE 1103 | PARADISE 1103CB | BUTTE | 2022-10-04 | 2023-09-22 17:01 | 95F | Community Rebuild | 0 | 2.1731 | 0 | 2.1731 | 0 | 0 | 0 | 0 | 0 | 2.1731 | 0 | 2.1731 | 0 | 0 | 0 | 0 | 4.7047
35227405 | 102831103 | PARADISE 1103 | Paradise 1103CB | BUTTE | 2023-04-10 | 2023-06-27 17:00 | 95F | Community Rebuild | 0 | 0.25795 | 0 | 0.25795 | 0 | 0 | 0 | 0 | 0 | 0.25795 | 0 | 0.25795 | 0 | 0 | 0 | 0 | 1.5088
35227406 | 102831104 | PARADISE 1104 | Paradise 1104CB | BUTTE | 2023-04-24 | 2023-10-06 17:00 | 95F | Community Rebuild | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 0 | 2.443 | 0 | 2.443 | 0 | 0 | 0 | 0 | 8.2796
35227404 | 102831104 | PARADISE 1104 | Paradise 1104CB | BUTTE | 2023-01-30 | 2023-07-12 17:00 | 95F | Community Rebuild | 0 | 1.5837 | 0 | 1.5837 | 0 | 0 | 0 | 0 | 0 | 1.5837 | 0 | 1.5837 | 0 | 0 | 0 | 0 | 4.7283
35227408 | 102831104 | PARADISE 1104 | Paradise 1104CB | BUTTE | 2023-05-16 | 2023-11-27 08:00 | 95F | Community Rebuild | 0 | 2.021 | 0 | 2.021 | 0 | 0 | 0 | 0 | 0 | 2.021 | 0 | 2.021 | 0 | 0 | 0 | 0 | 6.7892
35227411 | 102831105 | PARADISE 1105 | PARADISE 110599226 | BUTTE | 2023-05-30 | 2023-12-07 17:00 | 95F | Community Rebuild | 0 | 2.6496 | 0 | 2.6496 | 0 | 0 | 0 | 0 | 0 | 2.6496 | 0 | 2.6496 | 0 | 0 | 0 | 0 | 10.201
35189853 | 102831104 | PARADISE 1104 | PARADISE 11042206 | BUTTE | 2022-08-17 | 2023-01-12 17:00 | 95F | Community Rebuild | 0 | 1.4928 | 0 | 1.4928 | 0 | 0 | 0 | 0 | 0 | 1.4928 | 0 | 1.4928 | 0 | 0 | 0 | 0 | 3.1102
35246590 | 102831104 | PARADISE 1104 | Paradise 11042206 | BUTTE | 2023-07-10 | 2024-06-17 17:00 | 08W | Community Rebuild | 0 | 1.0816 | 0 | 1.0816 | 0 | 0 | 0 | 0 | 0 | 1.0816 | 0 | 1.0816 | 0 | 1.0441 | 0 | 1.0441 | 5.3339
35350874 | 102831104 | PARADISE 1104 | PARADISE 1104920400 | BUTTE | 2022-11-28 | 2023-07-15 08:00 | 95F | Community Rebuild | 0 | 1.66 | 0 | 1.66 | 0 | 0 | 0 | 0 | 0 | 1.66 | 0 | 1.66 | 0 | 0 | 0 | 0 | 3.9425
35286270 | 102831103 | PARADISE 1103 | Paradise 1103CB | BUTTE | 2023-05-15 | 2023-10-17 17:00 | 95F | Community Rebuild | 0 | 0.98144 | 0 | 0.98144 | 0 | 0 | 0 | 0 | 0 | 0.98144 | 0 | 0.98144 | 0 | 0 | 0 | 0 | 4.9311
35227415 | 102831103 | PARADISE 1103 | Paradise 110343008 | BUTTE | 2023-05-09 | 2023-10-27 17:00 | 95F | Community Rebuild | 0 | 2.879 | 0 | 2.879 | 0 | 0 | 0 | 0 | 0 | 2.879 | 0 | 2.879 | 0 | 0 | 0 | 0 | 7.618
35189983 | 102831103 | PARADISE 1103 | PARADISE 11032486 | BUTTE | 2022-03-14 | 2023-12-11 08:00 | 95F | Community Rebuild | 0 | 2.0981 | 0 | 2.0981 | 0 | 0 | 0 | 0 | 0 | 2.0981 | 0 | 2.0981 | 0 | 0 | 0 | 0 | 6.5541
35126752 | 102831104 | PARADISE 1104 | PARADISE 1104409622 | BUTTE | 2023-06-15 | 2023-10-31 17:00 | 95F | Community Rebuild | 0 | 1.2731 | 0 | 1.2731 | 0 | 0 | 0 | 0 | 0 | 1.2731 | 0 | 1.2731 | 0 | 0 | 0 | 0 | 3.3346
35189984 | 102831104 | PARADISE 1104 | PARADISE 110439216 | BUTTE | 2022-10-03 | 2023-05-31 17:00 | 95F | Community Rebuild | 0 | 3.4121 | 0 | 3.4121 | 0 | 0 | 0 | 0 | 0 | 3.4121 | 0 | 3.4121 | 0 | 0 | 0 | 0 | 7.5384
35189987 | 102831104 | PARADISE 1104 | PARADISE 1104457900 | BUTTE | 2022-10-31 | 2023-07-27 17:00 | 95F | Community Rebuild | 0 | 2.8201 | 0 | 2.8201 | 0 | 0 | 0 | 0 | 0 | 2.8201 | 0 | 2.8201 | 0 | 0 | 0 | 0 | 5.198
35227481 | 102831104 | PARADISE 1104 | PARADISE 1104954322 | BUTTE | 2022-09-20 | 2023-07-15 17:00 | 95F | Community Rebuild | 0 | 4.4428 | 0 | 4.4428 | 0 | 0 | 0 | 0 | 0 | 4.4428 | 0 | 4.4428 | 0 | 0 | 0 | 0 | 12.2483
35144480 | 102831105 | PARADISE 1105 | Paradise 1105121988 | BUTTE | 2023-05-23 | 2023-10-11 17:00 | 95F | Community Rebuild | 0 | 2.6464 | 0 | 2.6464 | 0 | 0 | 0 | 0 | 0 | 2.6464 | 0 | 2.6464 | 0 | 0 | 0 | 0 | 8.5385
35353399 | 102831105 | PARADISE 1105 | PARADISE 1105121988 | BUTTE | 2023-07-24 | 2023-12-01 08:00 | 08W | Community Rebuild | 0 | 2.2894 | 0 | 2.2894 | 0 | 0 | 0 | 0 | 0 | 2.2894 | 0 | 2.2894 | 0 | 0 | 0 | 0 | 8.567
35353466 | 102831105 | PARADISE 1105 | Paradise 1105829194 | BUTTE | 2023-07-10 | 2023-12-02 17:00 | 08W | Community Rebuild | 0 | 2.603 | 0 | 2.603 | 0 | 0 | 0 | 0 | 0 | 2.603 | 0 | 2.603 | 0 | 0 | 0 | 0 | 7.4073
35353467 | 102831105 | PARADISE 1105 | Paradise 1105878870 | BUTTE | 2023-04-10 | 2023-09-11 17:00 | 08W | Community Rebuild | 0 | 1.8271 | 0 | 1.8271 | 0 | 0 | 0 | 0 | 0 | 1.8271 | 0 | 1.8271 | 0 | 0 | 0 | 0 | 8.0105
35246598 | 102831105 | PARADISE 1105 | PARADISE 11052214 | BUTTE | 2023-08-14 | 2023-11-17 17:00 | 08W | Community Rebuild | 0 | 2.1311 | 0 | 2.1311 | 0 | 0 | 0 | 0 | 0 | 2.1311 | 0 | 2.1311 | 0 | 0 | 0 | 0 | 7.1516
35226602 | 102831104 | PARADISE 1104 | PARADISE 1104961990 | BUTTE | 2023-04-11 | 2023-04-28 | 95F | Community Rebuild | 0 | 0.092992 | 0 | 0.092992 | 0 | 0 | 0 | 0 | 0 | 0.092992 | 0 | 0.092992 | 0 | 0 | 0 | 0 | 0.4013
35246596 | 102831103 | PARADISE 1103 | PARADISE 1103143744 | BUTTE | 2023-06-05 | 2023-08-13 | 08W | Community Rebuild | 0 | 0.47178 | 0 | 0.47178 | 0 | 0 | 0 | 0 | 0 | 0.47178 | 0 | 0.47178 | 0 | 0 | 0 | 0 | 1.425
35254274 | 102831104 | PARADISE 1104 | PARADISE 110443008 | BUTTE | 2022-10-10 | 2023-08-15 | 95F | Community Rebuild | 0 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0 | 0 | 0 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0 | 0 | 0.15466
35254342 | 102831103 | PARADISE 1103 | PARADISE 11032486 | BUTTE | 2023-01-31 | 2023-07-23 | 95F | Community Rebuild | 0 | 0.045455 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0.045455 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0.21687
35333044 | 102831104 | PARADISE 1104 | PARADISE 1104457900 | BUTTE | 2023-01-26 | 2023-02-15 | 95F | Community Rebuild | 0 | 0.054924 | 0 | 0.054924 | 0 | 0 | 0 | 0 | 0 | 0.054924 | 0 | 0.054924 | 0 | 0 | 0 | 0 | 0.22511
35345874 | 102831104 | PARADISE 1104 | PARADISE 1104457900 | BUTTE | 2023-04-10 | 2023-07-30 | 08W | Community Rebuild | 0 | 0.8072 | 0 | 0.8072 | 0 | 0 | 0 | 0 | 0 | 0.8072 | 0 | 0.8072 | 0 | 0 | 0 | 0 | 3.092
35399500 | 102831104 | PARADISE 1104 | PARADISE 1104954322 | BUTTE | 2023-04-03 | 2023-05-03 | 95F | Community Rebuild | 0 | 0.15189 | 0 | 0.15189 | 0 | 0 | 0 | 0 | 0 | 0.15189 | 0 | 0.15189 | 0 | 0 | 0 | 0 | 0.14049
31437447 | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 110249144 | SHASTA | Not Available | 2022-09-16 | 10I | Other | 0 | 0.1553 | 0 | 0.1553 | 0 | 0 | 0 | 0 | 0 | 0.1553 | 0 | 0.1553 | 0 | 0 | 0 | 0 | Not Available
31533746 | 43432105 | SILVERADO 2105 | SILVERADO 2105247660 | NAPA | 2022-04-28 | 2022-04-28 | 10I | Other | 0 | 0.15814 | 0 | 0.15814 | 0 | 0 | 0 | 0 | 0 | 0.15814 | 0 | 0.15814 | 0 | 0 | 0 | 0 | Not Available
35159243 | 102541101 | VOLTA 1101 | VOLTA 110185234 | TEHEMA | 2021-06-03 | 2022-05-06 | 10H | Other | 0 | 0.95739 | 0 | 0.95739 | 0 | 0 | 0 | 0 | 0 | 0.95739 | 0 | 0.95739 | 0 | 0 | 0 | 0 | Not Available
35219276 | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | SOLANO | 2023-03-16 | 2024-06-30 | 08W | Base SH | 0 | 3.1549 | 0 | 3.1549 | 0 | 0 | 0 | 0 | 0 | 1.0816 | 0 | 1.0816 | 0 | 2.0733 | 0 | 2.0733 | 11.1537
35224712 | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | PLUMAS | 2023-05-31 | 2024-05-10 | 08W | Fire Rebuild | 0 | 2.0761 | 0 | 2.0761 | 0 | 0 | 0 | 0 | 0 | 1.4989 | 0 | 1.4989 | 0 | 0.57727 | 0 | 0.57727 | 12.3133
35224856 | 102831104 | Paradise 1104 | PARADISE 11042034 | BUTTE | 2023-08-15 | 2024-02-29 | 10K | Other | 0.11136 | 2.4278 | 0 | 2.5392 | 0 | 0 | 0 | 0 | 0.11136 | 2.3129 | 0 | 2.4242 | 0 | 0.11496 | 0 | 0.11496 | 10.1758
35277935 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2839 | FRESNO | 2023-06-26 | 2023-11-30 | 08W | Base SH | 0.0041667 | 0.083333 | 0 | 0.0875 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0 | 0.083333 | 0.0041667 | 0 | 0 | 0.0041667 | 0.52479
35283346 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | 2023-06-23 | 2024-06-14 | 08W | Base SH | 0 | 1.4462 | 0 | 1.4462 | 0 | 0 | 0 | 0 | 0 | 0.96799 | 0 | 0.96799 | 0 | 0.47822 | 0 | 0.47822 | 5.4524
35283938 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018974 | SAN MATEO | 2023-09-18 | 2024-05-30 | 08W | Base SH | 0 | 0.84356 | 0 | 0.84356 | 0 | 0 | 0 | 0 | 0 | 0.45341 | 0 | 0.45341 | 0 | 0.39015 | 0 | 0.39015 | 3.9884
35284023 | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | SONOMA | 2023-08-14 | 2024-06-07 | 08W | Fire Rebuild | 0 | 1.3411 | 0 | 1.3411 | 0 | 0 | 0 | 0 | 0 | 0.23977 | 0 | 0.23977 | 0 | 1.1013 | 0 | 1.1013 | 3.4654
35285249 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | LAKE | 2023-07-24 | 2023-11-30 | 08W | Base SH | 0 | 2.3348 | 0 | 2.3348 | 0 | 0 | 0 | 0 | 0 | 2.1686 | 0 | 2.1686 | 0 | 0.16629 | 0 | 0.16629 | 7.3882
35290544 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | PLUMAS | 2023-05-22 | 2024-01-30 | 08W | Fire Rebuild | 0 | 2.0723 | 0 | 2.0723 | 0 | 0 | 0 | 0 | 0 | 2.0521 | 0 | 2.0521 | 0 | 0.020265 | 0 | 0.020265 | 7.8962
35299635 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110247006 | BUTTE | 2023-08-28 | 2024-04-30 | 08W | Base SH | 0 | 2.3348 | 0 | 2.3348 | 0 | 0 | 0 | 0 | 0 | 0.65133 | 0 | 0.65133 | 0 | 1.6835 | 0 | 1.6835 | 5.364
35312540 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | SHASTA | 2023-05-15 | 2024-04-08 | 08W | Base SH | 0.38883 | 4.7848 | 0 | 5.1737 | 0 | 0 | 0 | 0 | 0.38883 | 4.7472 | 0 | 5.136 | 0 | 0.037689 | 0 | 0.037689 | 13.0391
35312543 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-07-10 | 2024-08-31 | 08W | Base SH | 0 | 3.1943 | 0 | 3.1943 | 0 | 0 | 0 | 0 | 0 | 2.9263 | 0 | 2.9263 | 0 | 0.26799 | 0 | 0.26799 | 9.7611
35312560 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | 2023-07-18 | 2024-07-26 | 08W | Base SH | 0 | 2.1254 | 0 | 2.1254 | 0 | 0 | 0 | 0 | 0 | 1.1481 | 0 | 1.1481 | 0 | 0.97727 | 0 | 0.97727 | 9.9914
35316018 | Not Available | Not Available | Not Available | PLUMAS | 2023-05-02 | 2023-12-08 | 95F | Community Rebuild | 0 | 0.6983 | 0 | 0.6983 | 0 | 0 | 0 | 0 | 0 | 0.57102 | 0 | 0.57102 | 0 | 0.12727 | 0 | 0.12727 | Not Available
35320440 | 63601111 | VACAVILLE 1111 | VACAVILLE 1111CB | SOLANO | 2023-06-26 | 2024-11-04 | 08W | Base SH | 0 | 2.5508 | 0 | 2.5508 | 0 | 0 | 0 | 0 | 0 | 1.7053 | 0 | 1.7053 | 0 | 0.84545 | 0 | 0.84545 | 7.5603
35320441 | 63601111 | VACAVILLE 1111 | VACAVILLE 111113652 | SOLANO | 2023-08-07 | 2024-04-12 | 08W | Base SH | 0 | 2.3703 | 0 | 2.3703 | 0 | 0 | 0 | 0 | 0 | 1.918 | 0 | 1.918 | 0 | 0.45227 | 0 | 0.45227 | 7.1185
35320442 | 63801102 | JAMESON 1102 | JAMESON 110265516 | SOLANO | 2023-07-24 | 2024-05-31 | 08W | Base SH | 0.10189 | 0.73826 | 0 | 0.84015 | 0 | 0 | 0 | 0 | 0 | 0.058712 | 0 | 0.058712 | 0.10189 | 0.67955 | 0 | 0.78144 | 4.391
35329013 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022094 | BUTTE | 2023-09-18 | 2024-04-30 | 08W | Base SH | 0.063636 | 1.3754 | 0 | 1.439 | 0 | 0 | 0 | 0 | 0 | 1.3754 | 0 | 1.3754 | 0.063636 | 0 | 0 | 0.063636 | 4.8464
35332360 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | GLENN | 2023-07-31 | 2024-06-30 | 08W | Base SH | 0.81288 | 2.7987 | 0 | 3.6116 | 0 | 0 | 0 | 0 | 0.81288 | 2.2564 | 0 | 3.0693 | 0 | 0.54223 | 0 | 0.54223 | 6.9669
35334754 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-08-07 | 2024-01-12 | 08W | Base SH | 0 | 3.8655 | 0 | 3.8655 | 0 | 0 | 0 | 0 | 0 | 3.8 | 0 | 3.8 | 0 | 0.06553 | 0 | 0.06553 | 8.4413
35334755 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | SOLANO | 2023-07-24 | 2023-11-01 | 08W | Base SH | 0 | 1.0534 | 0 | 1.0534 | 0 | 0 | 0 | 0 | 0 | 1.0371 | 0 | 1.0371 | 0 | 0.016288 | 0 | 0.016288 | 3.564
35335290 | 63601111 | VACAVILLE 1111 | VACAVILLE 111113652 | SOLANO | 2023-08-14 | 2024-02-23 | 08W | Base SH | 0 | 2.5305 | 0 | 2.5305 | 0 | 0 | 0 | 0 | 0 | 1.4413 | 0 | 1.4413 | 0 | 1.0892 | 0 | 1.0892 | 5.6998
35337008 | 103441102 | JESSUP 1102 | JESSUP 11021550 | SHASTA | 2023-06-20 | 2023-10-12 | 08W | Base SH | 0 | 1.5167 | 0 | 1.5167 | 0 | 0 | 0 | 0 | 0 | 1.2125 | 0 | 1.2125 | 0 | 0.30417 | 0 | 0.30417 | 3.818
35343394 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | 2023-08-02 | 2024-07-26 | 08W | Base SH | 0 | 1.2506 | 0 | 1.2506 | 0 | 0 | 0 | 0 | 0 | 0.97027 | 0 | 0.97027 | 0 | 0.2803 | 0 | 0.2803 | 4.3335
35343397 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 1110980944 | BUTTE | 2023-06-12 | 2024-07-26 | 08W | Base SH | 0 | 0.64451 | 0 | 0.64451 | 0 | 0 | 0 | 0 | 0 | 0.39394 | 0 | 0.39394 | 0 | 0.25057 | 0 | 0.25057 | 2.3668
35378609 | Not Available | Not Available | Not Available | PLUMAS | Not Available | 2024-04-07 | 95F | Community Rebuild | 0 | 0.58466 | 0 | 0.58466 | 0 | 0 | 0 | 0 | 0 | 0.062879 | 0 | 0.062879 | 0 | 0.52178 | 0 | 0.52178 | Not Available

## Q1 i-j
CPZs where UG work took place in 2023
CPZ | Customer Count - April 2024 | Sum of PSPS Minutes for Average Customer Outage on CPZ | Sum of PSPS Minutes for Maximum Event Duration on CPZ
EL DORADO PH 210119752 | 1034 | 18427.2075 | 19568.5333
SHINGLE SPRINGS 210935598 | 139 | 8248.4768 | 10600
STANISLAUS 17021804 | 603 | 12820.9199 | 12821
PINE GROVE 11021222 | 675 | 11699.1752 | 15602
CLAYTON 2215184604 | 1593 | 2621 | 2621
STANISLAUS 17021850 | 1054 | 12742.1202 | 12876
CLAYTON 221296224 | 100 | 9178.59 | 9683
TIDEWATER 210614072 | 57 | 2352 | 2352
KIRKER 2104442850 | 7 | 4103 | 4103
MARIPOSA 2102440236 | 495 | N/A | N/A
MIDDLETOWN 1103830 | 105 | 16172.7056 | 17148
BANGOR 1101CB | 186 | 16498.8065 | 16519
MOUNTAIN QUARRIES 2101CB | 290 | N/A | N/A
WILDWOOD 11011454 | 14 | 9875.0625 | 11972
MIDDLETOWN 1101548 | 366 | 20560.4088 | 31284
MIDDLETOWN 110148212 | 129 | 24631.7542 | 25045.55
VACAVILLE 11046542 | 779 | 12290.7566 | 13738
PLACERVILLE 21067522 | 1021 | 18631.2678 | 20257
OREGON TRAIL 110335002 | 786 | 14395 | 14395
MARTELL 1101CB | 891 | 5124 | 5124
CAMP EVERS 210311046 | 345 | 5384.8145 | 6233
VOLTA 1101CB | 52 | 21619.3934 | 21753
VOLTA 110153118 | 24 | 24429 | 24429
VOLTA 11011596 | 136 | 27302 | 27302
UPPER LAKE 11011276 | 166 | 12528 | 12528
DESCHUTES 11041370 | 398 | 11888.665 | 13956
MARIPOSA 210135244 | 107 | N/A | N/A
AUBERRY 1101R2578 | 582 | 3564.8325 | 3905
AUBERRY 1101CB | 334 | 2635 | 2635
STANISLAUS 1701CB | 359 | 9433.5229 | 12740
STANISLAUS 1702CB | 71 | 12315.3333 | 12406
POTTER VALLEY P H 110537476 | 104 | 9406 | 9406
POTTER VALLEY P H 11051904 | 341 | 12897.2089 | 13401
MOUNTAIN QUARRIES 21011350 | 248 | 13881.3761 | 13886
ANDERSON 11031600 | 111 | 13455.5574 | 15604
CLARK ROAD 110281296 | 82 | 22771.9651 | 25132
CLARK ROAD 11022070 | 6 | N/A | N/A
ANDERSON 1103226050 | 276 | 8508.2508 | 11580
CORNING 110253184 | 78 | 18108.0256 | 18112
CORNING 1102915324 | 0 | 15331.0909 | 17551
COTTONWOOD 1102544790 | 40 | 8839.4557 | 12954
CURTIS 1701CB | 629 | 5712.6458 | 5874
ELK CREEK 110193504 | 8 | 7741 | 7741
JESSUP 1103348657 | 18 | N/A | N/A
REDBUD 1101708166 | 87 | 12000 | 12000
ELK CREEK 11012002 | 30 | 9096.7719 | 9118
COTTONWOOD 11029026 | 285 | 10682.035 | 13135
REDBUD 1101754544 | 27 | 13471 | 13471
JESSUP 11021550 | 218 | 14346.3443 | 15036
LINCOLN 11042070 | 276 | 8537.6797 | 8711
VACAVILLE 110838316 | 88 | 15586 | 15586
HORSESHOE 110150140 | 466 | 6765.0211 | 7339
LINCOLN 1104275986 | 0 | 4010 | 4010
JAMESON 1105466348 | 244 | 14150.0859 | 15495
JAMESON 1105371694 | 52 | 9037.2 | 10781
JAMESON 1105913400 | 1 | 4822 | 4822
PANORAMA 1101CB | 502 | 9281.9286 | 12227
FLINT 1101958726 | 85 | 4069.8953 | 7724
CLARK ROAD 1102CB | 12 | 12021.5 | 14876
LINCOLN 1104997576 | 105 | 10543 | 10543
VACAVILLE 11088762 | 152 | 14989.1751 | 16597
JAMESON 11059472 | 131 | 12738.4885 | 14152
OAKHURST 110110090 | 614 | 3740.2525 | 4154
JAMESON 110265516 | 496 | 13971.2727 | 15338
WYANDOTTE 1110980944 | 1108 | 9463.399 | 12614
LINCOLN 1104685276 | 194 | 9410 | 9410
STANISLAUS 17021888 | 656 | 13245.6538 | 14235
BRUNSWICK 110651486 | 1050 | 17127.4848 | 20377
POTTER VALLEY P H 110576498 | 30 | 10926 | 10926
HALF MOON BAY 110369412 | 92 | 6660.6086 | 7556
WYANDOTTE 11031976 | 35 | N/A | N/A
BIG MEADOWS 21012248 | 8 | 2589 | 2589
WILLOW CREEK 11032936 | 257 | 4627 | 4627
SPANISH CREEK 4401CB | 1 | 2676 | 2676
BIG MEADOWS 21012260 | 272 | 2589 | 2589
BIG MEADOWS 21012476 | 155 | 2589 | 2589
BIG MEADOWS 21012586 | 107 | 2589 | 2589
BIG BASIN 110110720 | 176 | 4841 | 4841
BIG BASIN 11022253 | 9 | 7479.8333 | 7927
BIG BASIN 110212758 | 223 | 7889 | 7889
BIG BASIN 110296986 | 78 | 8103.9059 | 8136
BIG BEND 11021972 | 5 | N/A | N/A
KANAKA 1101CB | 108 | 17518.7859 | 19446
MARIPOSA 21019400 | 770 | 7941.1326 | 10569
MARIPOSA 210110240 | 280 | N/A | N/A
MARIPOSA 210110170 | 197 | 6850 | 6850
WYANDOTTE 11031941 | N/A | N/A | N/A
Paradise 110353544 | 78 | 23527.6857 | 23775
PARADISE 110636042 | 277 | 22118.1816 | 22209
PARADISE 1105CB | 66 | 22034 | 22034
Paradise 1106CB | 59 | 20954 | 20954
PARADISE 11042206 | 682 | 24828.1776 | 25087
PARADISE 11032534 | 134 | 21209 | 21209
PARADISE 1103CB | 324 | 23565.3692 | 24441
Paradise 1104CB | 72 | 23147.3133 | 23474
PARADISE 110599226 | 194 | 23868 | 23868
PARADISE 1104920400 | 70 | 24647 | 24647
Paradise 110343008 | 247 | 24223.9099 | 24234
PARADISE 11032486 | 288 | 23710.0161 | 23943
PARADISE 1104409622 | 213 | N/A | N/A
PARADISE 110439216 | 214 | 23845.2979 | 23898
PARADISE 1104457900 | 320 | 24565.9272 | 24777
PARADISE 1104954322 | 139 | 24926.1064 | 24969
Paradise 1105121988 | 131 | 24191 | 24191
Paradise 1105829194 | 365 | 24181.011 | 24189
Paradise 1105878870 | 113 | 23907.918 | 24252
PARADISE 11052214 | 382 | 23842 | 23842
PARADISE 1104961990 | 191 | 24600.8889 | 24630
PARADISE 1103143744 | 28 | N/A | N/A
PARADISE 110443008 | 206 | N/A | N/A
OREGON TRAIL 110249144 | 264 | 8961.6364 | 11675
SILVERADO 2105247660 | 44 | 16916 | 16916
VOLTA 110185234 | 368 | 27624 | 27624
BUCKS CREEK 1101CB | N/A | 27491 | 27491
PARADISE 11042034 | 99 | 25029.8182 | 25096
AUBERRY 1101R2839 | 132 | 2732 | 2732
WOODSIDE 11018974 | 298 | 10212.9838 | 10497
DUNBAR 1101416 | 21 | N/A | N/A
CLARK ROAD 110247006 | 94 | 26585.4571 | 29590
VACAVILLE 1111CB | 691 | 9354.4637 | 9919
VACAVILLE 111113652 | 74 | 10039.4296 | 10345
CLARK ROAD 11022094 | N/A | N/A | N/A

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program tracked in PG&E's Maintenance Activity Type (MAT) 08W. May include underground, overhead hardening and line removal projects.
Community Rebuild | Specific Fire Rebuild projects outside a High Fire Threat District (HFTD) currently associated with the Dixie and Camp fires in the county of Butte (towns of Paradise, Magalia) and Plumas (city of Greenville) .
Fire Rebuild | System Hardening work as a result of fires in an HFTD.
Other | Non-rebuild, base system hardening or targeted undergrounding projects in HFTD that are new business, Work Requested by Others (WRO), capacity upgrades, Rule 20A, etc.
MAT Code
MAT Code | Description
08W | System Hardening Wildfire Resiliency Projects
10H | Work Requested by Others - Rule 20B
10I | Work Requested by Others - Rule 20C
10J | Work Requested by Others - Overhead Relocation
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
3UG | Targeted Undergrounding
49M | Preinstalled Interconnection Hubs / Microgrids: non-gen
95F | Electric Distribution Major Emergency